RESTRICTED // CDN // NOFORN

SPRINTER-CLASS TACTICAL UAV

PARTS PROCUREMENT PACKAGE

Logistics and Sustainment Baseline for Canadian UCAS Program

────────────────────

Document No.: CDR-SPRSTRK-PPP-001  |  Revision: Baseline 1.0

Date: June 2026

Prepared for: Canadian Unmanned Combat Air System Program Office

CRITICAL DESIGN REVIEW TECHNICAL BASELINE

# Table of Contents

Right-click and select "Update Field" to refresh page numbers

Executive Summary	3

Part I: Platform Overview and Sustainment Philosophy	5

1.1 Sprinter Platform Summary	5

1.2 Sustainment Concept	6

Part II: Spare Parts and Consumables	8

2.1 Spare Parts Calculation Methodology	8

2.2 Sprinter Spare Parts List	9

2.3 Attrition Reserve Airframes	14

Part III: Ground Support Equipment (GSE)	15

Part IV: Training Systems	19

Part V: Weapons and Munitions Stockpile	21

Part VI: Maintenance and Repair Infrastructure	23

Part VII: Personnel and Manning	25

Part VIII: Cost Summary	27

Part IX: Risk Assessment and Mitigation	30

Part X: Recommendations and Implementation Timeline	32

Appendices	34

# Executive Summary

This Parts Procurement Package (PPP) defines the complete logistics and sustainment baseline for the Sprinter-class Tactical UAV, an attritable, frontal-aspect low-observable unmanned combat air vehicle designed for high-speed penetration of defended airspace. This document translates the Critical Design Review (CDR) technical baseline (CDR-SPRSTRK-001-BL, Part I) into actionable procurement requirements covering all spare parts, consumables, ground support equipment, training systems, weapons, and sustainment infrastructure necessary to field, operate, and maintain a fleet of 72 operational Sprinters over a 30-day high-intensity campaign and a 10-year service life.

## Bottom Line

The total procurement cost for the complete Sprinter sustainment package is estimated at USD $1,847.2 million (CAD $2,494.7 million at 1.35 exchange rate), comprising airframe procurement, spare parts, ground support equipment, training systems, weapons stockpile, and facilities infrastructure. Annual sustainment cost is estimated at USD $142.8 million (CAD $192.8 million). The 10-year lifecycle cost totals USD $3,275.0 million (CAD $4,421.3 million), which represents 35.4% of the total Gripen-plus-drone program cost of $9.24 billion CAD.

Operational availability target: 85% for the operational fleet during high-intensity operations, supported by a tiered supply chain with forward-deployed spares at four Main Operating Bases (MOBs), regional depot capability in Canada, and OEM support from Williams International (engine) and other key suppliers.

## Summary Table of Major Cost Categories

| Category | Cost (USD M) | Cost (CAD M) | % of Total |
| --- | --- | --- | --- |
| Sprinter Airframes (128 total) | 768.0 | 1,036.8 | 41.6% |
| Spare Parts and Consumables | 312.5 | 421.9 | 16.9% |
| Ground Support Equipment | 185.3 | 250.2 | 10.0% |
| Training Systems | 127.8 | 172.5 | 6.9% |
| Weapons and Munitions | 246.4 | 332.6 | 13.4% |
| Facilities (Depot + 4 MOBs) | 142.2 | 192.0 | 7.7% |
| Initial Support/CLS | 65.0 | 87.8 | 3.5% |
| TOTAL PROCUREMENT | 1,847.2 | 2,493.8 | 100.0% |

## Key Risk Areas

•  Single-source engine supplier (Williams International) — Mitigation: Strategic spares stockpile and dual-source qualification for Lot 10+

•  RAM material availability — Proprietary iron-ball formulation with limited suppliers; Mitigation: 24-month forward buy

•  Long lead times for composite structures (16-24 weeks) — Mitigation: Pre-positioned spares and production slot reservations

•  Arctic cold-weather impact on spares degradation — Mitigation: Heated storage, CS-RAM qualification, shelf-life monitoring

•  8-12% per-sortie attrition in contested environments — Mitigation: 33% attrition reserve (24 airframes), production surge capacity

# Part I: Platform Overview and Sustainment Philosophy

## 1.1 Sprinter Platform Summary

The Sprinter-class Tactical UAV is an attritable, frontal-aspect low-observable unmanned combat air vehicle designed for short-duration, high-intensity missions requiring supersonic dash capability. The design philosophy prioritizes frontal-aspect stealth, speed over endurance, and affordability over full-spectrum survivability.

### Key Performance Parameters

| Parameter | Value |
| --- | --- |
| Designation | Sprinter-class Tactical UAV |
| Role | High-speed decoy; ISR snapshot; electronic attack; SEAD/DEAD |
| Maximum Speed | Mach 1.6 (1,960 km/h) |
| Dash Speed (sustained) | Mach 1.5-1.6 for 5-6 minutes |
| Combat Range | 440 nm (815 km) with dash profile |
| Mission Endurance | 45-60 minutes typical |
| Payload Capacity | 250 kg internal bay (MIL-STD-1760) |
| Frontal RCS (X-band) | -20 dBsm (0.010 m²) |
| Design Life | 500 flight hours / 200 missions |
| Unit Cost (Lot 20) | USD $6.0M (EW variant) |

### Force Structure

The recommended inventory to sustain a 72-aircraft operational force through a 30-day high-intensity campaign:

| Category | Quantity | Notes |
| --- | --- | --- |
| Operational Fleet | 72 | Available for tasking |
| Training Aircraft | 12 | Dedicated to crew training |
| Depot Maintenance | 8 | ~10% of fleet in deep maintenance |
| Attrition Reserve | 24 | 33% buffer for combat losses |
| War Reserve | 12 | Strategic reserve, flyable storage |
| TOTAL PROCUREMENT | 128 | Sustained operational force |

## 1.2 Sustainment Concept

### Attritable Design Philosophy

The Sprinter is designed for a 500 flight-hour / 200-mission life. It is not intended for indefinite sustainment. This fundamentally changes the sustainment approach — the aircraft is replaced rather than repeatedly overhauled. Fatigue-life tracking, depot-level structural inspection, and complex life-limited part management are eliminated. Instead, sustainment focuses on:

•  Rapid turnaround between sorties (target: 30 minutes at -30°C)

•  Modular LRU replacement at field level

•  Replacement airframe procurement to match attrition

•  Engine overhaul at 500 flight hours (calendar limit: 5 years for elastomer seals)

### Supply Chain Strategy

Tiered supply chain architecture with three echelons:

•  Tier 1 — Forward-Deployed Spares: Mission-essential LRUs and consumables stored at each MOB (4 locations) to support 72 hours of high-tempo operations without resupply

•  Tier 2 — Regional Depot: Full spares inventory, engine overhaul, RAM refurbishment, and structural inspection at Mirabel, QC (primary) and Halifax, NS (alternate)

•  Tier 3 — OEM Support: Williams International (engine), Toray/Hexcel (composites), Honeywell (INS/GPS), CAE (training systems) with CLS agreements

### Maintenance Concept

Two-level maintenance — no intermediate level:

•  Field-Level Maintenance: LRU swap, refuel, rearm, inspect. Six-person crew per shift (2 avionics, 2 airframe, 2 ordnance). Standard tool kit: composite repair kit, portable NDI, RAM tile bonding kit, MIL-STD-1760 test set.

•  Depot-Level Maintenance: Engine overhaul (hot-section inspection, bearing replacement), full structural inspection (ultrasonic C-scan), RAM refurbishment and reapplication, avionics calibration and repair, landing gear overhaul. Interval: every 200 flight hours or annually. Duration: 5 calendar days.

### Operational Availability Target

85% Ao (Availability) for the operational fleet during high-intensity operations. This translates to 61 of 72 operational aircraft available for tasking at any given time. The target is achievable given:

•  30-minute combat turnaround validated through Arctic Gripen baselining

•  3.5 sorties per aircraft per day at high tempo

•  Modular LRU swap minimizing mean time to repair (MTTR)

•  24-airframe attrition reserve (33% of operational fleet)

•  8-airframe depot maintenance pool (~10%)

# Part II: Spare Parts and Consumables

## 2.1 Spare Parts Calculation Methodology

Spare parts quantities are calculated using a multi-factor methodology based on reliability engineering principles, operational tempo analysis, and campaign modeling derived from the Arctic Horizon war-gaming study (CDR-WARGAME-2026-002).

### Failure Rate Data

Mean Time Between Failures (MTBF) for each Line Replaceable Unit (LRU) is drawn from the CDR technical specifications (CDR-SPRSTRK-001-BL) and MIL-HDBK-217F calculations:

| LRU | MTBF (hours) | Source |
| --- | --- | --- |
| Flight Control Computer (FCC) | 25,000 | MIL-HDBK-217F, Ground Fixed, 25°C |
| Electrohydrostatic Actuator (EHA) | 18,000 | Including motor drive electronics |
| Air Data Module | 30,000 | Flush port pressure transducers |
| Rate Gyro Assembly | 35,000 | MEMS-based, tri-axial |
| Accelerometer Assembly | 40,000 | Piezoelectric, tri-axial |
| Servo Control Valve | 22,000 | Hydraulic valve only |
| FOHE (Fuel-to-Oil Heat Exchanger) | 12,000 | Estimated via preliminary analysis |

### Operational Tempo

At high-intensity operations:

•  3.5 sorties per aircraft per day x 72 aircraft = 252 sorties/day

•  Average sortie duration: 44 minutes (0.73 flight hours)

•  Daily flight hours: 252 sorties x 0.73 FH = 183.96 FH/day

•  30-day campaign total: 5,519 flight hours

•  10-year service life total: ~66,000 flight hours (6,000 FH/year at sustained tempo)

### Attrition Accounting

Loss rates per the Arctic Horizon war-gaming analysis:

•  Strike missions (S-400 environment): 8-12% loss per sortie

•  Patrol missions (fighter encounters): 2-5% loss per sortie

•  Anti-shipping: 0-2% loss per sortie

•  Air defence: 1-3% loss per sortie

•  Multi-vector defence: 12-18% loss per sortie

•  Weighted average across mission mix (60% strike, 30% ISR, 10% training): ~7.2% per sortie in contested environment

Attrition removes aircraft from the fleet and reduces spares demand for the lost airframe, but surviving aircraft accumulate flight hours faster as the fleet shrinks. The 24-airframe attrition reserve (33% of operational fleet) provides adequate buffer for a 30-day campaign at 7.2% average loss rate.

### Confidence Level

All spares quantities are calculated at 90% confidence using Poisson demand distribution. The formula: Spares Quantity = POISSON.INV(0.90, lambda), where lambda = (Operating Hours / MTBF) x Units in Service. For campaign-duration spares, operating hours = campaign FH. For initial provisioning, 10-year demand is calculated.

## 2.2 Sprinter Spare Parts List

The following tables present the complete spare parts list organized by subsystem. All quantities are calculated at 90% confidence level for the 128-airframe procurement (72 operational + 12 training + 8 depot + 24 attrition reserve + 12 war reserve). Unit costs are based on Lot 20 production learning curve (Crawford model, 85% slope).

### A. Airframe and Structure

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares Qty | Unit Cost (USD) | Total Cost (USD) | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Composite wing skin panel (L) | 1560-01-XXX-0001 | SPRW-SKIN-001-L | T800H/3900-2, 8-ply QI carbon-epoxy, left | 1 | 18 | $28,500 | $513,000 | 16 wks | Bombardier |
| Composite wing skin panel (R) | 1560-01-XXX-0002 | SPRW-SKIN-001-R | T800H/3900-2, 8-ply QI carbon-epoxy, right | 1 | 18 | $28,500 | $513,000 | 16 wks | Bombardier |
| Fuselage shell (upper) | 1560-01-XXX-0003 | SPRW-FUSE-001-U | Snap-fit longitudinal half, OOA cured | 1 | 14 | $42,000 | $588,000 | 20 wks | Bombardier |
| Fuselage shell (lower) | 1560-01-XXX-0004 | SPRW-FUSE-001-L | Snap-fit longitudinal half, OOA cured | 1 | 14 | $42,000 | $588,000 | 20 wks | Bombardier |
| Leading edge assembly (L) | 1560-01-XXX-0005 | SPRW-LE-001-L | Ti-matrix composite (Ti-6Al-4V facesheets) | 1 | 10 | $18,500 | $185,000 | 12 wks | Bombardier |
| Leading edge assembly (R) | 1560-01-XXX-0006 | SPRW-LE-001-R | Ti-matrix composite (Ti-6Al-4V facesheets) | 1 | 10 | $18,500 | $185,000 | 12 wks | Bombardier |
| RAM tile set (forward fuselage) | 5850-01-XXX-0001 | SPRW-RAM-001-F | Iron-ball magnetic RAM, 12mm, X-band opt. | 1 set | 22 | $8,200 | $180,400 | 8 wks | [Vendor consult] |
| RAM tile set (wing LE) | 5850-01-XXX-0002 | SPRW-RAM-001-W | Iron-ball magnetic RAM, 20mm, high-curvature | 1 set | 18 | $12,400 | $223,200 | 8 wks | [Vendor consult] |
| Elevon assembly (L) | 1560-01-XXX-0007 | SPRW-ELV-001-L | Full-span elevon with Ti hinges | 1 | 8 | $15,800 | $126,400 | 10 wks | Bombardier |
| Elevon assembly (R) | 1560-01-XXX-0008 | SPRW-ELV-001-R | Full-span elevon with Ti hinges | 1 | 8 | $15,800 | $126,400 | 10 wks | Bombardier |
| Air brake assembly | 1560-01-XXX-0009 | SPRW-BRK-001 | Drag brake, dual-panel, CMC trailing edge | 1 | 6 | $9,400 | $56,400 | 10 wks | Bombardier |
| Nose landing gear strut | 1620-01-XXX-0001 | SPRW-NLG-001 | Oleo-pneumatic, 150mm stroke, AerMet 100 | 1 | 10 | $22,000 | $220,000 | 14 wks | [Vendor consult] |
| Main landing gear strut (each) | 1620-01-XXX-0002 | SPRW-MLG-001 | Oleo-pneumatic, 200mm stroke, 1,400kg cap | 2 | 12 | $26,500 | $318,000 | 14 wks | [Vendor consult] |
| Landing gear wheel (nose) | 1630-01-XXX-0001 | SPRW-WHL-001-N | 400mm dia, carbon-carbon brake disc | 1 | 8 | $3,800 | $30,400 | 6 wks | Michelin |
| Landing gear wheel (main) | 1630-01-XXX-0002 | SPRW-WHL-001-M | 500mm dia, carbon-carbon brake disc | 2 | 12 | $4,200 | $50,400 | 6 wks | Michelin |
| Weapons bay door (upper) | 1560-01-XXX-0010 | SPRW-BAY-001-U | Serrated trailing edge, curved profile | 1 | 6 | $7,800 | $46,800 | 10 wks | Bombardier |
| Weapons bay door (lower) | 1560-01-XXX-0011 | SPRW-BAY-001-L | Serrated trailing edge, curved profile | 1 | 6 | $7,800 | $46,800 | 10 wks | Bombardier |
| DSI inlet duct assembly | 1560-01-XXX-0012 | SPRW-INT-001 | Serpentine S-curve, 30° over 1.2m, RAM-lined | 1 | 8 | $35,000 | $280,000 | 18 wks | Bombardier |
| Nozzle assembly (2D shrouded) | 1560-01-XXX-0013 | SPRW-NOZ-001 | Ti-6Al-4V petals, CMC TBC, 3:1 aspect ratio | 1 | 8 | $28,000 | $224,000 | 14 wks | [Vendor consult] |
| Fastener kit (primary) | 5305-01-XXX-0001 | SPRW-FST-001 | NAS6704-XX Ti tension bolts (x24), Hi-Lok collars | 1 kit | 25 | $2,400 | $60,000 | 4 wks | StandardAero |
| Fastener kit (secondary) | 5305-01-XXX-0002 | SPRW-FST-002 | NAS5161U Ti screws (x180), access panels | 1 kit | 25 | $1,800 | $45,000 | 4 wks | StandardAero |
|  |  |  |  |  | SUBTOTAL AIRFRAME |  | $4,793,000 |  |  |

### B. Propulsion System

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares Qty | Unit Cost (USD) | Total Cost (USD) | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Complete engine | 2840-01-XXX-0001 | SPRW-ENG-001 | Williams FJ44-4M derivative, 25kN class | 1 | 12 | $850,000 | $10,200,000 | 24 wks | Williams Int'l |
| Engine FADEC unit | 5998-01-XXX-0001 | SPRW-FAD-001 | Dual-redundant, ARINC 429, MIL-STD-810H | 1 | 8 | $45,000 | $360,000 | 12 wks | Williams Int'l |
| Fuel pump assembly | 2910-01-XXX-0001 | SPRW-FP-001 | High-pressure gear pump, JP-8 compatible | 1 | 8 | $12,500 | $100,000 | 8 wks | [Vendor consult] |
| Fuel control unit | 2910-01-XXX-0002 | SPRW-FCU-001 | Hydromechanical, FADEC-scheduled | 1 | 6 | $28,000 | $168,000 | 10 wks | [Vendor consult] |
| Oil pump assembly | 2910-01-XXX-0003 | SPRW-OP-001 | Pressure + scavenge, 15 L/min | 1 | 6 | $8,400 | $50,400 | 8 wks | [Vendor consult] |
| FOHE | 2940-01-XXX-0001 | SPRW-FOHE-001 | Plate-fin counterflow, 42kW, 4.2kg | 1 | 10 | $6,200 | $62,000 | 6 wks | [Vendor consult] |
| Ignition exciter | 2925-01-XXX-0001 | SPRW-IGN-001 | Capacitor discharge, 25kV | 1 | 8 | $4,500 | $36,000 | 6 wks | [Vendor consult] |
| Igniter plug (each) | 2925-01-XXX-0002 | SPRW-IGN-002 | Platinum-iridium electrode | 2 | 16 | $850 | $13,600 | 4 wks | [Vendor consult] |
| Starter/generator | 2925-01-XXX-0003 | SPRW-SG-001 | 40 kVA, 28VDC/115VAC 400Hz | 1 | 8 | $18,500 | $148,000 | 10 wks | [Vendor consult] |
| Inlet guide vanes (set) | 2840-01-XXX-0002 | SPRW-IGV-001 | stages 1-4, Ti-6Al-4V | 1 set | 6 | $15,000 | $90,000 | 12 wks | Williams Int'l |
| Compressor blades (set) | 2840-01-XXX-0003 | SPRW-CBL-001 | Stages 1-4, Ti-matrix composite | 1 set | 6 | $22,000 | $132,000 | 14 wks | Williams Int'l |
| Turbine blades (set) | 2840-01-XXX-0004 | SPRW-TBL-001 | Stages 1-2, Inconel 718 single-crystal | 1 set | 6 | $38,000 | $228,000 | 16 wks | Williams Int'l |
| Turbine vanes (set) | 2840-01-XXX-0005 | SPRW-TVN-001 | Stages 1-2, CMC | 1 set | 6 | $24,500 | $147,000 | 14 wks | Williams Int'l |
| Combustor liner | 2840-01-XXX-0006 | SPRW-CMB-001 | Segmented, film-cooled, CMC insert | 1 | 6 | $18,000 | $108,000 | 12 wks | Williams Int'l |
| Engine bearings (set) | 3110-01-XXX-0001 | SPRW-BRG-001 | Main + thrust, ceramic hybrid | 1 set | 8 | $5,200 | $41,600 | 8 wks | SKF Aerospace |
| Carbon face seals (set) | 5330-01-XXX-0001 | SPRW-SEAL-001 | Engine oil seals, 5-year calendar life | 1 set | 10 | $2,800 | $28,000 | 6 wks | [Vendor consult] |
|  |  |  |  |  | SUBTOTAL PROPULSION |  | $11,912,600 |  |  |

### C. Avionics and Flight Control

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares Qty | Unit Cost (USD) | Total Cost (USD) | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mission computer | 5998-01-XXX-0002 | SPRW-MC-001 | Dual Nvidia Jetson AGX Orin, 550 TOPS, 64GB | 1 | 10 | $35,000 | $350,000 | 8 wks | Nvidia/CAE |
| Flight control computer | 5998-01-XXX-0003 | SPRW-FCC-001 | Quad-redundant, dissimilar (PPC+ARM), DO-178C | 1 | 10 | $45,000 | $450,000 | 10 wks | CAE |
| INS/GPS unit | 5998-01-XXX-0004 | SPRW-INS-001 | Honeywell HG1930 RLG, 0.6nm/hr drift | 1 | 8 | $95,000 | $760,000 | 12 wks | Honeywell |
| Air data module | 5998-01-XXX-0005 | SPRW-ADM-001 | Flush pressure sensors, 5-hole probe | 1 | 8 | $12,500 | $100,000 | 8 wks | [Vendor consult] |
| Rate gyro assembly | 5998-01-XXX-0006 | SPRW-GYRO-001 | MEMS tri-axial, 200Hz | 1 | 6 | $4,200 | $25,200 | 6 wks | [Vendor consult] |
| Accelerometer assembly | 5998-01-XXX-0007 | SPRW-ACC-001 | Piezoelectric tri-axial | 1 | 6 | $3,800 | $22,800 | 6 wks | [Vendor consult] |
| Servo control valve (each) | 4810-01-XXX-0001 | SPRW-SCV-001 | Hydraulic, 4,000psi, 5-micron filter | 6 | 20 | $6,800 | $136,000 | 8 wks | [Vendor consult] |
| EHA (elevon, each) | 5998-01-XXX-0008 | SPRW-EHA-001 | Electrohydrostatic, 18,000hr MTBF | 4 | 14 | $18,500 | $259,000 | 10 wks | [Vendor consult] |
| EHA (air brake, each) | 5998-01-XXX-0009 | SPRW-EHA-002 | Electrohydrostatic, 18,000hr MTBF | 2 | 8 | $18,500 | $148,000 | 10 wks | [Vendor consult] |
| ARINC 429 bus coupler | 5998-01-XXX-0010 | SPRW-ARINC-001 | 4-channel, 100kbaud, transformer iso | 4 | 12 | $1,200 | $14,400 | 4 wks | [Vendor consult] |
| Power distribution unit | 5998-01-XXX-0011 | SPRW-PDU-001 | 28VDC/115VAC 400Hz, solid-state contactors | 1 | 8 | $8,500 | $68,000 | 6 wks | [Vendor consult] |
|  |  |  |  |  | SUBTOTAL AVIONICS |  | $2,333,400 |  |  |

### D. Sensors

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares Qty | Unit Cost (USD) | Total Cost (USD) | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EO/IR turret | 5855-01-XXX-0001 | SPRW-EOIR-001 | Wescam MX-10 derivative, retractable, 3-axis | 1 | 8 | $185,000 | $1,480,000 | 16 wks | L3Harris/CAE |
| ESM receiver | 5996-01-XXX-0001 | SPRW-ESM-001 | 2-18GHz, -70dBm, IFM+CVR architecture | 1 | 8 | $285,000 | $2,280,000 | 20 wks | MDA |
| ESM antenna (each) | 5996-01-XXX-0002 | SPRW-ANT-001 | Conformal Archimedean spiral, 2-turn | 4 | 16 | $8,500 | $136,000 | 8 wks | MDA |
| AESA radar (optional) | 5895-01-XXX-0001 | SPRW-AESA-001 | Leonardo Osprey derivative, 256 T/R, X-band | 1 | 4 | $320,000 | $1,280,000 | 24 wks | Leonardo/MDA |
| Laser rangefinder | 5855-01-XXX-0002 | SPRW-LRF-001 | 1.55µm eye-safe, 20km range | 1 | 6 | $12,500 | $75,000 | 8 wks | [Vendor consult] |
| Radar altimeter | 5998-01-XXX-0012 | SPRW-ALT-001 | 0-2,500ft AGL, ±2ft accuracy | 1 | 6 | $8,200 | $49,200 | 6 wks | [Vendor consult] |
| Vision-aided nav camera | 5998-01-XXX-0013 | SPRW-VNAV-001 | Downward-looking mono, DTED Level 3 | 1 | 6 | $6,800 | $40,800 | 6 wks | [Vendor consult] |
| Pitot-static probe (each) | 1560-01-XXX-0014 | SPRW-PSP-001 | Flush, heated, MIL-STD-810H | 2 | 10 | $2,400 | $24,000 | 6 wks | [Vendor consult] |
|  |  |  |  |  | SUBTOTAL SENSORS |  | $5,365,000 |  |  |

### E. Communications and Datalink

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares Qty | Unit Cost (USD) | Total Cost (USD) | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TTNT datalink radio | 5820-01-XXX-0001 | SPRW-TTNT-001 | MANET waveform, 5.03-5.091GHz, 10Mbps | 1 | 8 | $65,000 | $520,000 | 12 wks | [Vendor consult] |
| TTNT antenna (top) | 5820-01-XXX-0002 | SPRW-TANT-001-T | 16-element conformal phased array | 1 | 6 | $12,500 | $75,000 | 8 wks | MDA |
| TTNT antenna (bottom) | 5820-01-XXX-0003 | SPRW-TANT-001-B | 16-element conformal phased array | 1 | 6 | $12,500 | $75,000 | 8 wks | MDA |
| Link 16 terminal | 5820-01-XXX-0004 | SPRW-L16-001 | Receive-only, JTIDS/MIDS compatible | 1 | 6 | $25,000 | $150,000 | 10 wks | [Vendor consult] |
| Encryption module | 5810-01-XXX-0001 | SPRW-ENC-001 | AES-256 + CRYSTALS-Kyber, NSA Type-1 | 1 | 8 | $18,500 | $148,000 | 8 wks | [Vendor consult] |
| Datalink processor | 5998-01-XXX-0014 | SPRW-DLP-001 | Packet routing, waveform management | 1 | 6 | $8,200 | $49,200 | 6 wks | CAE |
|  |  |  |  |  | SUBTOTAL COMMS |  | $1,017,200 |  |  |

### F. Payload Bay Modules (Mission Pallets)

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares Qty | Unit Cost (USD) | Total Cost (USD) | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| EW pallet (complete) | 5865-01-XXX-0001 | SPRW-EWP-001 | DRFM 4-18GHz, 200W ERP, decoy repeater | 1 | 14 | $280,000 | $3,920,000 | 16 wks | MDA |
| DRFM processor | 5865-01-XXX-0002 | SPRW-EWP-002 | Digital RF memory, <100ms reaction | 1 | 8 | $85,000 | $680,000 | 12 wks | MDA |
| EW amplifier module | 5865-01-XXX-0003 | SPRW-EWP-003 | GaN SSPA, 200W ERP per sub-band | 1 | 6 | $42,000 | $252,000 | 10 wks | [Vendor consult] |
| ISR pallet (complete) | 5865-01-XXX-0004 | SPRW-ISRP-001 | Line-scan + SIGINT 0.5-18GHz + relay | 1 | 12 | $220,000 | $2,640,000 | 16 wks | L3Harris/CAE |
| Line-scan camera | 5865-01-XXX-0005 | SPRW-ISRP-002 | 0.15m GSD at 40kft/M1.5, 4k lines/s | 1 | 6 | $65,000 | $390,000 | 10 wks | [Vendor consult] |
| SIGINT receiver | 5865-01-XXX-0006 | SPRW-ISRP-003 | 0.5-18GHz, 2GHz IBW, -90dBm | 1 | 6 | $95,000 | $570,000 | 12 wks | MDA |
| A2A pallet (complete) | 1410-01-XXX-0001 | SPRW-A2AP-001 | 2x CUDA missile integration kit | 1 | 10 | $180,000 | $1,800,000 | 12 wks | CAE |
| A2G pallet (complete) | 1410-01-XXX-0002 | SPRW-A2GP-001 | 1x GBU-69/B SGM integration kit | 1 | 10 | $95,000 | $950,000 | 10 wks | CAE |
| Pallet interface adapter | 5998-01-XXX-0015 | SPRW-PIA-001 | MIL-STD-1760 mechanical + electrical | 1 | 20 | $8,500 | $170,000 | 6 wks | CAE |
| Chaff dispenser | 5865-01-XXX-0007 | SPRW-DISP-001 | ALE-70 compatible, 16x RR-180 | 1 | 16 | $6,200 | $99,200 | 6 wks | [Vendor consult] |
| Flare dispenser | 5865-01-XXX-0008 | SPRW-DISP-002 | ALE-70 compatible, 8x MJU-68 | 1 | 16 | $5,800 | $92,800 | 6 wks | [Vendor consult] |
|  |  |  |  |  | SUBTOTAL PAYLOAD |  | $11,564,000 |  |  |

### G. Electrical and Environmental Systems

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares Qty | Unit Cost (USD) | Total Cost (USD) | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Starter/generator | 2925-01-XXX-0003 | SPRW-SG-001 | 40 kVA, 28VDC/115VAC 400Hz | 1 | 8 | $18,500 | $148,000 | 10 wks | [Vendor consult] |
| Li-ion battery | 6140-01-XXX-0001 | SPRW-BAT-001 | 5kWh, 30-min emergency power, -55°C rated | 1 | 10 | $12,500 | $125,000 | 8 wks | [Vendor consult] |
| Ram Air Turbine | 2915-01-XXX-0001 | SPRW-RAT-001 | Deployable, 8kW at M0.5+ | 1 | 6 | $22,000 | $132,000 | 10 wks | [Vendor consult] |
| Power distribution bus | 5998-01-XXX-0011 | SPRW-PDU-001 | Dual-redundant, auto load shedding | 1 | 8 | $8,500 | $68,000 | 6 wks | [Vendor consult] |
| ECS pump | 4310-01-XXX-0001 | SPRW-ECS-001 | 4 L/min dual-redundant, glycol/water | 1 | 8 | $4,200 | $33,600 | 6 wks | [Vendor consult] |
| ECS heat exchanger | 4310-01-XXX-0002 | SPRW-ECS-002 | Fuel-to-coolant, 12kW capacity | 1 | 8 | $6,800 | $54,400 | 6 wks | [Vendor consult] |
| Coolant (ethylene glycol/water) | 6850-01-XXX-0001 | SPRW-COOL-001 | 50/50 mix, -60°C pour point | 20L | 40 | $85/L | $3,400 | 2 wks | Standard |
|  |  |  |  |  | SUBTOTAL ELEC/ENV |  | $564,400 |  |  |

### H. Consumables (Per Sortie / Per Flight Hour)

Consumable quantities are calculated for the 30-day high-intensity campaign at 252 sorties/day. For 10-year sustainment, multiply annual quantities by 10.

| Consumable | Unit | Consumption Rate | 30-Day Campaign Total | Unit Cost | 30-Day Total Cost | Annual Cost | 10-Year Cost |
| --- | --- | --- | --- | --- | --- | --- | --- |
| JP-8 fuel | kg | 195 kg/sortie | 1,469,280 kg | $0.90/kg | $1,322,352 | $16,074,240 | $160,742,400 |
| Hydraulic fluid (MIL-PRF-83282) | liters | 0.15 L/FH | 828 L | $45.00/L | $37,260 | $452,520 | $4,525,200 |
| Lubricating oil (Mobil Jet Oil II) | liters | 0.08 L/FH | 442 L | $28.50/L | $12,597 | $153,009 | $1,530,090 |
| Grease (MIL-G-81322) | grams | 5 g/sortie | 37,680 g | $0.12/g | $4,522 | $54,918 | $549,180 |
| Nitrogen (aviation grade) | L STP | 0.5 L/sortie | 3,768 L | $0.08/L | $301 | $3,656 | $36,560 |
| Chaff cartridges (RR-180) | each | Up to 16/sortie | 120,960 | $185/each | $22,377,600 | $27,158,400 | $271,584,000 |
| Flare cartridges (MJU-68) | each | Up to 8/sortie | 60,480 | $245/each | $14,817,600 | $17,980,800 | $179,808,000 |
| Oxygen (aviation breather) | liters | 0.2 L/sortie | 1,508 L | $0.15/L | $226 | $2,745 | $27,450 |
| De-icing fluid (Type IV) | liters | 12 L/sortie (Arctic) | 90,720 L | $12.50/L | $1,134,000 | $13,770,000 | $137,700,000 |
| Wiper blades (pitot covers) | each | 0.001/sortie | 76 | $85/each | $6,460 | $78,423 | $784,230 |
|  |  |  |  | TOTAL | $39,712,918 | $75,648,711 | $757,287,110 |

Note: Chaff and flare consumption assumes every sortie expends full countermeasure load. Actual consumption will be lower (estimated 40-60% of maximum). Weapons bay pallets contain pre-loaded countermeasure magazines; resupply occurs during pallet swap. De-icing fluid consumption is highly weather-dependent and assumes Arctic winter operations.

## 2.3 Attrition Reserve Airframes

Twenty-four (24) attrition reserve airframes are procured as complete flyable aircraft, representing 33% of the operational fleet of 72. This reserve is sized to sustain a 30-day high-intensity campaign at the weighted average loss rate of 7.2% per sortie.

Cost: 24 x $6.0M = $144.0M USD (included in total airframe procurement).

Storage: Attrition reserve airframes are preserved in flyable storage condition at the Mirabel depot facility. Each aircraft is stored with:

•  Engine preservation: desiccant bags, corrosion inhibitor (Mobil Jet Oil II fogging), sealed intakes/exhausts

•  Fuel system: purged with nitrogen, fuel lines capped

•  Avionics: stored in climate-controlled shelter (15°C, 45% RH)

•  Composites: UV protective covers, monthly inspection for moisture ingress

•  RAM tiles: protective film, quarterly reflectometry check

•  Rotation: Each reserve aircraft rotated through training pipeline every 6 months to verify systems integrity and maintain battery charge

Surge Production Capacity: In the event attrition exceeds the 24-airframe reserve, production surge at Bombardier Mirabel can deliver replacement aircraft at a rate of 4 per month ( Lot 20+ tooling), with first delivery 10 weeks from order.

# Part III: Ground Support Equipment (GSE)

Ground Support Equipment is sized for four Main Operating Bases (MOBs): CFB Cold Lake (AB), CFB Bagotville (QC), CFB Goose Bay (NL), and Thule/Pituffik (GL). Each MOB supports 18 operational Sprinters (1.5 per assigned Gripen). All GSE is rated for -55°C Arctic operation unless otherwise specified.

## 3.1 Aircraft Handling

| Item | Description | Qty per MOB | Total Qty (4 MOBs) | Unit Cost (USD) | Total Cost (USD) | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Aircraft tow bar (nose gear) | Heated grips, -55°C steel alloy, 3.5m length | 4 | 16 | $2,400 | $38,400 | [Vendor consult] |
| Wheel chocks (cold-weather) | Rubber composite, -55°C rated, 8 per set | 8 sets | 32 sets | $485/set | $15,520 | [Vendor consult] |
| Tie-down kit (Arctic wind) | Rated to 150kt gusts, ice screws, 4-point | 8 | 32 | $1,850 | $59,200 | [Vendor consult] |
| LG safety pins/covers | Nose + main, red anodized aluminum | 12 | 48 | $320 | $15,360 | [Vendor consult] |
| Engine intake cover | Insulated, -55°C, quick-fit | 6 | 24 | $680 | $16,320 | [Vendor consult] |
| Exhaust cover (insulated) | CMC blanket, -55°C, quick-fit | 6 | 24 | $520 | $12,480 | [Vendor consult] |
| Aircraft jack (hydraulic) | 3-ton capacity, -55°C hydraulic fluid | 4 | 16 | $18,500 | $296,000 | [Vendor consult] |
| Maintenance stands | Adjustable, heated platform, composite-safe | 6 | 24 | $8,200 | $196,800 | [Vendor consult] |

## 3.2 Refueling and Servicing

| Item | Description | Qty per MOB | Total Qty (4 MOBs) | Unit Cost (USD) | Total Cost (USD) | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Single-point refueling truck | JP-8, 5,000L, heated, -55°C rated | 2 | 8 | $285,000 | $2,280,000 | [Vendor consult] |
| Fuel filtration unit | Water separation, 5-micron absolute | 2 | 8 | $42,000 | $336,000 | [Vendor consult] |
| Fuel sampling kit | Contamination detection, cold-rated | 4 | 16 | $3,800 | $60,800 | [Vendor consult] |
| Oil servicing cart (heated) | Mobil Jet Oil II, 100L capacity, -55°C | 2 | 8 | $18,500 | $148,000 | [Vendor consult] |
| Hydraulic fluid cart (heated) | MIL-PRF-83282, 50L, -55°C rated | 2 | 8 | $22,000 | $176,000 | [Vendor consult] |
| Nitrogen servicing cart | Aviation grade, regulator, -55°C | 2 | 8 | $12,500 | $100,000 | [Vendor consult] |
| Grease dispensing equipment | Heated reservoir, MIL-G-81322, -40°C | 4 | 16 | $4,200 | $67,200 | [Vendor consult] |

## 3.3 Weapons and Payload Handling

| Item | Description | Qty per MOB | Total Qty (4 MOBs) | Unit Cost (USD) | Total Cost (USD) | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Weapons loading cart | MIL-STD-1760 compatible, hydraulic lift | 2 | 8 | $65,000 | $520,000 | CAE |
| Hoist assembly (payload bay) | 500kg capacity, 10-min swap capability | 2 | 8 | $28,500 | $228,000 | [Vendor consult] |
| Munitions storage container | Temperature-controlled, -55 to +60°C | 12 | 48 | $8,500 | $408,000 | [Vendor consult] |
| Chaff/flare reloading cart | ALE-70 compatible, heated shelter | 2 | 8 | $18,500 | $148,000 | [Vendor consult] |
| Pallet swap cart | Hydraulic, 250kg capacity, 10-min swap | 4 | 16 | $12,500 | $200,000 | CAE |

## 3.4 Power and Starting

| Item | Description | Qty per MOB | Total Qty (4 MOBs) | Unit Cost (USD) | Total Cost (USD) | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Ground Power Unit (GPU) | 28VDC/115VAC 400Hz, 60kVA, -55°C | 4 | 16 | $85,000 | $1,360,000 | [Vendor consult] |
| Battery charging/test unit | Li-ion, 5kWh, diagnostic capability | 4 | 16 | $12,500 | $200,000 | [Vendor consult] |
| Engine starting cart | Emergency pre-heat, -55°C rated | 2 | 8 | $45,000 | $360,000 | Williams Int'l |
| External power cables | 100ft, -55°C rated insulation | 8 | 32 | $1,850 | $59,200 | [Vendor consult] |

## 3.5 Environmental and De-icing

| Item | Description | Qty per MOB | Total Qty (4 MOBs) | Unit Cost (USD) | Total Cost (USD) | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Heated aircraft shelter | Portable, 15x12m, -55°C, diesel heater | 4 | 16 | $285,000 | $4,560,000 | [Vendor consult] |
| Aircraft heater (forced air) | 100,000 BTU, -55°C rated | 4 | 16 | $42,000 | $672,000 | [Vendor consult] |
| De-icing vehicle | Type IV fluid, heated, 2,000L capacity | 2 | 8 | $185,000 | $1,480,000 | [Vendor consult] |
| Ice detection/removal kit | Scrapers, heated pads, IR thermometer | 4 | 16 | $3,200 | $51,200 | [Vendor consult] |
| Avionics bay purge unit | Dry air, heated, -55°C dewpoint | 2 | 8 | $18,500 | $148,000 | [Vendor consult] |

## 3.6 Maintenance and Inspection

| Item | Description | Qty per MOB | Total Qty (4 MOBs) | Unit Cost (USD) | Total Cost (USD) | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Composite repair kit | Vacuum bagging, heat blankets, -55°C | 4 | 16 | $28,500 | $456,000 | Bombardier |
| Ultrasonic NDI gauge | Pulse-echo, composite thickness measurement | 2 | 8 | $45,000 | $360,000 | Olympus/NDT |
| Eddy current inspection unit | Conductivity, crack detection | 2 | 8 | $38,000 | $304,000 | Olympus/NDT |
| Digital radiography unit | Portable X-ray, composite/RAM inspection | 1 | 4 | $125,000 | $500,000 | [Vendor consult] |
| RAM tile bonding kit | Heated application tools, adhesive film | 4 | 16 | $8,200 | $131,200 | [Vendor consult] |
| Torque wrench set (calibrated) | -55°C rated, 5-200 Nm range, certified | 4 | 16 | $6,800 | $108,800 | [Vendor consult] |
| Specialized tool kit | Composite-safe, carbon fiber tools preferred | 4 | 16 | $12,500 | $200,000 | Snap-on/Bombardier |
| Maintenance work platforms | Adjustable, heated, 2-person | 6 | 24 | $8,500 | $204,000 | [Vendor consult] |
| LED lighting towers | Portable, 360°, -55°C rated battery | 4 | 16 | $4,200 | $67,200 | [Vendor consult] |

## 3.7 Communications and Mission Planning

| Item | Description | Qty per MOB | Total Qty (4 MOBs) | Unit Cost (USD) | Total Cost (USD) | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Ground Control Station (GCS) | Deployable, ruggedized, TTNT, -40°C | 2 | 8 | $485,000 | $3,880,000 | CAE |
| Mission planning workstation | Software + hardware, threat analysis | 4 | 16 | $65,000 | $1,040,000 | CAE |
| TTNT ground antenna (LOS) | Phased array, 200nm range, -55°C | 2 | 8 | $125,000 | $1,000,000 | MDA |
| Secure comms equipment | Encrypted voice/data, STU-V compatible | 4 | 16 | $28,500 | $456,000 | [Vendor consult] |

## GSE Total Cost Summary

| Category | Total Cost (USD) |
| --- | --- |
| 3.1 Aircraft Handling | $649,280 |
| 3.2 Refueling and Servicing | $3,167,520 |
| 3.3 Weapons/Payload Handling | $1,504,000 |
| 3.4 Power and Starting | $1,979,200 |
| 3.5 Environmental/De-icing | $6,961,200 |
| 3.6 Maintenance/Inspection | $2,331,200 |
| 3.7 Comms/Mission Planning | $6,376,000 |
| TOTAL GSE | $22,968,400 |

# Part IV: Training Systems

## 4.1 Training Philosophy

The Sprinter training program is designed to produce qualified operators, maintainers, and mission planners on an accelerated timeline consistent with the attritable nature of the platform. Training emphasizes operational proficiency over deep technical expertise, leveraging the platform's high-autonomy design and simplified maintenance concept.

### Initial Training Pipeline

•  Pilot/Safety Pilot: 4-week conversion course for existing military pilots (any airframe). Covers GCS operation, emergency recovery procedures, manual override, and lost-link protocols.

•  Mission Planner: 3-week course for fighter pilots or weapons officers. Covers mission planning software, threat analysis, AI behavior tuning, corridor planning, and Gripen integration.

•  Maintainer: 6-week course for aviation technicians. Covers composite repair, avionics troubleshooting, RAM maintenance, LRU replacement, and cold-weather procedures.

### Recurrent Training

Annual proficiency requirements: 40 hours simulator currency for operators, 24 hours for maintainers, 16 hours for mission planners. Quarterly team exercises with Gripen integration.

## 4.2 Training Equipment

| Item | Description | Qty | Unit Cost (USD) | Total Cost (USD) | Supplier |
| --- | --- | --- | --- | --- | --- |
| Full-mission simulator (FMS) | High-fidelity Sprinter + Gripen integration, dome display, motion base | 2 | $12,500,000 | $25,000,000 | CAE |
| Sprinter GCS simulator | Ground control station trainer, identical hardware/software | 4 | $1,850,000 | $7,400,000 | CAE |
| Maintenance training devices | Physical airframe section, engine cutaway, avionics rack | 6 | $485,000 | $2,910,000 | CAE/Bombardier |
| Mission planning trainer | Software-based, threat library, AI tuning sandbox | 4 | $125,000 | $500,000 | CAE |
| e-Learning modules | CBT for all systems, 200+ hours content | 1 system | $680,000 | $680,000 | CAE |
| Composite repair trainer | OOA curing station, sample panels, inspection tools | 2 | $85,000 | $170,000 | Bombardier |
| Arctic operations trainer | Cold chamber (-55°C), survival equipment, cold-start procedures | 1 | $2,200,000 | $2,200,000 | CAE |
| Classroom/conference facilities | 20-seat, video teleconference, classified processing | 4 rooms | $285,000 | $1,140,000 | [Vendor consult] |
|  |  | TOTAL |  | $40,000,000 |

## 4.3 Training Personnel Requirements

| Role | Qty | Source | Training Duration | Annual Salary (USD) |
| --- | --- | --- | --- | --- |
| Instructor Pilot (Sprinter/GCS) | 8 | RCAF + CAE contract | 6-week IP course | $125,000 |
| Instructor Pilot (Gripen) | 12 | RCAF | Standard IP qual | $125,000 |
| Simulator operator/maintainer | 6 | RCAF/contractor | 4-week qual | $85,000 |
| Training administrator | 4 | RCAF/contractor | 2-week orientation | $72,000 |
| Curriculum developer | 3 | CAE contractor | 6-month development | $95,000 |

Total initial training cohort: 48 Gripen pilots, 24 Sprinter operators, 16 mission planners, 48 maintainers, 12 ordnance specialists. All personnel complete Arctic familiarization at Cold Lake prior to operational assignment.

# Part V: Weapons and Munitions Stockpile

## 5.1 Weapons Procurement Strategy

The Sprinter employs palletized internal carriage with four mission configurations: Electronic Warfare (EW), Intelligence/Surveillance/Reconnaissance (ISR), Air-to-Air (A2A), and Air-to-Ground (A2G). Weapon procurement is sized for the 72-aircraft operational fleet conducting 252 sorties/day at high tempo.

Peacetime inventory: Sufficient for 30 days of training and patrol operations at reduced tempo (1.5 sorties/AC/day).

Surge inventory for 30-day campaign: Maximum-rate consumption at 252 sorties/day with full countermeasure and weapons expenditure.

Replacement rate: Post-campaign resupply to restore both peacetime and surge inventory within 60 days.

## 5.2 Weapons List

| Weapon | Description | Unit Cost (USD) | Peacetime Qty | Campaign Qty | Total Qty | Total Cost (USD) | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CUDA missile | Compact A2A, 30km, Mach 3.5, active radar | $285,000 | 48 | 144 | 192 | $54,720,000 | Raytheon/Kratos |
| AIM-9X Block III | WVR A2A, IIR + active radar, HOBS | $485,000 | 24 | 48 | 72 | $34,920,000 | Raytheon |
| GBU-69/B SGM | Small glide munition, 70km, GPS/INS+laser | $125,000 | 36 | 216 | 252 | $31,500,000 | [Vendor consult] |
| Chaff (RR-180) | Brass-coated glass fiber, programmable | $185 | 4,320 | 120,960 | 125,280 | $23,176,800 | [Vendor consult] |
| Flare (MJU-68) | Mg/Teflon, 2-sec burn, IR decoy | $245 | 2,160 | 60,480 | 62,640 | $15,346,800 | [Vendor consult] |
| SPEAR 3 (Striker) | Mini-cruise, 140km, multi-mode (noted for completeness) | $485,000 | 0 | 0 | 0 | $0 | MBDA |
|  |  |  |  |  | TOTAL | $159,663,600 |  |

Note: SPEAR 3 and SDB are Striker weapons; listed for completeness only. Sprinter A2G missions employ GBU-69/B SGM exclusively. GBU-69/B quantity assumes 30% of A2G sorties against point targets. Chaff/flare quantities assume full-load expenditure per EW sortie; actual consumption 40-60% of maximum.

## 5.3 Weapons Storage and Handling

All live weapons storage complies with CF Ammunition Storage and Transport Regulations (CF AST Regs) and NATO STANAG 4324. Requirements per MOB:

•  Secure magazine: 500m² minimum, blast-resistant construction, climate-controlled (5-25°C)

•  Lightning protection: NFPA 780 compliant, class I division 1

•  Intrusion detection: Perimeter sensors, CCTV, armed response

•  Fire suppression: CO2 + foam, automatic activation, manual override

•  Environmental monitoring: Temperature, humidity, air quality, 24/7 recording

# Part VI: Maintenance and Repair Infrastructure

## 6.1 Depot-Level Maintenance Facility

Primary depot location: Mirabel Aerospace Centre, Quebec (Bombardier facility). Secondary/alternate: IMP Aerospace, Halifax, NS. The depot provides full structural inspection, RAM refurbishment, avionics calibration and repair, engine overhaul, landing gear overhaul, and control surface rigging.

### Facility Specifications

| Requirement | Specification | Cost (USD) |
| --- | --- | --- |
| Heated hangar | 10,000 sq ft min, 18°C maintained, 15-ton crane | $45,200,000 |
| Cleanroom (RAM application) | Class 7, 2,000 sq ft, 22°1°C, 50±5% RH | $12,500,000 |
| Environmental chamber | -60°C to +70°C, full aircraft profile | $8,200,000 |
| Engine test cell | 25kN thrust class, noise attenuation, FADEC ground rig | $18,500,000 |
| Composite repair shop | OOA curing ovens, 5-axis CNC, NDI suite | $6,800,000 |
| Avionics repair shop | ESD-controlled, 3,000 sq ft, test benches | $4,200,000 |
| Paint/RAM application booth | Spray booth, robotic traverse, cure oven | $5,500,000 |
| Tooling and jigs | Wing, fuselage, engine fixtures, alignment tools | $3,800,000 |
| IT infrastructure | Classified network, logistics management, diagnostics | $2,400,000 |
|  | TOTAL DEPOT FACILITY | $107,100,000 |

## 6.2 Field-Level Maintenance Facilities (per MOB)

Four MOBs: Cold Lake (AB), Bagotville (QC), Goose Bay (NL), Thule/Pituffik (GL). Each provides LRU swap, minor RAM repair, minor composite repair, refueling/rearming, and pre/post-flight inspections.

| Requirement | Specification | Cost per MOB (USD) |
| --- | --- | --- |
| Heated maintenance hangar | 5,000 sq ft min, 15°C maintained | $8,500,000 |
| Weapons storage/handling area | Secure magazine, 200m², blast-rated | $2,200,000 |
| Fuel storage and dispensing | 50,000L JP-8, single-point, filtration | $1,850,000 |
| Parts storage (heated) | 500m², 15°C, environmentally controlled | $1,200,000 |
| Crew facilities | Heated rest areas, -55°C rated, 24-person | $2,800,000 |
|  | TOTAL PER MOB | $16,550,000 |

Total for 4 MOBs: $66,200,000

## 6.3 Forward Operating Location (FOL) Kits

Deployable maintenance kits for austere forward bases. Six kits procured (two per MOB, plus two spares). Each kit supports 72 hours of autonomous operations.

| Item | Description | Qty per Kit | Unit Cost (USD) | Kit Total |
| --- | --- | --- | --- | --- |
| Portable shelter (heated) | 5x4m, diesel heater, -55°C rated | 2 | $18,500 | $37,000 |
| Tool kit (composite-safe) | Carbon fiber tools, torque wrenches, NDI basic | 1 | $12,500 | $12,500 |
| LRU spares (mission-essential) | FCC, EHA, FADEC, TTNT radio, battery | 1 set | $185,000 | $185,000 |
| Fuel (pre-positioned) | JP-8, 10,000L in collapsible bladder | 1 | $12,500 | $12,500 |
| Oil (pre-positioned) | Mobil Jet Oil II, 200L | 1 | $5,800 | $5,800 |
| Comms equipment | Field radio, TTNT relay, satellite backhaul | 1 | $45,000 | $45,000 |
| Generator | 30kVA, diesel, -55°C rated | 1 | $28,500 | $28,500 |
| Tie-down/anchoring kit | 150kt rated, permafrost anchors | 4 | $1,200 | $4,800 |
|  |  | KIT TOTAL |  | $331,100 |

Total FOL program (6 kits): $1,986,600

# Part VII: Personnel and Manning

## 7.1 Personnel Requirements

Manning is calculated for four MOBs with 18 operational Sprinters each, plus depot maintenance and training pipeline. All positions include 25% personnel redundancy to cover leave, training, and illness.

| Role | Per MOB | Total (4 MOBs) | Depot/Other | Total Personnel | Training | Source |
| --- | --- | --- | --- | --- | --- | --- |
| Gripen Pilots | 12 | 48 | 0 | 48 | 4 wks | RCAF |
| Sprinter Operators | 6 | 24 | 0 | 24 | 4 wks | RCAF |
| Mission Planners | 4 | 16 | 0 | 16 | 3 wks | RCAF |
| Avionics Technicians | 8 | 32 | 8 | 40 | 6 wks | RCAF/contractor |
| Airframe Technicians | 8 | 32 | 6 | 38 | 6 wks | RCAF/contractor |
| Ordnance Specialists | 6 | 24 | 4 | 28 | 6 wks | RCAF/contractor |
| Engine Mechanics | 4 | 16 | 6 | 22 | 6 wks | RCAF/contractor |
| Quality Assurance | 2 | 8 | 4 | 12 | 4 wks | RCAF/contractor |
| Logistics/Supply | 4 | 16 | 6 | 22 | 3 wks | RCAF/contractor |
| Flight Safety Officers | 2 | 8 | 2 | 10 | 4 wks | RCAF |
| Administration | 4 | 16 | 4 | 20 | 2 wks | RCAF/contractor |
|  |  |  |  | 280 |  |  |

## 7.2 Training Pipeline

### Initial Training

Location: CFB Cold Lake (primary), CAE Montreal (simulator). Duration: 12 weeks total including Arctic familiarization.

•  Weeks 1-4: Ground school — Sprinter systems, autonomy framework, datalink architecture, weapons integration

•  Weeks 5-8: Simulator phase — GCS operation, emergency procedures, mission planning, Gripen coordination

•  Weeks 9-10: Live flying — Supervised operations from Cold Lake, day/night, cold weather

•  Weeks 11-12: Arctic familiarization — Cold Lake winter operations, -40°C procedures, survival training

### Recurrent Training

•  Quarterly: 8-hour simulator session per operator, tactics review, AI behavior updates

•  Annually: 40-hour simulator currency, live flying (12 sorties), weapons certification

•  Biennially: Arctic deployment exercise (2 weeks), full-spectrum operations

### Instructor Requirements

Instructor pilots: 8 (4 per FMS location, 2 per shift). Minimum qualification: 500 Sprinter flight hours, IP school graduate. Instructor maintainers: 6 (2 per training location).

# Part VIII: Cost Summary

## 8.1 Total Procurement Cost (Phase 1)

| Category | Cost (USD) | Cost (CAD) |
| --- | --- | --- |
| Sprinter airframes (128 total) | $768,000,000 | $1,036,800,000 |
| Spare parts (90% confidence) | $37,085,000 | $50,064,750 |
| Consumables (initial 30-day stock) | $39,712,918 | $53,612,439 |
| Ground support equipment | $22,968,400 | $31,007,340 |
| Training systems | $40,000,000 | $54,000,000 |
| Weapons and munitions | $159,663,600 | $215,545,860 |
| Facilities (depot + 4 MOBs) | $175,286,600 | $236,636,910 |
| Initial support/CLS contract | $65,000,000 | $87,750,000 |
| FOL kits (6 deployable) | $1,986,600 | $2,681,910 |
| Contingency (10%) | $151,070,312 | $203,944,921 |
| TOTAL PROCUREMENT (Phase 1) | $1,661,773,430 | $2,243,394,130 |

Exchange rate: 1.35 CAD/USD. Figures rounded to nearest thousand.

## 8.2 Annual Sustainment Cost

| Category | Cost (USD/year) | Cost (CAD/year) |
| --- | --- | --- |
| Spare parts replenishment | $8,500,000 | $11,475,000 |
| Consumables (fuel, oil, etc.) | $28,500,000 | $38,475,000 |
| Depot maintenance (airframes + engines) | $32,400,000 | $43,740,000 |
| Field maintenance labor | $18,200,000 | $24,570,000 |
| RAM refurbishment | $5,400,000 | $7,290,000 |
| Training and exercises | $4,800,000 | $6,480,000 |
| Contractor logistics support (CLS) | $15,000,000 | $20,250,000 |
| Facilities O&M (depot + MOBs) | $8,500,000 | $11,475,000 |
| Personnel (280 staff) | $22,800,000 | $30,780,000 |
| Insurance and admin | $2,400,000 | $3,240,000 |
| Contingency (8%) | $11,840,000 | $15,984,000 |
| TOTAL SUSTAINMENT/year | $158,340,000 | $213,759,000 |

## 8.3 Lifecycle Cost (10 Years)

| Category | Cost (USD) | Cost (CAD) |
| --- | --- | --- |
| Procurement (Phase 1) | $1,661,773,430 | $2,243,394,130 |
| Annual sustainment x 10 | $1,583,400,000 | $2,137,590,000 |
| Attrition replacement (24 AC) | $144,000,000 | $194,400,000 |
| Block II upgrade (2030) | $51,200,000 | $69,120,000 |
| Block III upgrade (2035) | $102,400,000 | $138,240,000 |
| Program management/office | $24,000,000 | $32,400,000 |
| Technology refresh (IT/GSE) | $18,500,000 | $24,975,000 |
| Contingency (5%) | $179,263,672 | $242,005,957 |
| TOTAL LIFECYCLE COST (10yr) | $3,764,537,102 | $5,082,125,087 |

Note: Lifecycle cost represents 38.4% of the total Gripen-plus-drone program cost of $9.24B CAD (saving $5.76B vs. F-35-only). The Sprinter-specific cost of $5.08B CAD (10-year) is the reference figure for program budgeting. Annual operating cost of $213.8M CAD compares favorably with $1.52B CAD for an equivalent F-35 fleet — an 86% reduction.

# Part IX: Risk Assessment and Mitigation

## 9.1 Key Supply Chain Risks

### Risk 1: Single-Source Engine Supplier (Williams International)

Impact: CRITICAL. Williams International is the sole qualified supplier for the FJ44-4M derivative. Any disruption (financial, production, export control) grounds the entire fleet.

Mitigation:

•  Strategic spares stockpile: 12 complete engines (9.4% of fleet), 8 FADEC units, 6 hot-section kits

•  Dual-source qualification: Initiate qualification of Honeywell HTF7000 scaled derivative as alternate by Lot 10 (2029)

•  Engine overhaul capability: Establish in-Canada hot-section inspection and repair at P&WC Montreal

•  Export control contingency: Pre-negotiated export license with 12-month notification clause

Residual Risk: MEDIUM (with mitigation). Time to recover: 24 weeks for spares deployment, 18 months for dual-source production.

### Risk 2: RAM Material Availability

Impact: HIGH. Iron-ball magnetic RAM uses proprietary ferrite formulation with limited qualified suppliers. Cryo-stable variant (CS-RAM) adds rare-earth dysprosium doping, further constraining supply.

Mitigation:

•  24-month forward buy: Lock in raw material supply (nickel-zinc-cobalt ferrite + dysprosium)

•  Domestic production: Qualify Canadian supplier for ferrite powder production (18-month qualification)

•  Strategic stockpile: 22 aircraft-sets of RAM tiles (sufficient for 18 months of operations)

•  Alternative formulation: Research program on iron-nanowire RAM as backup (TRL 4, 5-year development)

Residual Risk: MEDIUM. Time to recover: 8 weeks from stockpile, 6 months from alternate supplier.

### Risk 3: Long Lead Times for Composite Structures

Impact: HIGH. Out-of-autoclave (OOA) cured composite structures require 16-24 week lead time due to tooling availability and cure cycle duration. Contested campaign attrition could exhaust attrition reserve.

Mitigation:

•  Production slot reservations: Guaranteed quarterly production slots at Bombardier Mirabel (4 aircraft/month surge)

•  Subassembly inventory: Pre-position wing spars and fuselage shells at 50% completion (8-week reduction)

•  Second-source qualification: Qualify De Havilland or Viking Air for wing skin production

•  Rapid production: Accelerated cure cycle (HexFlow RTM6) reduces wing assembly time by 35% for Lot 10+

Residual Risk: MEDIUM. Surge production rate: 4 aircraft/month, first delivery 10 weeks from order.

### Risk 4: Arctic Cold-Weather Impact on Spares

Impact: MEDIUM. Sustained operations at -55°C degrade elastomeric seals, battery performance, and hydraulic fluid viscosity. Cold-start cycles increase wear on engine bearings and starter/generator.

Mitigation:

•  CS-RAM qualification: All RAM tiles qualified to -55°C with 2,000 thermal cycle life

•  Arctic-rated consumables: MIL-PRF-83282 hydraulic fluid (pour point -54°C), arctic grease (MIL-G-81322), heated oil carts

•  Heated storage: All spares stored at +15°C minimum; heated shelters for field operations

•  Kalrez seals: FFKM fluorocarbon seals rated to -60°C for fuel system, landing gear, and ECS

Residual Risk: LOW. Arctic qualification exceeds worst-case operational environment.

### Risk 5: Attrition Exceeding Reserve (24 Airframes)

Impact: HIGH. 30-day campaign at 12% per-sortie loss rate (heavily defended environment) consumes 24-airframe reserve by day 14. Multi-vector defence scenarios show 12-18% loss rates.

Mitigation:

•  Surge production: Bombardier Mirabel can deliver 4 replacement aircraft/month at Lot 20+ rates

•  Reduced tempo: From day 15, reduce to 2.5 sorties/AC/day to preserve remaining fleet

•  Reserve allocation: War reserve (12 aircraft) released after attrition reserve depleted

•  Mission profile adjustment: Shift to lower-risk ISR patrol and base defence missions

Residual Risk: MEDIUM. With surge production + war reserve, effective reserve = 36 aircraft (50% of operational fleet).

## 9.2 Risk Summary Matrix

| Risk | Probability | Impact | Score | Mitigation Status |
| --- | --- | --- | --- | --- |
| Single-source engine | MEDIUM | CRITICAL | HIGH | Active — dual-source by 2029 |
| RAM availability | MEDIUM | HIGH | HIGH | Active — 24-mo forward buy |
| Composite lead times | MEDIUM | HIGH | HIGH | Active — production slots reserved |
| Arctic cold-weather | HIGH | MEDIUM | MEDIUM | Mitigated — CS-RAM qualified |
| Attrition exceeding reserve | LOW-MEDIUM | HIGH | MEDIUM | Active — surge capacity |
| Cyber attack on datalink | MEDIUM | HIGH | HIGH | Active — mesh autonomy dev |
| Williams export control | LOW | CRITICAL | MEDIUM | Active — license pre-negotiated |

# Part X: Recommendations and Implementation Timeline

## 10.1 Immediate Actions (2026-2027)

•  Q3 2026: Award GSE and training systems contracts (CAE, Bombardier) — $127.8M combined

•  Q3 2026: Begin initial spares procurement at 90% confidence level — $37.1M

•  Q4 2026: Establish depot-level maintenance facility at Mirabel — $107.1M construction start

•  Q4 2026: Recruit and train initial maintenance cadre (40 personnel) — Cold Lake

•  Q1 2027: Field first training aircraft (12 airframes) to Cold Lake

•  Q1 2027: Establish CLS agreement with Williams International — 5-year, $75M

•  Q2 2027: Complete MOB facility construction at Cold Lake and Bagotville

•  Q2 2027: Begin operator training on GCS simulators

## 10.2 Near-Term Actions (2028-2030)

•  Q1 2028: Achieve Initial Operational Capability (IOC) — 36 operational Sprinters across 2 MOBs

•  Q2 2028: Complete initial spares stockpile at all 4 MOBs

•  Q3 2028: Establish forward-deployed spares at Goose Bay and Thule/Pituffik

•  Q4 2028: Conduct first operational exercise with Gripen integration (Arctic Challenge)

•  Q1 2029: Begin Block II upgrade development (enhanced engine, improved autonomy)

•  Q2 2029: Qualify Honeywell HTF7000 as alternate engine source

•  Q3 2029: Complete domestic RAM production qualification

•  Q4 2029: Refine spares requirements based on first 18 months of operational data

•  Q2 2030: Achieve Full Operational Capability (FOC) — 72 operational Sprinters, all 4 MOBs

•  Q4 2030: First Block II aircraft delivery (+15% thrust, enhanced autonomy)

## 10.3 Long-Term Actions (2031+)

•  2031-2032: Complete Block II fleet upgrade (72 aircraft)

•  2032-2033: Begin export variant development for Nordic/NATO markets

•  2033-2034: Establish second production line for export orders (Australia, Finland)

•  2034-2035: Begin Block III upgrade study (hypersonic booster, directed energy payload)

•  2035+: Sustainment optimization based on 8+ years of actual usage data; transition to predictive maintenance

## 10.4 Critical Path Items

| Item | Duration | Start | Risk Level |
| --- | --- | --- | --- |
| Engine CLS agreement negotiation | 6 months | Q3 2026 | HIGH |
| Mirabel depot facility construction | 18 months | Q4 2026 | MEDIUM |
| First training aircraft delivery | 6 months | Q1 2027 | MEDIUM |
| Operator training (first cohort) | 12 weeks | Q2 2027 | LOW |
| IOC declaration | 18 months | Q1 2028 | MEDIUM |
| FOC declaration | 30 months | Q2 2030 | LOW |

The Sprinter procurement package represents a transformative approach to Canadian air combat capability. By accepting controlled attrition of $6M unmanned platforms in place of risking $89M manned fighters and invaluable aircrew, the program delivers 88% more daily sorties at 25% of the operating cost. The attritable sustainment model — replace rather than repair — simplifies logistics, reduces depot burden, and ensures operational availability remains high even under the most demanding combat conditions.

# Appendices

## Appendix A: Detailed Spare Parts List Summary (Excel-Compatible)

The following summary table consolidates all spare parts quantities and costs for database import. Full detail with NSN, part numbers, specifications, and storage requirements is maintained in the master logistics database (accessible via CDR-SPRSTRK-PPP-001, Enclosure 1).

| Subsystem | Line Items | Total Spares Qty | Total Cost (USD) |
| --- | --- | --- | --- |
| A. Airframe and Structure | 22 | 312 | $4,793,000 |
| B. Propulsion System | 16 | 118 | $11,912,600 |
| C. Avionics and Flight Control | 11 | 108 | $2,333,400 |
| D. Sensors | 8 | 62 | $5,365,000 |
| E. Communications and Datalink | 7 | 48 | $1,017,200 |
| F. Payload Bay Modules | 11 | 104 | $11,564,000 |
| G. Electrical and Environmental | 7 | 56 | $564,400 |
| TOTAL | 82 | 808 | $37,549,600 |

## Appendix B: GSE Technical Specifications

Full GSE technical specifications including environmental ratings, power requirements, dimensions, weight, and MIL-STD compliance certificates are maintained in document CDR-SPRSTRK-PPP-001, Enclosure 2. Key standards invoked:

•  MIL-STD-810H: Environmental Engineering Considerations (all GSE rated to Method 502.6, -55°C)

•  MIL-STD-461G: EMC Requirements for refueling trucks, GPU, and starting carts

•  MIL-PRF-83282: Hydraulic fluid, fire-resistant, synthetic hydrocarbon

•  STANAG 2563: Aircraft ground support equipment interoperability

•  CF TO-00-35A-GEI-001: Canadian Forces aerospace equipment inspection criteria

## Appendix C: Training System Specifications

Training system technical specifications including simulator fidelity requirements, motion base parameters, visual system field-of-view, and software version control are maintained in document CDR-SPRSTRK-PPP-001, Enclosure 3. Key parameters:

•  FMS dome display: 280° H x 140° V, 8K resolution, 120Hz refresh

•  Motion base: 6-DOF, 3.5g peak, 15°/s rate, 60ms latency

•  GCS simulator: Identical hardware/software to operational stations, <50ms latency

•  e-Learning: SCORM 2004 compliant, 200+ hours, classified network hosting

## Appendix D: Facility Requirements

Detailed facility drawings, utility requirements (power, HVAC, communications), security specifications, and environmental compliance documentation are maintained in document CDR-SPRSTRK-PPP-001, Enclosure 4.

•  Depot (Mirabel): 10,000 sq ft hangar + 2,000 sq ft cleanroom + 5,000 sq ft shops + 3,000 sq ft offices

•  MOB (each): 5,000 sq ft hangar + 500 sq ft parts storage + 200 sq ft weapons magazine + 500 sq ft crew facilities

•  All facilities: 400A three-phase power, 100Mbps secure network, fire suppression (FM-200 + water), backup generator (72-hour autonomy)

## Appendix E: Personnel Manning Document

Detailed position descriptions, qualification requirements, training matrices, and manning charts for all 280 personnel are maintained in document CDR-SPRSTRK-PPP-001, Enclosure 5. Manning assumptions:

•  3-shift operations at high tempo (24-hour operations capability)

•  25% personnel redundancy for leave, training, illness coverage

•  6-person field maintenance crew per shift (2 avionics, 2 airframe, 2 ordnance)

•  15:1 maintainer-to-aircraft ratio (industry standard for UAVs: 10-20:1)

## Appendix F: Cost Model Assumptions

The cost model underlying this procurement package uses the following key assumptions. Sensitivity analysis shows total procurement cost varies ±15% under worst-case scenarios.

| Parameter | Value | Basis | Sensitivity |
| --- | --- | --- | --- |
| Exchange rate (CAD/USD) | 1.35 | BoC 2026 forecast | ±0.10 = ±5.2% total |
| Learning curve (airframe) | 85% (Crawford) | Lots 1-20 | Lot delay = +3%/quarter |
| Fuel cost (JP-8) | $0.90/kg | DND fuel contract | ±0.15 = ±2.1% sustainment |
| Attrition rate | 7.2% weighted avg | Arctic Horizon war-game | +3% = +$18M replacement |
| MTBF achievement | 100% of spec | Verified at IOT&E | -20% = +$4.2M spares/year |
| Sustainment inflation | 2.5%/year | Canadian defence CPI | +1% = +$12.8M/10yr |
| Contractor fee | 7% (CPAF) | Standard DND contract | Fixed ceiling |
| Contingency | 10% procurement, 8% sustainment | DND risk guidance | Fixed |

All costs are expressed in constant 2026 USD unless otherwise noted. Escalation to then-year dollars requires application of the Canadian defence-specific inflation index (forecast 2.5% annually).

## Document Certification

This document has been prepared in accordance with Department of National Defence procurement policy and Canadian aerospace standards. All quantities have been calculated using recognized reliability engineering methodologies (MIL-HDBK-217F, MIL-HDBK-472). All costs have been validated against current vendor quotations where available, and estimated using parametric cost models where vendor data is pending.

This procurement package shall be reviewed and updated annually, or within 30 days of any CCB-approved engineering change to the Sprinter baseline.

SPRINTER PROCUREMENT PACKAGE

Logistics and Sustainment Baseline

Canadian Unmanned Combat Air System Program Office

June 2026

RESTRICTED // CDN // NOFORN

CDR-SPRSTRK-PPP-001 | Revision: Baseline 1.0