STRIKER-CLASS

LOYAL WINGMAN UAV

PARTS PROCUREMENT PACKAGE

Logistics and Sustainment Baseline for Canadian UCAS Program

Document No.: CDR-STRKR-PPP-001  |  Revision: Baseline 1.0

Date: June 2026

Prepared for: Canadian Unmanned Combat Air System Program Office

# Table of Contents

Right-click the TOC and select "Update Field" to refresh page numbers

Executive Summary	3

Part I: Platform Overview and Sustainment Philosophy	4

1.1 Striker Platform Summary	5

1.2 Sustainment Concept	6

Part II: Spare Parts and Consumables	7

2.1 Spare Parts Calculation Methodology	8

2.2 Striker Spare Parts List	9

2.3 Attrition Reserve Airframes	10

Part III: Ground Support Equipment (GSE)	11

Part IV: Training Systems	12

Part V: Weapons and Munitions Stockpile	13

Part VI: Maintenance and Repair Infrastructure	14

Part VII: Personnel and Manning	15

Part VIII: Cost Summary	16

Part IX: Risk Assessment and Mitigation	17

Part X: Recommendations and Implementation Timeline	18

Appendices	19

# Executive Summary

This Parts Procurement Package (PPP) defines the complete logistics and sustainment baseline for the Striker-class Loyal Wingman UAV, a survivable, all-aspect stealth unmanned combat air vehicle designed for penetrating precision strike, persistent electronic warfare, and loyal wingman operations. This document translates the Critical Design Review (CDR) technical baseline (CDR-SPRSTRK-001-BL, Part II) into actionable procurement requirements covering all spare parts, consumables, ground support equipment, training systems, weapons, and sustainment infrastructure necessary to field, operate, and maintain a fleet of 36 operational Strikers over a 30-day high-intensity campaign and a 10-year service life.

## Bottom Line

The total procurement cost for the complete Striker sustainment package is estimated at USD $1,523.8 million (CAD $2,057.1 million at 1.35 exchange rate), comprising airframe procurement, spare parts, ground support equipment, training systems, weapons stockpile, and facilities infrastructure. Annual sustainment cost is estimated at USD $118.4 million (CAD $159.8 million). The 10-year lifecycle cost totals USD $2,708.0 million (CAD $3,655.8 million), which represents 29.3% of the total Gripen-plus-drone program cost of $9.24 billion CAD.

Operational availability target: 90% for the operational fleet during high-intensity operations, supported by a tiered supply chain with forward-deployed spares at four Main Operating Bases (MOBs), regional depot capability in Canada, and OEM support from Pratt & Whitney (engine), Boeing (MUM-T autonomy), and other key suppliers.

## Summary Table of Major Cost Categories

| Category | Cost (USD M) | Cost (CAD M) | % of Total |
| --- | --- | --- | --- |
| Striker Airframes (64 total) | 595.2 | 803.5 | 39.1% |
| Spare Parts and Consumables | 285.6 | 385.6 | 18.7% |
| Ground Support Equipment | 168.4 | 227.3 | 11.0% |
| Training Systems | 96.4 | 130.1 | 6.3% |
| Weapons and Munitions | 198.2 | 267.6 | 13.0% |
| Facilities (Depot + 4 MOBs) | 128.6 | 173.6 | 8.4% |
| Initial Support/CLS | 51.4 | 69.4 | 3.4% |
| TOTAL PROCUREMENT | 1,523.8 | 2,057.1 | 100.0% |

## Key Risk Areas

•  Single-source engine supplier (Pratt & Whitney) — Mitigation: Strategic spares stockpile and dual-source qualification for Lot 10+

•  RAM material availability — Proprietary dual-layer formulation with limited suppliers; Mitigation: 24-month forward buy

•  Long lead times for composite structures (20-28 weeks) — Mitigation: Pre-positioned spares and production slot reservations

•  Arctic cold-weather impact on spares degradation — Mitigation: Heated storage, CS-RAM qualification, shelf-life monitoring

•  2-4% per-sortie attrition in contested environments — Mitigation: 33% attrition reserve (12 airframes), production surge capacity

•  Collaborative Combat AI software integration — Mitigation: Boeing CLS agreement, software escrow, phased autonomy rollout

# Part I: Platform Overview and Sustainment Philosophy

## 1.1 Striker Platform Summary

The Striker-class Loyal Wingman UAV is a survivable, all-aspect low-observable unmanned combat air vehicle designed for penetrating precision strike, persistent electronic warfare, and loyal wingman operations in contested airspace. Unlike the attritable Sprinter, the Striker is engineered for multi-mission reuse, with a design life of 800 flight hours / 300 missions and a target loss rate of only 2-4% per sortie in contested environments — a reflection of its comprehensive stealth design and defensive systems.

### Key Performance Parameters

| Parameter | Value |
| --- | --- |
| Designation | Striker-class Loyal Wingman UAV |
| Role | Penetrating precision strike; loyal wingman; persistent EW; air defense |
| Maximum Speed | Mach 1.6 (1,960 km/h) |
| Dash Speed (sustained) | Mach 1.4-1.5 for 3-6 minutes |
| Combat Range | 620 nm (1,148 km) with 30-min loiter |
| Mission Endurance | 90-120 minutes typical; 150 min max |
| Payload Capacity | 450 kg dual internal bays (MIL-STD-1760) |
| Frontal RCS (X-band) | -28 dBsm (0.0016 m²) |
| All-aspect RCS | -18 dBsm lateral / -14 dBsm aft / -16 dBsm top-bottom |
| Design Life | 800 flight hours / 300 missions |
| Unit Cost (Lot 15) | USD $9.3M (survivable configuration) |

### Force Structure

The recommended inventory to sustain a 36-aircraft operational force through a 30-day high-intensity campaign:

| Category | Quantity | Notes |
| --- | --- | --- |
| Operational Fleet | 36 | Available for tasking; 9 per MOB |
| Training Aircraft | 6 | Dedicated to crew training and AI development |
| Depot Maintenance | 4 | ~11% of fleet in deep maintenance at any time |
| Attrition Reserve | 12 | 33% buffer for combat losses over campaign |
| War Reserve | 6 | Strategic reserve, flyable storage |
| TOTAL PROCUREMENT | 64 | Sustained operational force |

## 1.2 Sustainment Concept

### Survivable Design Philosophy

The Striker is designed for an 800 flight-hour / 300-mission life. Unlike the attritable Sprinter, the Striker is intended for reuse across multiple missions, requiring a more traditional sustainment model with fatigue tracking, depot-level inspections at 300-flight-hour intervals, and life-limited part management. The all-aspect stealth design (RCS: -28 dBsm frontal, -18 dBsm lateral, -14 dBsm aft) demands regular RAM refurbishment and careful handling procedures to maintain signature integrity.

### Supply Chain Strategy

Tiered supply chain architecture with three echelons:

•  Tier 1 — Forward-Deployed Spares: Mission-essential LRUs and consumables stored at each MOB (4 locations) to support 72 hours of high-tempo operations without resupply

•  Tier 2 — Regional Depot: Full spares inventory, engine overhaul, RAM refurbishment, and structural inspection at Mirabel, QC (primary) and Halifax, NS (alternate)

•  Tier 3 — OEM Support: Pratt & Whitney (engine), Boeing (MUM-T autonomy, Collaborative Combat AI), Honeywell (INS/GPS), CAE (training systems), MDA (sensors) with CLS agreements

### Maintenance Concept

Two-level maintenance — no intermediate level:

•  Field-Level Maintenance: LRU swap, refuel, rearm, inspect. Eight-person crew per shift (2 avionics, 2 airframe, 2 ordnance, 1 engine mechanic, 1 QA inspector). Standard tool kit: composite repair kit, portable NDI, RAM tile bonding kit (dual-layer), MIL-STD-1760 test set, AESA radar test set.

•  Depot-Level Maintenance: Engine overhaul (hot-section inspection, bearing replacement), full structural inspection (ultrasonic C-scan, radiography, acoustic emission), RAM complete refurbishment and reapplication (dual-layer), avionics calibration and repair (AESA, EODAS, ESM), landing gear overhaul, Collaborative Combat AI software updates. Interval: every 300 flight hours or biennially. Duration: 10 calendar days.

### Operational Availability Target

90% Ao (Availability) for the operational fleet during high-intensity operations. This translates to 32-33 of 36 operational aircraft available for tasking at any given time. The higher availability target (vs. 85% for Sprinter) reflects the Striker's lower loss rate and the greater investment per airframe. The target is achievable given:

•  30-minute combat turnaround validated through Arctic Gripen baselining

•  2.0 sorties per aircraft per day at high tempo

•  Modular LRU swap minimizing mean time to repair (MTTR)

•  12-airframe attrition reserve (33% of operational fleet)

•  4-airframe depot maintenance pool (~11%)

# Part II: Spare Parts and Consumables

## 2.1 Spare Parts Calculation Methodology

Spare parts quantities are calculated using a multi-factor methodology based on reliability engineering principles, operational tempo analysis, and campaign modeling derived from the Arctic Horizon war-gaming study (CDR-WARGAME-2026-002).

### Failure Rate Data

Mean Time Between Failures (MTBF) for each Line Replaceable Unit (LRU) is drawn from the CDR technical specifications (CDR-SPRSTRK-001-BL) and MIL-HDBK-217F calculations. Higher reliability is expected than the Sprinter due to the Striker's more mature design, triple-redundant systems (vs. dual), and longer design life:

| LRU | MTBF (hours) | Source |
| --- | --- | --- |
| Mission Computer (Jetson AGX Orin) | 35,000 | MIL-HDBK-217F, Ground Fixed, 25°C |
| Flight Control Computer (FCC) | 30,000 | MIL-HDBK-217F, diss. processors |
| Electrohydrostatic Actuator (EHA) | 22,000 | Including motor drive electronics |
| INS/GPS Unit (Honeywell HG1930) | 25,000 | Vendor data |
| AESA Radar (600 T/R modules) | 18,000 | Estimated, GaN technology |
| EODAS Processing Unit | 28,000 | MIL-HDBK-217F |
| FADEC (triple-redundant) | 40,000 | P&W vendor data |
| FOHE (Fuel-to-Oil Heat Exchanger) | 15,000 | Estimated via analysis |
| TTNT Datalink Radio | 20,000 | MIL-HDBK-217F |
| ESM Receiver (0.5-40 GHz) | 24,000 | Estimated via analysis |

### Operational Tempo

At high-intensity operations:

•  2.0 sorties per aircraft per day x 36 aircraft = 72 sorties/day

•  Average sortie duration: 99 minutes (1.65 flight hours)

•  Daily flight hours: 72 sorties x 1.65 FH = 118.8 FH/day

•  30-day campaign total: 3,564 flight hours

•  10-year service life total: ~43,200 flight hours (4,320 FH/year at sustained tempo)

### Attrition Accounting

Loss rates per the Arctic Horizon war-gaming analysis (lower than Sprinter due to all-aspect stealth):

•  Strike missions (S-400 environment): 2-4% loss per sortie

•  Patrol missions (fighter encounters): 0.5-1% loss per sortie

•  Anti-shipping: 0-1% loss per sortie

•  Air defence: 0% loss per sortie (Striker not typically committed)

•  Multi-vector defence: 3-5% loss per sortie

•  Weighted average across mission mix (50% strike, 30% patrol, 20% training): ~2.1% per sortie in contested environment

The 12-airframe attrition reserve (33% of operational fleet) provides adequate buffer for a 30-day campaign at 2.1% average loss rate, with projected losses of 2-3 aircraft.

### Confidence Level

All spares quantities are calculated at 90% confidence using Poisson demand distribution. The formula: Spares Quantity = POISSON.INV(0.90, lambda), where lambda = (Operating Hours / MTBF) x Units in Service. For campaign-duration spares, operating hours = campaign FH. For initial provisioning, 10-year demand is calculated.

## 2.2 Striker Spare Parts List

The following tables present the complete spare parts list organized by subsystem. All quantities are calculated at 90% confidence level for the 64-airframe procurement (36 operational + 6 training + 4 depot + 12 attrition reserve + 6 war reserve). Unit costs are based on Lot 15 production learning curve (Crawford model, 85% slope).

### A. Airframe and Structure

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares | Unit Cost | Total Cost | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Composite wing skin panel (L) | 1560-01-XXX-1001 | STRK-SKIN-001-L | T800H/3900-2, 10-ply QI, BMI compatible | 1 | 12 | $42,000 | $504,000 | 20 wks | Bombardier |
| Composite wing skin panel (R) | 1560-01-XXX-1002 | STRK-SKIN-001-R | T800H/3900-2, 10-ply QI, BMI compatible | 1 | 12 | $42,000 | $504,000 | 20 wks | Bombardier |
| Fuselage shell (upper) | 1560-01-XXX-1003 | STRK-FUSE-001-U | BMI high-temp resin, Tg=230°C, snap-fit | 1 | 10 | $58,000 | $580,000 | 24 wks | Bombardier |
| Fuselage shell (lower) | 1560-01-XXX-1004 | STRK-FUSE-001-L | BMI high-temp resin, Tg=230°C, snap-fit | 1 | 10 | $58,000 | $580,000 | 24 wks | Bombardier |
| CMC leading edge (L) | 1560-01-XXX-1005 | STRK-CMC-001-L | Ceramic matrix composite, 230°C sustained | 1 | 8 | $32,000 | $256,000 | 16 wks | Bombardier |
| CMC leading edge (R) | 1560-01-XXX-1006 | STRK-CMC-001-R | Ceramic matrix composite, 230°C sustained | 1 | 8 | $32,000 | $256,000 | 16 wks | Bombardier |
| RAM tile set (dual-layer) | 5850-01-XXX-1001 | STRK-RAM-001 | Magnetic+dielectric dual-layer, 15-28mm | 1 set | 18 | $22,400 | $403,200 | 12 wks | [Vendor consult] |
| Elevon assembly (L) | 1560-01-XXX-1007 | STRK-ELV-001-L | Full-span elevon with Ti hinges, 4.2m² | 1 | 6 | $22,500 | $135,000 | 12 wks | Bombardier |
| Elevon assembly (R) | 1560-01-XXX-1008 | STRK-ELV-001-R | Full-span elevon with Ti hinges, 4.2m² | 1 | 6 | $22,500 | $135,000 | 12 wks | Bombardier |
| LE flap assembly (L, 3-seg) | 1560-01-XXX-1009 | STRK-FLP-001-L | Three-segment leading edge flap, droop 0-25° | 1 | 6 | $18,200 | $109,200 | 12 wks | Bombardier |
| LE flap assembly (R, 3-seg) | 1560-01-XXX-1010 | STRK-FLP-001-R | Three-segment leading edge flap, droop 0-25° | 1 | 6 | $18,200 | $109,200 | 12 wks | Bombardier |
| Air brake assembly | 1560-01-XXX-1011 | STRK-BRK-001 | Ventral split panels, 1.2m² deployed | 1 | 5 | $12,400 | $62,000 | 10 wks | Bombardier |
| Nose landing gear strut | 1620-01-XXX-1001 | STRK-NLG-001 | Oleo-pneumatic, 180mm stroke, AerMet 100 | 1 | 8 | $32,000 | $256,000 | 16 wks | [Vendor consult] |
| Main landing gear strut (ea) | 1620-01-XXX-1002 | STRK-MLG-001 | Oleo-pneumatic, 220mm stroke, 1,800kg cap | 2 | 10 | $38,500 | $385,000 | 16 wks | [Vendor consult] |
| Landing gear wheel (nose) | 1630-01-XXX-1001 | STRK-WHL-001-N | 450mm dia, Michelin Arctic, carbon-carbon brake | 1 | 6 | $5,200 | $31,200 | 8 wks | Michelin |
| Landing gear wheel (main) | 1630-01-XXX-1002 | STRK-WHL-001-M | 550mm dia, Michelin Arctic, carbon-carbon brake | 2 | 10 | $5,800 | $58,000 | 8 wks | Michelin |
| Weapons bay door (port, upper) | 1560-01-XXX-1012 | STRK-BAY-001-PU | Serrated trailing edge, curved profile, RAM-lined | 1 | 5 | $12,400 | $62,000 | 12 wks | Bombardier |
| Weapons bay door (port, lower) | 1560-01-XXX-1013 | STRK-BAY-001-PL | Serrated trailing edge, curved profile, RAM-lined | 1 | 5 | $12,400 | $62,000 | 12 wks | Bombardier |
| Weapons bay door (stbd, upper) | 1560-01-XXX-1014 | STRK-BAY-001-SU | Serrated trailing edge, curved profile, RAM-lined | 1 | 5 | $12,400 | $62,000 | 12 wks | Bombardier |
| Weapons bay door (stbd, lower) | 1560-01-XXX-1015 | STRK-BAY-001-SL | Serrated trailing edge, curved profile, RAM-lined | 1 | 5 | $12,400 | $62,000 | 12 wks | Bombardier |
| S-duct assembly (port) | 1560-01-XXX-1016 | STRK-INT-001-P | Serpentine S-duct, 1.8m, 22.5° turn, RAM-lined | 1 | 6 | $48,000 | $288,000 | 20 wks | Bombardier |
| S-duct assembly (starboard) | 1560-01-XXX-1017 | STRK-INT-001-S | Serpentine S-duct, 1.8m, 22.5° turn, RAM-lined | 1 | 6 | $48,000 | $288,000 | 20 wks | Bombardier |
| 2D TV nozzle assembly | 1560-01-XXX-1018 | STRK-NOZ-001 | TiAl petals, CMC TBC, ±10° vectoring, 4:1 aspect | 1 | 6 | $58,000 | $348,000 | 18 wks | [Vendor consult] |
| Fastener kit (primary) | 5305-01-XXX-1001 | STRK-FST-001 | NAS6704-XX Ti tension bolts (x28), Hi-Lok collars | 1 kit | 20 | $3,200 | $64,000 | 6 wks | StandardAero |
| Fastener kit (secondary) | 5305-01-XXX-1002 | STRK-FST-002 | NAS5161U Ti screws (x220), access panels | 1 kit | 20 | $2,400 | $48,000 | 6 wks | StandardAero |
| SUBTOTAL AIRFRAME |  |  |  |  |  |  | $6,236,800 |  |  |

### B. Propulsion System

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares | Unit Cost | Total Cost | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Complete engine | 2840-01-XXX-1001 | STRK-ENG-001 | P&W PW800 derivative, 36 kN class, BPR 4.5:1 | 1 | 10 | $1,850,000 | $18,500,000 | 28 wks | Pratt & Whitney |
| Engine FADEC unit | 5998-01-XXX-1001 | STRK-FAD-001 | Triple-redundant, ARINC 429, prognostic HUMS | 1 | 8 | $85,000 | $680,000 | 14 wks | Pratt & Whitney |
| Fuel pump assembly | 2910-01-XXX-1001 | STRK-FP-001 | Dual boost pumps, pressure-fed, 250 L/min | 1 | 8 | $18,500 | $148,000 | 10 wks | [Vendor consult] |
| Fuel control unit | 2910-01-XXX-1002 | STRK-FCU-001 | FADEC-scheduled, full-authority digital | 1 | 6 | $42,000 | $252,000 | 12 wks | [Vendor consult] |
| Oil pump assembly | 2910-01-XXX-1003 | STRK-OP-001 | Pressure + scavenge, 20 L/min, triple-redundant | 1 | 6 | $12,400 | $74,400 | 10 wks | [Vendor consult] |
| FOHE | 2940-01-XXX-1001 | STRK-FOHE-001 | Plate-fin counterflow, 65 kW, dual-loop | 1 | 10 | $10,200 | $102,000 | 8 wks | [Vendor consult] |
| Ignition exciter | 2925-01-XXX-1001 | STRK-IGN-001 | Capacitor discharge, 30 kV, dual-channel | 1 | 8 | $8,500 | $68,000 | 8 wks | [Vendor consult] |
| Igniter plug (each) | 2925-01-XXX-1002 | STRK-IGN-002 | Platinum-iridium electrode, 800-hr life | 2 | 18 | $1,200 | $21,600 | 6 wks | [Vendor consult] |
| Starter/generator | 2925-01-XXX-1003 | STRK-SG-001 | 60 kVA, 28VDC/115VAC 400Hz, -55°C rated | 1 | 8 | $32,000 | $256,000 | 12 wks | [Vendor consult] |
| Inlet guide vanes (set) | 2840-01-XXX-1002 | STRK-IGV-001 | Stages 1-5, Ti-6Al-4V, twin inlets | 1 set | 6 | $28,000 | $168,000 | 14 wks | P&W |
| Compressor blades (set) | 2840-01-XXX-1003 | STRK-CBL-001 | Stages 1-5, Ti-matrix composite, OPR 22:1 | 1 set | 6 | $38,000 | $228,000 | 16 wks | P&W |
| Turbine blades (set) | 2840-01-XXX-1004 | STRK-TBL-001 | Stages 1-2, CMSX-4 single-crystal, TBC coated | 1 set | 6 | $72,000 | $432,000 | 20 wks | P&W |
| Turbine vanes (set) | 2840-01-XXX-1005 | STRK-TVN-001 | Stages 1-2, CMC, 1,550°C rated | 1 set | 6 | $42,000 | $252,000 | 18 wks | P&W |
| Combustor liner | 2840-01-XXX-1006 | STRK-CMB-001 | Segmented, film-cooled, CMC insert, low-NOx | 1 | 6 | $32,000 | $192,000 | 14 wks | P&W |
| Engine bearings (set) | 3110-01-XXX-1001 | STRK-BRG-001 | Main + thrust, ceramic hybrid SKF, 800-hr life | 1 set | 8 | $8,500 | $68,000 | 10 wks | SKF Aerospace |
| Engine seals (set) | 5330-01-XXX-1001 | STRK-SEAL-001 | FFKM Kalrez 7075, -55°C rated, 6-yr calendar | 1 set | 10 | $4,200 | $42,000 | 8 wks | [Vendor consult] |
| TV nozzle actuators (pair) | 2840-01-XXX-1007 | STRK-TVA-001 | Electrohydraulic, ±10°, 5°/s slew rate | 1 pair | 6 | $28,000 | $168,000 | 12 wks | [Vendor consult] |
| SUBTOTAL PROPULSION |  |  |  |  |  |  | $21,681,000 |  |  |

### C. Avionics and Flight Control

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares | Unit Cost | Total Cost | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Mission computer | 5998-01-XXX-1002 | STRK-MC-001 | Quad-redundant Jetson AGX Orin, 1,100 TOPS, 128GB | 1 | 10 | $85,000 | $850,000 | 10 wks | Nvidia/CAE |
| Flight control computer | 5998-01-XXX-1003 | STRK-FCC-001 | Quad-redundant, dissimilar (PPC+ARMx2), DO-178C | 1 | 10 | $68,000 | $680,000 | 12 wks | CAE |
| INS/GPS unit | 5998-01-XXX-1004 | STRK-INS-001 | Honeywell HG1930 RLG, 0.6nm/hr drift, 4-constellation | 1 | 8 | $125,000 | $1,000,000 | 14 wks | Honeywell |
| Air data module (FADS) | 5998-01-XXX-1005 | STRK-ADM-001 | 16-port flush pressure system, ±0.3° AoA | 1 | 8 | $28,500 | $228,000 | 10 wks | [Vendor consult] |
| Rate gyro assembly | 5998-01-XXX-1006 | STRK-GYRO-001 | MEMS tri-axial, 400 Hz, -55°C rated | 1 | 6 | $6,800 | $40,800 | 8 wks | [Vendor consult] |
| Accelerometer assembly | 5998-01-XXX-1007 | STRK-ACC-001 | Piezoelectric tri-axial, 400 Hz update | 1 | 6 | $5,800 | $34,800 | 8 wks | [Vendor consult] |
| Servo control valve (each) | 4810-01-XXX-1001 | STRK-SCV-001 | Hydraulic, 4,000 psi, 5-micron filter | 8 | 22 | $8,200 | $180,400 | 10 wks | [Vendor consult] |
| EHA (elevon, each) | 5998-01-XXX-1008 | STRK-EHA-001 | Electrohydrostatic, 22,000-hr MTBF, dual per surface | 4 | 12 | $24,500 | $294,000 | 12 wks | [Vendor consult] |
| EHA (LE flap, each) | 5998-01-XXX-1009 | STRK-EHA-002 | Electrohydrostatic, 22,000-hr MTBF | 4 | 10 | $18,500 | $185,000 | 12 wks | [Vendor consult] |
| EHA (air brake, each) | 5998-01-XXX-1010 | STRK-EHA-003 | Electrohydrostatic, 22,000-hr MTBF | 2 | 8 | $18,500 | $148,000 | 12 wks | [Vendor consult] |
| ARINC 429 bus coupler | 5998-01-XXX-1011 | STRK-ARINC-001 | 8-channel, 100 kbaud, transformer isolated | 4 | 10 | $2,400 | $24,000 | 6 wks | [Vendor consult] |
| MIL-STD-1553B terminal | 5998-01-XXX-1012 | STRK-1553-001 | Dual-redundant, 1 Mbps, BC/RT/BM | 1 | 6 | $12,500 | $75,000 | 8 wks | [Vendor consult] |
| Power distribution unit | 5998-01-XXX-1013 | STRK-PDU-001 | 28VDC/115VAC 400Hz, solid-state contactors, 60kVA | 1 | 8 | $18,500 | $148,000 | 8 wks | [Vendor consult] |
| Collab. Combat AI module | 5998-01-XXX-1014 | STRK-AI-001 | Boeing MUM-T derivative, 50 Hz replanning | 1 | 8 | $185,000 | $1,480,000 | 16 wks | Boeing/CAE |
| SUBTOTAL AVIONICS |  |  |  |  |  |  | $5,388,000 |  |  |

### D. Sensors

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares | Unit Cost | Total Cost | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AESA radar (nose array) | 5895-01-XXX-1001 | STRK-AESA-001 | 600 T/R modules, X-band, 2.4 kW peak, GaN | 1 | 6 | $485,000 | $2,910,000 | 24 wks | MDA/CAE |
| AESA radar power supply | 5998-01-XXX-1015 | STRK-AESA-002 | Liquid-cooled, 3.5 kW avg, 28VDC input | 1 | 6 | $42,000 | $252,000 | 12 wks | MDA |
| AESA radar processor | 5998-01-XXX-1016 | STRK-AESA-003 | SAR/GMTI beamformer, 16-bit ADC, 3 GS/s | 1 | 6 | $68,000 | $408,000 | 14 wks | MDA |
| EODAS aperture (each) | 5855-01-XXX-1001 | STRK-EODAS-001 | IR-transparent window, FSS coating, RF stealth | 5 | 16 | $22,500 | $360,000 | 14 wks | MDA |
| EODAS processing unit | 5998-01-XXX-1017 | STRK-EODAS-002 | Missile warning, spherical coverage, 4π steradian | 1 | 6 | $125,000 | $750,000 | 16 wks | MDA |
| ESM receiver | 5996-01-XXX-1001 | STRK-ESM-001 | 0.5-40 GHz, -80 dBm, 5,000-emitter library | 1 | 6 | $385,000 | $2,310,000 | 20 wks | MDA |
| ESM antenna (each) | 5996-01-XXX-1002 | STRK-ANT-001 | Conformal spiral, flush-mounted, dual-pol | 6 | 14 | $12,500 | $175,000 | 10 wks | MDA |
| SIGINT receiver | 5996-01-XXX-1003 | STRK-SIGINT-001 | 20 MHz-6 GHz, 4 TB recording, 8-hr continuous | 1 | 6 | $145,000 | $870,000 | 16 wks | MDA |
| Radar altimeter | 5998-01-XXX-1018 | STRK-ALT-001 | 0-5,000 ft AGL, ±1 ft accuracy, FM-CW | 1 | 6 | $14,500 | $87,000 | 8 wks | [Vendor consult] |
| Vision nav camera (pair) | 5998-01-XXX-1019 | STRK-VNAV-001 | Stereo pair, 10 Hz fix, ±10m GNSS-denied | 1 pair | 6 | $12,800 | $76,800 | 8 wks | [Vendor consult] |
| FADS pressure sensors (set) | 1560-01-XXX-1019 | STRK-FADS-001 | 16-port set, Kulite XTL-190, -55°C rated | 1 set | 8 | $8,200 | $65,600 | 8 wks | [Vendor consult] |
| SUBTOTAL SENSORS |  |  |  |  |  |  | $8,264,400 |  |  |

### E. Communications and Datalink

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares | Unit Cost | Total Cost | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| TTNT datalink radio | 5820-01-XXX-1001 | STRK-TTNT-001 | MANET waveform, 20 Mbps, <50 ms latency, 128-node | 1 | 8 | $125,000 | $1,000,000 | 14 wks | [Vendor consult] |
| TTNT antenna (dorsal) | 5820-01-XXX-1002 | STRK-TANT-001-D | 32-element conformal phased array | 1 | 6 | $22,500 | $135,000 | 10 wks | MDA |
| TTNT antenna (ventral) | 5820-01-XXX-1003 | STRK-TANT-001-V | 32-element conformal phased array | 1 | 6 | $22,500 | $135,000 | 10 wks | MDA |
| Link 16 terminal | 5820-01-XXX-1004 | STRK-L16-001 | Full participant, JTIDS/MIDS compatible, voice | 1 | 6 | $65,000 | $390,000 | 12 wks | [Vendor consult] |
| IFDL radio | 5820-01-XXX-1005 | STRK-IFDL-001 | 60 GHz mm-wave, 100 Mbps, <10 ms latency | 1 | 6 | $85,000 | $510,000 | 14 wks | [Vendor consult] |
| SATCOM terminal | 5820-01-XXX-1006 | STRK-SAT-001 | Ku-band, 5 Mbps BLOS, 0.6m flat panel | 1 | 6 | $145,000 | $870,000 | 16 wks | [Vendor consult] |
| Encryption module | 5810-01-XXX-1001 | STRK-ENC-001 | AES-256 + CRYSTALS-Kyber, NSA Type-1 equiv. | 1 | 8 | $32,000 | $256,000 | 10 wks | [Vendor consult] |
| Datalink processor | 5998-01-XXX-1020 | STRK-DLP-001 | Multi-waveform routing, gateway translation | 1 | 6 | $18,500 | $111,000 | 8 wks | CAE |
| MADL gateway module | 5998-01-XXX-1021 | STRK-MADL-001 | F-35 MADL to TTNT translation, <100 ms | 1 | 6 | $85,000 | $510,000 | 14 wks | [Vendor consult] |
| SUBTOTAL COMMS |  |  |  |  |  |  | $3,917,000 |  |  |

### F. Weapons Bay Modules and Armament

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares | Unit Cost | Total Cost | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Boeing Smart Launcher | 1410-01-XXX-1001 | STRK-BSL-001 | Trapeze + pneumatic ejection, MIL-STD-1760, dual bay | 2 | 10 | $48,000 | $480,000 | 14 wks | Boeing |
| Bay door actuator (each) | 4810-01-XXX-1002 | STRK-BDA-001 | Linear electromechanical, 3-sec cycle, dual per door | 4 | 10 | $12,500 | $125,000 | 10 wks | Boeing |
| Bay RAM lining kit | 5850-01-XXX-1002 | STRK-BRAM-001 | Dual-layer RAM for bay cavity, corner reflector mitigation | 1 set | 12 | $8,200 | $98,400 | 10 wks | [Vendor consult] |
| A/G pallet (SDB/SPEAR) | 1410-01-XXX-1002 | STRK-AGP-001 | 4x SDB or 4x SPEAR 3 integration, quick-swap | 1 | 14 | $85,000 | $1,190,000 | 12 wks | Boeing/CAE |
| A/A pallet (AMRAAM) | 1410-01-XXX-1003 | STRK-AAP-001 | 2x AMRAAM per bay, rail launch, 450 lbf ejection | 1 | 10 | $125,000 | $1,250,000 | 12 wks | Boeing/CAE |
| Mixed load pallet | 1410-01-XXX-1004 | STRK-MLP-001 | AMRAAM + AIM-9X, combined rail adapter | 1 | 8 | $145,000 | $1,160,000 | 14 wks | Boeing/CAE |
| EW pallet (NGJ-MB) | 5865-01-XXX-1001 | STRK-EWP-001 | Scaled NGJ-MB pod, 1 kW ERP/sub-band, cognitive | 1 | 10 | $220,000 | $2,200,000 | 16 wks | Boeing |
| ISR pallet | 5865-01-XXX-1002 | STRK-ISRP-001 | Advanced SAR 0.1m, multi-spectral, SIGINT relay | 1 | 8 | $185,000 | $1,480,000 | 16 wks | MDA/CAE |
| Chaff dispenser | 5865-01-XXX-1003 | STRK-DISP-001 | ALE-70 compatible, 32x RR-180 per aircraft | 2 | 16 | $8,500 | $136,000 | 8 wks | [Vendor consult] |
| Flare dispenser | 5865-01-XXX-1004 | STRK-DISP-002 | ALE-70 compatible, 16x MJU-68 per aircraft | 2 | 16 | $7,200 | $115,200 | 8 wks | [Vendor consult] |
| SUBTOTAL WEAPONS BAY |  |  |  |  |  |  | $8,234,600 |  |  |

### G. Electrical and Environmental Systems

| Item | NSN (Est.) | Part Number | Description | Qty/AC | Spares | Unit Cost | Total Cost | Lead Time | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Starter/generator | 2925-01-XXX-1003 | STRK-SG-001 | 60 kVA continuous, 28VDC/115VAC 400Hz | 1 | 8 | $32,000 | $256,000 | 12 wks | [Vendor consult] |
| Li-ion battery | 6140-01-XXX-1001 | STRK-BAT-001 | 8 kWh, 45-min emergency power, -55°C rated | 1 | 10 | $28,500 | $285,000 | 10 wks | [Vendor consult] |
| Ram Air Turbine | 2915-01-XXX-1001 | STRK-RAT-001 | Deployable, 12 kW at M0.45+, spring-loaded | 1 | 6 | $32,000 | $192,000 | 12 wks | [Vendor consult] |
| Power distribution bus | 5998-01-XXX-1022 | STRK-PDB-001 | Dual-redundant bus bars, solid-state contactors | 1 | 8 | $14,500 | $116,000 | 8 wks | [Vendor consult] |
| ECS pump (each) | 4310-01-XXX-1001 | STRK-ECS-001 | Triple-redundant centrifugal, 6 L/min, glycol/water | 3 | 10 | $6,800 | $68,000 | 8 wks | [Vendor consult] |
| ECS heat exchanger | 4310-01-XXX-1002 | STRK-ECS-002 | Fuel-to-coolant + air-to-coolant backup, 15 kW ea | 2 | 8 | $12,500 | $100,000 | 8 wks | [Vendor consult] |
| Coolant (ethylene glycol) | 6850-01-XXX-1001 | STRK-COOL-001 | 50/50 mix, -60°C pour point, MIL-A-46153 | 30 L | 50 | $95/L | $4,750 | 4 wks | Standard |
| Nitrogen generation system | 4310-01-XXX-1003 | STRK-NGS-001 | Hollow-fiber membrane, fire suppression + inerting | 1 | 6 | $18,500 | $111,000 | 10 wks | [Vendor consult] |
| SUBTOTAL ELEC/ENV |  |  |  |  |  |  | $1,132,750 |  |  |

### H. Consumables (Per Sortie / Per Flight Hour)

| Consumable | Unit | Consumption Rate | 30-Day Campaign Total | Unit Cost | 30-Day Total Cost |
| --- | --- | --- | --- | --- | --- |
| JP-8 fuel | kg | 280 kg/sortie | 604,800 kg | $0.90/kg | $544,320 |
| Hydraulic fluid (MIL-PRF-83282) | L | 0.20 L/FH | 713 L | $52.00/L | $37,076 |
| Lubricating oil (Mobil Jet Oil II) | L | 0.10 L/FH | 356 L | $32.00/L | $11,392 |
| Grease (MIL-G-81322) | g | 8 g/sortie | 17,280 g | $0.14/g | $2,419 |
| Nitrogen (aviation grade) | L STP | 1.0 L/sortie | 2,160 L | $0.10/L | $216 |
| Chaff cartridges (RR-180) | ea | Up to 32/sortie | 69,120 | $195/ea | $13,478,400 |
| Flare cartridges (MJU-68) | ea | Up to 16/sortie | 34,560 | $255/ea | $8,812,800 |
| De-icing fluid (Type IV) | L | 15 L/sortie (Arctic) | 32,400 L | $13.50/L | $437,400 |
| TOTAL CONSUMABLES |  |  |  |  | $23,324,023 |

## 2.3 Attrition Reserve Airframes

Twelve (12) attrition reserve airframes are procured as complete flyable aircraft, representing 33% of the operational fleet of 36. This reserve is sized to sustain a 30-day high-intensity campaign at the weighted average loss rate of 2.1% per sortie.

Cost: 12 x $9.3M = $111.6M USD (included in total airframe procurement).

Storage: Attrition reserve airframes are preserved in flyable storage condition at the Mirabel depot facility. Each aircraft is stored with:

•  Engine preservation: desiccant bags, corrosion inhibitor (Mobil Jet Oil II fogging), sealed intakes/exhausts

•  Fuel system: purged with nitrogen, fuel lines capped

•  Avionics: stored in climate-controlled shelter (15°C, 45% RH)

•  Composites: UV protective covers, monthly inspection for moisture ingress

•  RAM tiles: protective film, quarterly reflectometry check

•  Rotation: Each reserve aircraft rotated through training pipeline every 6 months to verify systems integrity and maintain battery charge

Surge Production Capacity: In the event attrition exceeds the 12-airframe reserve, production surge at Bombardier Mirabel can deliver replacement aircraft at a rate of 2 per month (Lot 15+ tooling), with first delivery 12 weeks from order.

# Part III: Ground Support Equipment (GSE)

Ground support equipment for the Striker program must support operations at four Main Operating Bases (MOBs): Cold Lake (AB), Bagotville (QC), Goose Bay (NL), and Thule/Pituffik (GL). All GSE is specified for -55°C minimum operating temperature to meet the Canadian Arctic Defence Accelerator (CADA) requirement. Equipment quantities are specified per MOB and total for the four-MOB network.

## 3.1 Aircraft Handling

| Item | Description | Qty/MOB | Total (4 MOB) | Unit Cost | Total Cost | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Aircraft tow bar | Nose gear, 1,000 kg capacity, -55°C rated hydraulics | 2 | 8 | $8,500 | $68,000 | TLD |
| Wheel chocks | Rubber composite, -55°C rated, tethered (4/set) | 8 sets | 32 sets | $420 | $13,440 | [Vendor consult] |
| Tie-down kits | 150 kt rated, heated anchors, Arctic wind (8/set) | 4 sets | 16 sets | $3,200 | $51,200 | [Vendor consult] |
| Safety pins/covers | Gear lock pins, intake/exhaust covers (twin inlets), insulated | 4 kits | 16 kits | $6,800 | $108,800 | Bombardier |
| Aircraft jacks | Hydraulic, 5-ton capacity, heated reservoir, -55°C | 4 | 16 | $28,500 | $456,000 | Malabar |
| Maintenance stands | Heated, adjustable height, 360° access platform | 4 | 16 | $12,500 | $200,000 | [Vendor consult] |

## 3.2 Refueling and Servicing

| Item | Description | Qty/MOB | Total (4 MOB) | Unit Cost | Total Cost | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Refuel truck (5,000L) | JP-8, single-point pressure, heated for -55°C | 2 | 8 | $285,000 | $2,280,000 | Esterer |
| Fuel filtration unit | Water separator, 5-micron filter, heated | 2 | 8 | $18,500 | $148,000 | Velcon |
| Fuel sampling kit | Contamination test, flash point, conductivity | 4 | 16 | $4,200 | $67,200 | [Vendor consult] |
| Oil servicing cart | Mobil Jet Oil II, heated reservoir, 50L capacity | 2 | 8 | $8,500 | $68,000 | [Vendor consult] |
| Hydraulic fluid cart | MIL-PRF-83282, heated, 100L capacity | 2 | 8 | $12,500 | $100,000 | [Vendor consult] |
| Nitrogen servicing cart | With regulator, -55°C rated, 50L cylinder | 2 | 8 | $6,800 | $54,400 | [Vendor consult] |
| Grease dispensing equip. | MIL-G-81322, heated gun, 5-kg reservoir | 4 | 16 | $2,400 | $38,400 | [Vendor consult] |

## 3.3 Weapons and Payload Handling

| Item | Description | Qty/MOB | Total (4 MOB) | Unit Cost | Total Cost | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Weapons loading cart | MIL-STD-1760 compatible, dual bay, 450 kg cap | 2 | 8 | $42,000 | $336,000 | [Vendor consult] |
| Hoist assembly | Weapons bay access, 450 kg capacity, electric | 2 | 8 | $18,500 | $148,000 | [Vendor consult] |
| Munitions storage | Temperature-controlled container, 8-unit, heated | 4 | 16 | $32,000 | $512,000 | [Vendor consult] |
| Chaff/flare reload cart | ALE-70 compatible, 32+16 magazine, heated | 2 | 8 | $8,500 | $68,000 | [Vendor consult] |
| Smart Launcher MTE | BIT/test set for Boeing Smart Launcher, automated | 1 | 4 | $125,000 | $500,000 | Boeing |

## 3.4 Power and Starting

| Item | Description | Qty/MOB | Total (4 MOB) | Unit Cost | Total Cost | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Ground Power Unit (GPU) | 28VDC/115VAC 400Hz, 60 kVA, -55°C rated | 2 | 8 | $85,000 | $680,000 | [Vendor consult] |
| Battery charging unit | Li-ion charger, 8 kWh, diagnostic capable | 2 | 8 | $12,500 | $100,000 | [Vendor consult] |
| Engine starting cart | Emergency start, pre-heat capability, -55°C | 1 | 4 | $45,000 | $180,000 | [Vendor consult] |
| External power cables | 100 ft, -55°C rated, 60 kVA | 4 | 16 | $2,800 | $44,800 | [Vendor consult] |

## 3.5 Environmental and De-icing

| Item | Description | Qty/MOB | Total (4 MOB) | Unit Cost | Total Cost | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Heated hangar (portable) | 12,000 sq ft, -55°C exterior, +15°C interior | 1 | 4 | $4,200,000 | $16,800,000 | [Vendor consult] |
| Aircraft heater (forced air) | 100,000 BTU, -55°C rated, diesel | 4 | 16 | $18,500 | $296,000 | [Vendor consult] |
| De-icing vehicle | Type IV heated fluid, 2,000L, -55°C | 2 | 8 | $125,000 | $1,000,000 | [Vendor consult] |
| Ice detection/removal tools | Heated scrapers, heated pads, IR camera | 2 kits | 8 kits | $8,500 | $68,000 | [Vendor consult] |
| Avionics bay purge unit | Dry air, heated, 50 L/min, humidity <10% | 2 | 8 | $12,500 | $100,000 | [Vendor consult] |

## 3.6 Maintenance and Inspection

| Item | Description | Qty/MOB | Total (4 MOB) | Unit Cost | Total Cost | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Composite repair kit | Vacuum bagging, heat blankets, BMI resin compatible | 2 | 8 | $18,500 | $148,000 | [Vendor consult] |
| NDI equipment set | Ultrasonic, eddy current, digital radiography | 1 set | 4 sets | $185,000 | $740,000 | Olympus/Zetec |
| RAM tile bonding kit | Dual-layer application, heated tools, 72-hr field | 2 | 8 | $22,500 | $180,000 | [Vendor consult] |
| Torque wrench set | Calibrated for -55°C, 1-250 ft-lb, digital | 2 sets | 8 sets | $4,200 | $33,600 | Snap-on |
| Specialized tool kit | Composite-safe, carbon fiber tools preferred | 2 | 8 | $12,500 | $100,000 | Snap-on |
| AESA radar test set | Automated BIT, pattern validation, power cal | 1 | 4 | $125,000 | $500,000 | MDA |
| EODAS alignment tools | 5-aperture calibration, IR source, boresight | 1 set | 4 sets | $85,000 | $340,000 | MDA |

## 3.7 Communications and Mission Planning

| Item | Description | Qty/MOB | Total (4 MOB) | Unit Cost | Total Cost | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Ground Control Station | Deployable, ruggedized, -55°C rated, 4 consoles | 1 | 4 | $1,250,000 | $5,000,000 | CAE |
| Mission planning workstation | With mission planning software, crypto-loaded | 2 | 8 | $42,000 | $336,000 | CAE |
| Datalink ground antennas | TTNT, Link 16, SATCOM, tripod-mounted | 3 sets | 12 sets | $65,000 | $780,000 | MDA |
| Secure comms equipment | Encrypted voice/data, KG-250X equivalent | 2 sets | 8 sets | $32,000 | $256,000 | [Vendor consult] |

# Part IV: Training Systems

## 4.1 Training Philosophy

The Striker training program integrates with existing RCAF training pipelines while establishing new competencies in unmanned combat air systems, collaborative autonomy, and MUM-T operations. Training is structured across three tiers:

•  Initial Training: Converts existing RCAF pilots, sensor operators, and maintainers to Striker-qualified status. Leverages 36 Gripen pilots already trained in MUM-T operations.

•  Recurrent Training: Maintains currency and proficiency across all crew positions. Focus on evolving threat environments, software updates, and tactics development.

•  Collaborative Combat AI Certification: Specialized training for operators managing autonomous teaming behaviors, trust calibration, and human-machine interface optimization.

## 4.2 Training Equipment

| Item | Description | Qty | Unit Cost | Total Cost | Supplier |
| --- | --- | --- | --- | --- | --- |
| Full-mission simulator (FMS) | High-fidelity Striker + Gripen integration, 6-DOF, visual 270° | 2 | $14,500,000 | $29,000,000 | CAE |
| Striker GCS simulator | Ground control station trainer, tactical datalink | 4 | $1,850,000 | $7,400,000 | CAE |
| Collab. Combat AI trainer | MUM-T simulation, multi-drone coordination, Boeing IP | 2 | $4,200,000 | $8,400,000 | CAE/Boeing |
| Maintenance training devices | Physical + virtual trainers: airframe, engine, avionics | 6 | $1,250,000 | $7,500,000 | CAE/Bombardier |
| Mission planning trainer | Software-based planning + rehearsal, terrain database | 4 | $485,000 | $1,940,000 | CAE |
| e-Learning modules | CBT for all Striker systems, SCORM-compliant | 1 | $285,000 | $285,000 | CAE |
| Simulator facility (each) | Building, HVAC, power, network, security | 2 | $3,500,000 | $7,000,000 | [Vendor consult] |
| TOTAL TRAINING |  |  |  | $61,525,000 |  |

## 4.3 Training Personnel Requirements

Based on operational analysis and crew ratio modeling:

| Role | Per MOB | Total (4 MOB) | Notes |
| --- | --- | --- | --- |
| Instructor Pilots | 3 | 12 | RCAF Gripen-converted; MUM-T qualified |
| Striker Operators | 6 | 24 | Sensor operators, AI interaction specialists |
| Mission Planners | 4 | 16 | Pre-flight planning, corridor design, ROE |
| Avionics Technicians | 4 | 16 | LRU swap, BIT, software load |
| Airframe Technicians | 4 | 16 | Composite repair, RAM maintenance |
| Ordnance Specialists | 3 | 12 | Weapon load, chaff/flare, 1760 test |
| Engine Mechanics | 2 | 8 | FADEC, FOHE, borescope inspection |
| Quality Assurance | 2 | 8 | Inspection sign-off, NDI certified |
| Logistics/Supply | 3 | 12 | Parts ordering, inventory, shipping |
| AI/Software Specialists | 2 | 8 | Autonomy updates, mission data load |
| TOTAL | 33 | 132 | Per shift; x2 for 24/7 = 264 |

# Part V: Weapons and Munitions Stockpile

## 5.1 Weapons Procurement Strategy

The Striker's dual internal weapons bays (2.6 m x 0.45 m x 0.5 m each, 585 L) provide four mission configurations via the Boeing Smart Launcher system: Air-to-Ground (SDB/SPEAR 3), Air-to-Air (AMRAAM), Mixed Load (AMRAAM + AIM-9X), Electronic Warfare (NGJ-MB), and ISR. Weapons inventory is sized for three operational states:

•  Peacetime Inventory: Sufficient for 30 days of training and patrol operations at reduced tempo (1.0 sortie/day per aircraft)

•  Surge Inventory (30-day campaign): Maximum-rate consumption at 72 sorties/day, optimized mission mix

•  Replacement Rate: Post-campaign resupply to restore both peacetime and surge inventory within 60 days via strategic airlift

### Mission Mix Assumptions (30-day campaign)

| Mission Type | Sorties | % of Total | Weapons Load |
| --- | --- | --- | --- |
| Penetrating Strike (SDB) | 1,080 | 50% | 4x SDB per sortie |
| Anti-Shipping (SPEAR 3) | 324 | 15% | 4x SPEAR 3 per sortie |
| Air Patrol (AMRAAM) | 540 | 25% | 2x AMRAAM per sortie |
| SEAD/EW (NGJ-MB) | 216 | 10% | 1x EW pallet per sortie |
| TOTAL | 2,160 | 100% |  |

## 5.2 Weapons List

| Weapon | Description | Unit Cost | Peacetime Qty | Campaign Qty | Total Cost |
| --- | --- | --- | --- | --- | --- |
| GBU-39/B SDB | 110 km glide, GPS/INS, penetrating blast | $42,000 | 432 | 4,320 | $198,144,000 |
| GBU-53/B StormBreaker | 110 km tri-mode (radar/IR/laser) | $185,000 | 108 | 0 | $19,980,000 |
| SPEAR 3 | 140 km powered, turbojet, multi-mode | $685,000 | 108 | 1,296 | $961,584,000 |
| AIM-120D3 AMRAAM | 160+ km BVR, active radar terminal | $1,250,000 | 270 | 1,080 | $1,687,500,000 |
| AIM-9X Block III | 25 km WVR, IIR + active radar | $485,000 | 54 | 0 | $26,190,000 |
| NGJ-MB EW Pod | Scaled, 1 kW ERP/sub-band, cognitive | $2,200,000 | 12 | 24 | $79,200,000 |
| TOTAL WEAPONS |  |  |  |  | $2,972,598,000 |

### Countermeasures (Chaff and Flare)

Each aircraft carries 32 chaff (RR-180) and 16 flare (MJU-68) cartridges distributed across two ALE-70 compatible dispensers in the weapons bays. Expenditure rate varies by mission type and threat environment:

| Countermeasure | Peacetime Qty | Campaign Qty | Unit Cost | Total Cost |
| --- | --- | --- | --- | --- |
| Chaff (RR-180) | 20,736 | 69,120 | $195 | $17,506,920 |
| Flare (MJU-68) | 10,368 | 34,560 | $255 | $11,465,640 |
| ALE-70 Towed Decoy | 48 | 144 | $125,000 | $24,000,000 |
| TOTAL |  |  |  | $52,972,560 |

### Weapons Bay Pallet Summary

| Pallet Type | Qty Required | Unit Cost | Total Cost |
| --- | --- | --- | --- |
| Air-to-Ground (SDB/SPEAR) | 24 | $85,000 | $2,040,000 |
| Air-to-Air (AMRAAM) | 18 | $125,000 | $2,250,000 |
| Mixed Load (AMRAAM+9X) | 12 | $145,000 | $1,740,000 |
| EW (NGJ-MB) | 16 | $220,000 | $3,520,000 |
| ISR (SAR+multi-spectral) | 8 | $185,000 | $1,480,000 |
| TOTAL PALLETS | 78 |  | $11,030,000 |

# Part VI: Maintenance and Repair Infrastructure

## 6.1 Depot-Level Maintenance Facility

Primary Location: Mirabel, Quebec (QC) — Leverages existing Bombardier aerospace infrastructure, skilled composite workforce, and cold-weather testing experience.

Secondary/Alternate: Halifax, Nova Scotia (NS) — Strategic Atlantic location, existing DND maintenance facilities, port access for oversized spares.

### Capabilities

•  Full Structural Inspection: Ultrasonic C-scan (Olympus OmniScan MX2), digital radiography (Yxlon Y.MU2000-D), acoustic emission monitoring (Physical Acoustics Micro-II). Annual throughput: 24 aircraft.

•  RAM Refurbishment: Complete removal and reapplication of dual-layer RAM. Cleanroom Class 7 (ISO 14644-1). Temperature-controlled application (18±2°C). Curing ovens: 2m x 3m x 12m, 250°C max. Throughput: 4 aircraft/month.

•  Avionics Calibration and Repair: AESA radar anechoic chamber (12m x 8m x 8m, -60 dB reflectivity), EODAS 5-aperture alignment rig, ESM/SIGINT RF test range (shielded anechoic chamber, 0.5-40 GHz).

•  Engine Overhaul: Hot-section inspection (borescope, dimensional), bearing replacement, FADEC bench test, compressor blade replacement. Partner: Pratt & Whitney Montreal Service Center.

•  Landing Gear Overhaul: Oleo-pneumatic seal replacement, nitrogen recharge, brake disc inspection, retraction functional test.

•  Collaborative Combat AI Updates: Secure software loading facility, mission data preparation, autonomy algorithm regression testing. Partner: Boeing Phantom Works via secure datalink.

### Facility Requirements — Mirabel Primary Depot

| Facility Element | Specification | Estimated Cost |
| --- | --- | --- |
| Heated hangar (12,000 sq ft) | Two bays, +15°C, -55°C exterior, snow load 2.4 kPa | $18,500,000 |
| Cleanroom (Class 7, RAM) | 2m x 3m x 12m curing oven, temp/humidity control | $4,200,000 |
| Environmental chamber | -55°C to +85°C, 5m x 5m x 8m | $2,800,000 |
| Engine test cell | 36 kN class, sound-attenuated, FADEC bench | $8,500,000 |
| Composite repair shop | BMI resin capability, autoclave 2m x 4m | $3,200,000 |
| Avionics repair shop | ESD-controlled, anechoic chamber, RF test | $6,800,000 |
| AESA radar test range | 12m x 8m x 8m, -60 dB reflectivity | $5,400,000 |
| Anechoic chamber (ESM) | Shielded, 0.5-40 GHz, 10m x 8m x 6m | $4,600,000 |
| Secure software load facility | SCIF, NSA Type-1 encryption, air-gapped | $2,400,000 |
| Administrative and support | Offices, training rooms, crypto storage | $3,200,000 |
| TOTAL FACILITY COST |  | $60,600,000 |

## 6.2 Field-Level Maintenance Facilities (per MOB)

Four MOBs: Cold Lake (AB), Bagotville (QC), Goose Bay (NL), Thule/Pituffik (GL). Each MOB requires:

•  Heated Maintenance Hangar: Minimum 6,000 sq ft (two bays), +15°C interior, -55°C exterior capability. Structural steel, insulated panels, snow loading 2.4 kPa.

•  Weapons Storage and Handling: Dual bay capacity, MIL-STD-1760 pre-flight test capability, temperature 10-25°C, humidity <60%.

•  Fuel Storage: 40,000 L JP-8 minimum, single-point pressure refueling, water separator, heated reservoir.

•  Parts Storage: Heated, environmentally controlled (15-25°C, 40-60% RH), ESD-safe for avionics LRU storage.

•  Crew Facilities: Heated rest areas, -55°C rated PPE issue, decontamination station for composite dust and RAM materials.

## 6.3 Forward Operating Location (FOL) Kits

Deployable maintenance kits for austere forward bases, sized to support 30 days of autonomous operations:

•  Portable Shelters: 4x clamshell shelters, 20′ x 30′, Arctic-rated, 100 mph wind, heated (diesel).

•  Tool Kits: Composite-safe tools (Toray carbon fiber compatible), cold-weather rated, calibrated.

•  LRU Spares: Mission-essential LRU set (top 20 by failure rate), pre-packaged, heated storage.

•  Fuel and Oil: 10,000L JP-8 pre-positioned, 200L Mobil Jet Oil II, 100L hydraulic fluid.

•  Communications: TTNT ground node, SATCOM backup, portable GCS capability.

# Part VII: Personnel and Manning

## 7.1 Personnel Requirements

Personnel requirements are based on operational analysis: 36 operational aircraft, 2.0 sorties per aircraft per day at high tempo, 30-minute turnaround, 24/7 operations during campaign periods. Manning is calculated per MOB (4 MOBs total) with surge augmentation for campaign periods.

| Role | Per MOB | Total (4) | Shift | Training | Duration | Source |
| --- | --- | --- | --- | --- | --- | --- |
| Gripen Pilots | 9 | 36 | Day only | RCAF FTU + MUM-T | 26 wks | RCAF |
| Striker Operators | 6 | 24 | Day/Night | CAE Striker Course | 26 wks | RCAF/CAE |
| Mission Planners | 4 | 16 | Day | Striker + AI cert | 29 wks | RCAF |
| Avionics Techs | 4 | 16 | Day/Night | MOSQ + Striker | 16 wks | RCAF |
| Airframe Techs | 4 | 16 | Day/Night | Composite + RAM | 20 wks | RCAF |
| Ordnance Spec. | 3 | 12 | Day | 1760 + Smart Ldr | 12 wks | RCAF |
| Engine Mechanics | 2 | 8 | Day | P&W FADEC | 12 wks | RCAF/P&W |
| Quality Assurance | 2 | 8 | Day | NDI cert + Striker | 8 wks | RCAF |
| Logistics/Supply | 3 | 12 | Day | Supply chain | 4 wks | RCAF/CLS |
| AI/Software Spec. | 2 | 8 | Day | Boeing AI cert | 12 wks | Boeing/CAE |
| TOTAL PER MOB | 39 | 156 |  |  |  |  |

## 7.2 Training Pipeline

### Initial Training

Duration: 26 weeks (6 months) full-time. Location: Cold Lake Primary Flying Training School / CAE Montreal Training Centre.

•  Weeks 1-4: Ground School — Striker systems overview, stealth handling procedures, RAM awareness, ground safety.

•  Weeks 5-8: Simulator Phase — FMS and GCS simulator training, basic maneuvering, system emergencies.

•  Weeks 9-14: Tactical Integration — MUM-T operations, Collaborative Combat AI interaction, weapon delivery, EW employment.

•  Weeks 15-20: Live Flying — Actual Striker sorties (minimum 20 sorties), supervised operations, formation flight.

•  Weeks 21-24: Combat Mission Qualification — Arctic operations, contested environment tactics, emergency procedures.

•  Weeks 25-26: Certification — Final examination, currency demonstration, logbook sign-off.

### Recurrent Training

Frequency: Quarterly (every 3 months) for operators; Annually for maintainers. Duration: 1 week for operators, 2 weeks for maintainers. Content: Software updates, new threat briefings, tactics refresh, hands-on LRU swap for maintainers.

### Instructor Training

Prerequisites: 500+ flight hours as Striker operator, instructor pilot qualification (RCAF IP badge). Additional 4-week instructor methods course at CAE Montreal. IP-to-student ratio: 1:4 for initial training, 1:8 for recurrent.

### Collaborative Combat AI Certification

Additional 3-week course beyond standard operator training. Covers: AI trust calibration, behavior prediction, intervention protocols, mission replanning assessment, adversarial AI concepts. Required for all operators before independent Striker command. Annual recertification with 2-day update.

# Part VIII: Cost Summary

All costs in 2025 USD unless noted. CAD converted at 1.35 (2025 average). Costs include contractor fee (CPAF, 8% fee cap) but exclude contingency and GFE. Learning curve applied: Crawford model, 85% slope, Lot 15 production maturity.

## 8.1 Total Procurement Cost (Phase 1)

| Category | Cost (USD M) | Cost (CAD M) |
| --- | --- | --- |
| Striker Airframes (64 x $9.3M) | 595.2 | 803.5 |
| Spare Parts and Consumables | 285.6 | 385.6 |
| Ground Support Equipment | 168.4 | 227.3 |
| Training Systems | 96.4 | 130.1 |
| Weapons and Munitions | 198.2 | 267.6 |
| Facilities (Depot + 4 MOB) | 128.6 | 173.6 |
| Initial Spares and Support | 51.4 | 69.4 |
| TOTAL PROCUREMENT | 1,523.8 | 2,057.1 |

## 8.2 Annual Sustainment Cost

| Category | Cost (USD M/yr) | Cost (CAD M/yr) |
| --- | --- | --- |
| Spare Parts Replenishment | 24.2 | 32.7 |
| Consumables (fuel, oil, etc.) | 18.6 | 25.1 |
| Depot Maintenance | 22.4 | 30.2 |
| Field Maintenance Labor | 16.8 | 22.7 |
| RAM Refurbishment | 14.2 | 19.2 |
| Training and Exercises | 8.4 | 11.3 |
| Contractor Logistics Support | 13.8 | 18.6 |
| TOTAL SUSTAINMENT/YR | 118.4 | 159.8 |

## 8.3 Lifecycle Cost (10 Years)

| Category | Cost (USD M) | Cost (CAD M) |
| --- | --- | --- |
| Procurement (Phase 1) | 1,523.8 | 2,057.1 |
| Annual Sustainment x 10 | 1,184.0 | 1,598.4 |
| Attrition Replacement (10 yr) | 55.8 | 75.3 |
| Mid-Life Upgrades (S/W + SENSORS) | 168.0 | 226.8 |
| Decommissioning/Disposal | 8.2 | 11.1 |
| Contingency (5%) | - | - |
| TOTAL LIFECYCLE (10 YR) | 2,708.0 | 3,655.8 |

### Economic Justification

The total 10-year lifecycle cost of USD $2,708.0 million represents 29.3% of the combined Gripen-plus-drone program cost of $9.24 billion CAD. On a per-sortie basis over 10 years (projected 43,200 FH / 26,190 sorties), the Striker costs approximately $103,400 per sortie — significantly lower than a manned Gripen E sortie (~$285,000 per sortie including aircrew and full sustainment). The 2.75:1 cost advantage, combined with the Striker's ability to penetrate contested environments without risking aircrew, provides compelling operational economics.

The Striker's direct operating cost of $1,200 per flight hour (from CDR specifications) compares favorably with other UCAV programs: MQ-9 Reaper ($3,800/FH), XQ-58A Valkyrie ($1,800/FH projected), and Taranis ($2,200/FH estimated). The lower cost reflects the Striker's mature subsystem selection (COTS where possible), Canadian industrial participation, and efficient depot design leveraging existing Bombardier infrastructure.

# Part IX: Risk Assessment and Mitigation

## 9.1 Key Supply Chain Risks

| Risk | Description | Severity | Mitigation |
| --- | --- | --- | --- |
| Engine (P&W) | Single-source PW800 derivative; 28-week lead time; geopolitical risk | HIGH | Strategic spares stockpile ($45M); dual-source qualification by Lot 10 |
| RAM Materials | Proprietary dual-layer formulation; limited global suppliers | HIGH | 24-month forward buy ($28M); Canadian supplier development |
| Composite Structures | BMI high-temp resin; 20-24 week lead time; skill-dependent | MEDIUM | Production slot reservations; Bombardier capacity guarantee |
| Arctic Environment | -55°C degrades elastomers, batteries, adhesives; CS-RAM required | MEDIUM | Cold-weather qualification program; heated storage; accelerated life testing |
| MUM-T Software | Boeing proprietary AI; IP protection; update dependency | HIGH | Software escrow; source code license; CAE backup development |
| AESA Radar | 600 GaN T/R modules; ITAR-controlled; MDA single source | MEDIUM | Domestic GaN foundry investment; second-source by 2031 |
| EODAS Sensors | IR-transparent windows; FSS coating; limited vendors | MEDIUM | Strategic stockpile; alternative coating development |
| Attrition Rate | 2-4% per sortie in contested environment may underestimate losses | HIGH | 12-airframe reserve (33%); surge production at 2 AC/month |

## 9.2 Mitigation Strategies

### Dual Sourcing Where Possible

Critical components with single-source risk (AESA T/R modules, FADEC, MUM-T software) will be qualified with a second source by Lot 10 (2030). Investment: $45M over 4 years. Priority items: engine bearings (SKF + Timken), hydraulic actuators (Parker + Moog), mission computers (Nvidia + Qualcomm).

### Strategic Spares Stockpile

A 24-month forward buy of long-lead items (engine hot section components, composite wing skins, AESA T/R modules) will be established at the Mirabel depot. Investment: $85M initial, $12M/year replenishment. Stockpile covers projected demand through Lot 20 (2035).

### Pre-Positioned Forward Spares

Each MOB maintains 72 hours of mission-essential spares (top 20 LRUs by failure rate). Forward spares are rotated through the depot every 6 months to prevent shelf-life expiration. Total forward spares value: $42M across 4 MOBs.

### Contractor Logistics Support (CLS)

10-year CLS agreements with Pratt & Whitney (engine), Boeing (autonomy/MUM-T), Honeywell (navigation), MDA (sensors), and CAE (training). CLS covers: technical support, engineering changes, provisioning updates, depot augmentation. Total CLS value: $138M over 10 years.

### Rapid Resupply via Strategic Airlift

Memorandum of Understanding with RCAF Air Mobility and Allied Airlift (NATO SAC). Priority airlift for critical spares: 48-hour delivery from Mirabel to any MOB. Pre-positioned spares at Thule AB (USAFE) for northernmost MOB support.

### Software Update and Maintenance Plan

Collaborative Combat AI software updates delivered quarterly via secure datalink. Major autonomy revisions (annual) require depot visit for validation. Software escrow agreement with Boeing ensures continuity in event of contract termination. Mission data loads (threat libraries, terrain maps) updated monthly.

# Part X: Recommendations and Implementation Timeline

## 10.1 Immediate Actions (2026-2027)

•  Q3 2026: Establish procurement contracts for all GSE and training systems. Release RFPs for major subsystems (engine CLS, autonomy license, sensor support).

•  Q4 2026: Begin initial spares procurement at 90% confidence level. Issue production orders for Lot 1-5 attrition reserve airframes (12 aircraft).

•  Q1 2027: Establish depot-level maintenance facility at Mirabel. Begin facility construction (12,000 sq ft hangar, cleanroom, test cells).

•  Q2 2027: Recruit and train initial maintenance cadre (32 personnel). Begin 26-week operator training pipeline.

•  Q3 2027: Establish forward-deployed spares at Cold Lake and Bagotville MOBs.

•  Q4 2027: Initial Operational Capability (IOC) — 12 operational Strikers, 2 MOBs active, basic MUM-T with Gripen E.

## 10.2 Near-Term Actions (2028-2030)

•  2028: Complete initial spares stockpile. Establish Goose Bay and Thule MOBs. Full FOL kit deployment.

•  2029: Full Operational Capability (FOC) — 36 operational aircraft, 4 MOBs, full weapons qualification.

•  2030: Conduct operational testing of sustainment concept. Refine spares requirements based on actual usage data. Complete Lot 10 dual-source qualification.

## 10.3 Long-Term Actions (2031+)

•  2031-2033: Software and sensor upgrades (AESA GaN++ technology, EODAS Gen 2, enhanced autonomy STANAG 4818 compliance for Tempest interoperability).

•  2033-2035: Export variant development (Australian, NATO partner configurations).

•  2035+: Sustainment optimization based on actual usage data. Transition to predictive maintenance using HUMS prognostics. Potential block upgrade to extend service life to 1,200 FH.

### Program Milestones Summary

| Milestone | Date | Criteria |
| --- | --- | --- |
| CDR Complete | June 2026 | Technical baseline approved |
| First Flight | March 2027 | 5 flight test aircraft |
| IOC | December 2027 | 12 aircraft, 2 MOBs, basic MUM-T |
| FOT&E Complete | June 2029 | All weapons qualified |
| FOC | September 2029 | 36 aircraft, 4 MOBs, full capability |
| 30-Day Campaign Ready | January 2030 | Validated surge ops, 72 sorties/day |
| Full Block Upgrade | 2035 | Tempest interoperable, 1,200 FH life |

# Appendices

## Appendix A: Detailed Spare Parts Summary by Cost Category

| Subsystem Category | Total Spares Cost (USD) |
| --- | --- |
| A. Airframe and Structure | $6,236,800 |
| B. Propulsion System | $21,681,000 |
| C. Avionics and Flight Control | $5,388,000 |
| D. Sensors | $8,264,400 |
| E. Communications and Datalink | $3,917,000 |
| F. Weapons Bay Modules | $8,234,600 |
| G. Electrical and Environmental | $1,132,750 |
| H. Consumables (30-day campaign) | $23,324,023 |
| TOTAL SPARE PARTS | $285,600,000 |

## Appendix B: GSE Technical Specifications Summary

Complete GSE technical specifications available in separate document CDR-STRKR-GSE-001. Key environmental requirements: All GSE rated for -55°C minimum operating temperature per CADA. Electrical: 28VDC/115VAC 400Hz aircraft power, 208VAC 60Hz ground power. Hydraulics: MIL-PRF-83282 fluid, 4,000 psi system pressure. Communications: TTNT, Link 16, SATCOM Ku-band ground segment.

## Appendix C: Training System Specifications

Complete training system specifications available in separate document CDR-STRKR-TRG-001. FMS visual system: 270° x 80° FOV, 8K resolution, 60 Hz refresh, collimated display. Motion: 6-DOF electric hexapod, +/-25° pitch/roll, 6 m heave. GCS simulator: Replicates tactical control station, dual 4K displays, TTNT waveform simulation. AI trainer: 50,000+ simulated scenarios, reinforcement learning environment, adversarial AI red team.

## Appendix D: Facility Requirements

Complete facility drawings and specifications available in separate document CDR-STRKR-FAC-001. Mirabel depot: 12,000 sq ft heated hangar (2 bays), 2,400 sq ft cleanroom (Class 7), 1,800 sq ft avionics repair (ESD), 1,200 sq ft composite shop, 800 sq ft engine test cell control room. MOB hangars: 6,000 sq ft each (2 bays), 15°C minimum interior. All facilities: NBC protection, force protection per DND standards, secure communications (SCIF for autonomy updates).

## Appendix E: Personnel Manning Document

Complete manning tables, rank structure, and billet descriptions available in separate document CDR-STRKR-MAN-001. Total program personnel: 156 core (4 MOBs) + 32 Mirabel depot + 24 training staff + 18 HQ/program office = 230 military + 45 contractor = 275 total. Surge augmentation for 30-day campaign: +48 personnel (12 per MOB) drawn from reserve and other RCAF units.

## Appendix F: Cost Model Assumptions

| Parameter | Assumption |
| --- | --- |
| Exchange rate (USD/CAD) | 1.35 (2025 average) |
| Learning curve | Crawford model, 85% slope, Lot 15 maturity |
| Contractor fee | CPAF, 8% fee cap |
| Inflation | 2.1% annual (Bank of Canada target) |
| Operating tempo (sustained) | 1.0 sortie/AC/day |
| Operating tempo (campaign) | 2.0 sorties/AC/day |
| Average sortie duration | 99 minutes (1.65 FH) |
| 30-day campaign sorties | 2,160 (36 AC x 2.0 x 30 days) |
| Annual flight hours (sustained) | 4,320 FH |
| 10-year flight hours | 43,200 FH |
| Attrition rate (weighted avg) | 2.1% per sortie (contested) |
| Attrition reserve | 12 airframes (33% of ops fleet) |
| Confidence level (spares) | 90% (Poisson distribution) |
| Fuel cost (JP-8) | $0.90/kg (DND bulk contract) |
| Direct operating cost | $1,200/FH (from CDR spec) |
| Annual sustainment per AC | $265,000 (from CDR spec) |
| Mid-life upgrade cost | $168M total (software + sensors) |

STRIKER-CLASS LOYAL WINGMAN UAV

Parts Procurement Package

Document No.: CDR-STRKR-PPP-001  |  Revision: Baseline 1.0  |  June 2026

Prepared for: Canadian Unmanned Combat Air System Program Office

RESTRICTED // CDN // NOFORN  |  Canadian Eyes Only