The Optimal Striker Procurement Package v6.1

Canadian-led, non-US-controlled acquisition and sustainment baseline

PRELIMINARY — PLANNING DATA — NOT FOR OPERATIONAL USE

Issue date: 6 September 2026

All values are expressed in 2026 Canadian dollars. Technical references trace to The Optimal Striker Technical Specifications v6.1.

# Document Control and Marking

PRELIMINARY — PLANNING DATA — NOT FOR OPERATIONAL USE. This package contains concept-stage procurement planning data for the Striker unmanned combat air system. Costs are 2026 Canadian-dollar planning estimates, not vendor quotations; quantities and lead times require supplier confirmation; and nothing in this document authorises expenditure, production, export or weapons release.

Table 0-1  Document control

| Item | Entry |
| --- | --- |
| Title | The Optimal Striker Procurement Package v6.1 |
| Document number | STR-AIR-PPP-003 |
| Controlled technical baseline | The Optimal Striker Technical Specifications v6.1, baseline STRIKER-v6.1-BL |
| Doctrine reference | The Opening Doors Doctrine, DCT-OD-2026-001 |
| Compilation authority | Programme office, air vehicle procurement cell |
| Cost basis | 2026 CAD; rough-order-of-magnitude planning confidence, ±25% |
| Fleet pricing point | 48 aircraft; 17 fleet options from 10 through 72 aircraft analysed |
| Currency rule | Every price in this package is expressed in Canadian dollars |
| Scope/depth reference | The Optimal Striker Procurement Package v5.0; no technical or cost value is inherited from that obsolete issue |
| Security handling | PRELIMINARY — concept-stage planning data; handle under programme security instructions |
| Distribution | Programme office, PSPC liaison, DND project office and shortlisted suppliers under NDA |

## Compilation Methodology

Eight checks govern every line of this package. A line that fails a check is corrected before issue. The checks preserve the clean-baseline discipline of TS v6.1 while translating engineering requirements into procurable resources, money and export-control actions.

Table 0-2  Immutable compilation matrix

| Check | Rule applied |
| --- | --- |
| 1. Baseline traceability | Every technical statement traces to a section, table, requirement, derivation or verification event in TS v6.1. Untraceable technical content is removed. |
| 2. Quantity consistency | Quantities per aircraft match the v6.1 configuration: 5,320 kg MTOW, 2,988 kg OEW, 3,010 kg grown weight, 1,940 kg fuel, two 585 L bays and two 3.80 m chine stations. |
| 3. Currency discipline | All planning values are CAD. No USD price, conversion artifact or mixed-currency total appears in the document. |
| 4. Cost reconciliation | Category rollups reconcile to CAD 24.30M recurring unit cost at the 48-aircraft reference point; programme rollups reconcile to CAD 2.380B NRE and the fleet equations of Part IX. |
| 5. Canadian priority | A qualified Canadian source leads every line where domestic capability exists. Offshore sources are limited to close Canadian allies other than the United States. |
| 6. Export-control closure | The recurring air-vehicle register carries no ITAR-controlled article. Residual allied export permits, COMSEC controls and F-35 interface approvals receive explicit owners and lead times. |
| 7. Supplier qualification | Production suppliers require AS9100-class quality registration; special processes require NADCAP or an approved equivalent; distributors require AS9120. |
| 8. Sustainment translation | Turnaround, hot-pit, engine-removal, LRU, inspection, Arctic and sortie-generation requirements convert into spares, equipment, manpower and money in Part X. |

# Table of Contents

Document Control and Marking	4

Compilation Methodology	5

Table of Contents	6

Executive Summary	7

Bottom Line	7

Principal Findings	7

Part I — Platform Overview and Programme Basis	9

1.1 Platform Summary	9

1.2 Mission Set and Provisioning Drivers	10

1.3 Programme Quantities	10

1.4 Cost Definitions and Boundaries	11

Part II — Master Parts Breakdown (Air Vehicle)	12

2.1 Category A — Airframe structure	13

2.2 Category B — Raw materials, fasteners and shop consumables	14

2.3 Category C — Propulsion and fuel system	16

2.4 Category D — Landing gear and brakes	18

2.5 Category E — Avionics, sensors and geolocation	18

2.6 Category F — Signature materials and treatments	20

2.7 Category G — Electronic warfare and self-protection	21

2.8 Category H — Bay, launch and weapons interface	21

2.9 Category I — Communications and datalinks	22

2.10 Category J — Electrical power	23

2.11 Category K — Flight controls and actuation	24

2.12 Category L — Thermal management	25

2.13 Category Summary and Initial Spares Pool	26

Part III — Weapons and Stores Provisioning	28

Part IV — Ground Support Equipment	29

Part V — Training System	31

Part VI — Facilities and Infrastructure	33

Part VII — Supplier Directory and Outreach Pathways	34

7.1 Standard Engagement Sequence	36

Part VIII — Acquisition Strategy and Procurement Routes	38

8.1 Route by Line Type	38

8.2 Industrial and Canadian Priority Rule	38

8.3 Competition Posture	38

Part IX — Cost Analysis and Fleet Economics	40

9.1 Recurring Unit-Cost Reconciliation	40

9.2 Non-Recurring Programme Cost	41

9.3 Fleet-Quantity Cost Model	41

9.4 Decision-Basis Adders	43

9.5 Cost Sensitivity and Control Points	43

Part X — Sustainment Package	45

10.1 Requirement-to-Resource Translation	45

10.2 Initial Spares and Repairable Pool	45

10.3 Depot Equipment and Repair Pipeline	46

10.4 Software, Data and Consumables Support	47

10.5 Support Manpower	47

10.6 Sustainment Cost Estimate	48

Part XI — ITAR and Export-Control Strategy	49

11.1 Control Classification Matrix	50

11.2 Country and Regime Analysis	50

11.3 Canadian Controlled-Goods and Security Implementation	51

11.4 No-ITAR Recurring BOM Claim and Boundaries	51

11.5 Substitution and Waiver Control	51

11.6 Licence Workflow and Data-Release Gates	52

Part XII — Industrial and Canadian Workshare Plan	53

12.1 Prime and Integrator Structure	54

12.2 Canadian Assembly and Component Manufacture	54

12.3 Domestic-Content Objectives	55

12.4 Technology-Transfer Assumptions	55

12.5 Potential Participating Companies	55

12.6 Industrial and Technological Benefits	56

Part XIII — Schedule and Long-Lead Procurement Plan	58

13.1 Programme Milestones	58

13.2 Long-Lead Items	59

13.3 Delivery and Rate Planning	59

Part XIV — Procurement Risk, Quality and Compliance	60

14.1 Top Programme Risks	60

14.2 Quality Standards and Verification	61

14.3 Traceability and Records	62

Part XV — Appendices and Procurement Reference Tables	63

Appendix A — Cost Formulas	63

Appendix B — Supplier Directory	63

Appendix C — Standards and Compliance Reference	65

Appendix D — Assumptions and Exclusions	65

Appendix E — Compilation Certification	66

Part XVI — Procurement Decision Summary	67

# Executive Summary

## Bottom Line

This package translates the Striker v6.1 clean baseline into a Canadian-led, non-US-controlled procurement programme. The reference recurring unit cost is CAD 24.30M at a 48-aircraft pricing point. A 92% learning curve produces CAD 29.35M per aircraft at quantity 10 and CAD 23.14M at quantity 72. Fixed NRE is CAD 2.380B. Initial spares and support follow CAD 68M + CAD 3.0M per aircraft. Across the 17 requested fleet sizes, core programme acquisition runs from CAD 2.771B at 10 aircraft to CAD 4.330B at 72 aircraft, before weapons, infrastructure and contingency.

When the standard initial effects package, infrastructure and a 10% contingency are added, total acquisition runs from CAD 3.321B at 10 aircraft to CAD 5.699B at 72 aircraft. The 15-year lifecycle support estimate runs from CAD 1.710B to CAD 3.632B. These are comparable planning economics, not vendor quotations.

## Principal Findings

- Canadian and non-US allied sourcing closes the baseline: the M88-2 propulsion system is French; weapons are MBDA and Diehl; computing and networking use Canadian and European sources; no recurring line depends on an ITAR-controlled US article.

- Canadian content objective: 51% of recurring flyaway value at first article, 60% at rate production, and at least 70% of sustainment labour. Final assembly, structural integration, training, depot activation and support management remain in Canada.

- Long-lead critical path: M88-2 engine slots, the 480-element AESA, the DRFM jammer, the EuroMIDS terminal, certified flight-control software, the geolocation timing chain and recycled-material allowables. Orders by programme month M12 protect first flight at M40.

- The 48-aircraft point is a costing reference, not a force-structure recommendation. It yields CAD 1.166B recurring aircraft procurement, CAD 2.380B NRE, CAD 212M initial spares/support and CAD 3.758B core programme acquisition.

- Payload/weapons procurement is separable. The standard initial effects package costs CAD 9.18M per aircraft at planning level and can be deleted without changing the aircraft cost model.

- PV-09 remains the key capability validation: Mach 1.40 Meteor-class separation from the reinforced chine stations. The Mach 0.95–1.20 fallback envelope preserves the D-4 high-value-asset geometry per TS v6.1 §10.5.

The procurement posture is executable if long-lead contracts are placed by M12, the engine-pool agreement with the Sprinter fleet is signed by M18, and export-control screening occurs before supplier data release. The cost model deliberately prices supply resilience rather than assuming it.

# Part I — Platform Overview and Programme Basis

## 1.1 Platform Summary

Striker v6.1 is a 5,320 kg class, single-engine, all-aspect signature-managed loyal wingman. It sustains Mach 1.40 at 45,000 ft on dry M88-2 power, carries two internal bays and two reinforced semi-conformal chine stations, anchors the cooperative geolocation network, and bridges the Striker/Sprinter/Gripen mesh to Link 16 without MADL. The platform summary below is controlled by TS v6.1, not by the obsolete procurement issue.

Table 1-1  v6.1 platform summary for procurement

| Parameter | Value | TS v6.1 reference |
| --- | --- | --- |
| Maximum take-off mass | 5,320 kg | Executive baseline summary; §14.1 |
| Operating empty mass | 2,988 kg model; 3,010 kg grown; 3,150 kg ceiling | §2.3; Table 2-3 |
| Internal fuel | 1,940 kg total / 1,910 kg usable | §4.5; §14.1 |
| Payload | 392 kg at full fuel; 836 kg maximum weapons at reduced fuel | §2.3; §14.1 |
| Corridor speed | Mach 1.40 sustained at 45,000 ft; +26.4% dry excess thrust with two IRIS-T | §3.2; Table 3-2 |
| Maximum / never-exceed speed | Mach 1.50 maximum level; Mach 1.60 VNE | §§2.1, 3.2 |
| Design missions | D-1 620 nm strike; D-2 500 nm-class cover; D-3 2,100 nm ferry; D-4 600 nm HVA hunt | §5.1 |
| Engine | 1× Safran M88-2; 50 / 75 kN SLS; 897 kg bare | §4.1; Table 4-1 |
| Weapon provision | Two 2.60 × 0.45 × 0.50 m bays; two 3.80 m chine rails | §2.2; §10.1 |
| Sensor fit | 480-element AESA; five EODAS apertures; six-aperture ESM/geolocation suite | §10.2 |
| Recycled content | 482 kg first article (16.1% OEW); 595 kg rate target (20%) | §6.2; Table 6-2 |
| Fleet commonality | One M88-2 pool, timing architecture, pallet standard and circular-materials chain with Sprinter | §12.3 |
| Turnaround | 268.6 min full cycle; 45 min hot pit; 2.0 sustained / 2.4 surge sorties per aircraft-day | §§11.1, 12.4 |
| Design life | 1,200 flight hours / 330 missions; 150 h phased and 600 h depot events | §11.1 |

## 1.2 Mission Set and Provisioning Drivers

Four closing missions drive provisioning. D-1 drives bay stores, fuel-system capacity and hot-pit reload; D-2 drives EW spares, power and cooling; D-3 drives ferry readiness and preservation; D-4 drives reinforced chine rails, Meteor-class integration and the PV-09 separation campaign.

Table 1-2  Mission provisioning drivers

| Mission | v6.1 profile | Fuel margin | Procurement consequence |
| --- | --- | --- | --- |
| D-1 corridor precision strike | 620 nm radius; 120 nm at Mach 1.40; two SPEAR 3-class plus two IRIS-T | +234 kg | Bay trapezes, reload carts, SPEAR-class interfaces, IRIS-T stations and rapid refuel |
| D-2 electronic cover | 500 nm class; 75 min jamming station; two EW pallets plus two Meteor-class | +103 kg | Jammer spares, technique library, 12 kW power path and cooling capacity |
| D-3 ferry | 2,100 nm with reserves, clean configuration | +42 kg | Preservation, covers, ferry mission-data loads and ground handling |
| D-4 HVA hunt | 600 nm radius; Mach 1.40 launch point; two SPEAR 3-class plus two Meteor-class | +34 kg | Reinforced chine rails, Meteor interfaces, captive-carry and PV-09 separation campaign |

## 1.3 Programme Quantities

Table 1-3  Programme quantity and cost basis

| Quantity | Value | Note |
| --- | --- | --- |
| Fleet options analysed | 10, 15, 20, 25, 28, 30, 35, 38, 40, 45, 50, 55, 58, 60, 65, 70, 72 | All 17 requested quantities |
| Reference pricing point | 48 aircraft | Calibration point; not a force-structure recommendation |
| Recurring reference unit cost | CAD 24.30M | 2026 CAD; 48-aircraft pricing point |
| Production learning curve | 92% | Unit cost varies with quantity in Part IX |
| Non-recurring engineering | CAD 2.380B | Fixed development and qualification allocation |
| Initial spares/support | CAD 68M + CAD 3.0M per aircraft | Spares pool plus support activation |
| Standard initial effects package | CAD 9.18M per aircraft | Separable weapons account |
| Infrastructure | CAD 150M + CAD 0.55M per aircraft | Bases, depot, production cell and secure digital infrastructure |
| Contingency | 10% | Applied to aircraft, NRE, support, weapons and infrastructure |
| Lifecycle support horizon | 15 years | CAD 1.400B fixed + CAD 31M per aircraft |

## 1.4 Cost Definitions and Boundaries

- Recurring unit cost buys one complete flyaway air vehicle, including installed engine, mission systems, signature materials, assembly, acceptance test, programme fee and flight-line GSE amortisation. It excludes weapons, infrastructure, initial spares and sustainment.

- Total aircraft procurement cost equals fleet quantity multiplied by the learning-curve unit cost.

- Allocated non-recurring cost is the fixed CAD 2.380B development, qualification, test, gateway, tooling and production-readiness allocation. It is not re-estimated downward for small fleets.

- Initial spares/support includes the first depot-cycle spares pool, engine float share, training-and-support activation, mission-control shelter activation, support engineering and initial consumables.

- Total core programme acquisition equals aircraft procurement + NRE + initial spares/support. It excludes weapons, infrastructure, contingency and lifecycle support so the 17 fleet sizes remain directly comparable.

- Decision-basis total acquisition adds the standard initial effects package, infrastructure and 10% contingency. Lifecycle support is shown separately and is not added to acquisition.

- Estimates exclude sales taxes, financing charges, inflation after 2026, classified crypto-key production costs, combat weapon replenishment, disposal and any F-35 programme charges outside the Striker-hosted gateway.

# Part II — Master Parts Breakdown (Air Vehicle)

This part lists the parts, materials and integration services required to build one Striker air vehicle. The register format follows the programme precedent: item and stock-class family, STRK6 part number, description and baseline trace, quantity per aircraft, initial spares quantity at the 48-aircraft reference, CAD unit cost, recurring line cost, lead time and supplier pathway. Supplier codes resolve in Part VII. Line costs are planning allocations and reconcile by category to the recurring build-up in Part IX.

Spares quantities are demand-based starting quantities, not simply one-for-one duplicates. Category pools also include pipeline stock, rotable modules, engine-pool readiness and price/attrition reserve; Part X gives the sustainment logic. National stock numbers remain pending codification, so stock-class families appear instead of invented national item numbers.

## 2.1 Category A — Airframe structure

Primary and secondary structure for the controlled 12.60 m / 11.30 m configuration. Composite shells use out-of-autoclave carbon-epoxy; hot zones use carbon-BMI; recycled titanium, aluminium and carbon fibre enter only where TS v6.1 §6.2 permits. Chine-station structure carries the reinforced Meteor-class interface of §10.5.

Table 2-1  Category A register — Airframe structure

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wing skin panel, upper, port (1560) | STRK6-SKN-001-P | Carbon-epoxy OoA, co-cured stiffeners; controlled planform per TS v6.1 §2.2 | 1 | 5 | 74,000 | 74,000 | 22 wks | BOM / AVC |
| Wing skin panel, upper, starboard (1560) | STRK6-SKN-001-S | Mirror of port; 28.40 m² reference wing area | 1 | 5 | 74,000 | 74,000 | 22 wks | BOM / AVC |
| Wing skin panel, lower, port (1560) | STRK6-SKN-002-P | Lower skin with access cutouts and conductive joint preparation | 1 | 5 | 79,000 | 79,000 | 22 wks | BOM / AVC |
| Wing skin panel, lower, starboard (1560) | STRK6-SKN-002-S | Mirror of port; lightning mesh provisions per §6.5 | 1 | 5 | 79,000 | 79,000 | 22 wks | BOM / AVC |
| Wing spar, front (1560) | STRK6-SPR-001 | Carbon-epoxy I-spar, single-shot co-cure | 1 | 4 | 56,000 | 56,000 | 24 wks | MAG / BOM |
| Wing spar, rear (1560) | STRK6-SPR-002 | Carbon-epoxy I-spar, bonded-plus-bolted attach | 1 | 4 | 56,000 | 56,000 | 24 wks | MAG / BOM |
| Wing rib set (1560) | STRK6-RIB-000 | Fourteen carbon-epoxy ribs and attachment fittings | 1 | 3 | 49,000 | 49,000 | 18 wks | AVC / MAG |
| Fuselage shell, upper (1560) | STRK6-FUS-001-U | OoA shell with integral spine and chine blend; 12.60 m length | 1 | 4 | 94,000 | 94,000 | 26 wks | BOM |
| Fuselage shell, lower (1560) | STRK6-FUS-001-L | Bay and gear cutouts; two 585 L internal bays | 1 | 4 | 98,000 | 98,000 | 26 wks | BOM |
| Centrebody frame set (1560) | STRK6-FRM-010 | Recycled Ti-6Al-4V bulkheads; bay reaction frames | 1 | 3 | 92,000 | 92,000 | 39 wks | MAG / CYC |
| Secondary frame set (1560) | STRK6-FRM-020 | Recycled Al-Li and 7xxx frames, brackets and longerons | 1 | 3 | 44,000 | 44,000 | 20 wks | CYC / MAG |
| Keel beam (1560) | STRK6-KEL-001 | Carbon-epoxy beam with titanium end fittings | 1 | 3 | 52,000 | 52,000 | 22 wks | MAG |
| Chine station structure, port (1560) | STRK6-CHN-001-P | 3.80 m reinforced semi-conformal recess; Meteor-class station | 1 | 3 | 62,000 | 62,000 | 18 wks | BOM / MAG |
| Chine station structure, starboard (1560) | STRK6-CHN-001-S | Mirror of port; 8 kg reinforcement in grown mass model | 1 | 3 | 62,000 | 62,000 | 18 wks | BOM / MAG |
| Chine closure fairing, port (1560) | STRK6-CHF-001-P | Serrated conductive closure fairing | 1 | 5 | 17,000 | 17,000 | 12 wks | AVC |
| Chine closure fairing, starboard (1560) | STRK6-CHF-001-S | Mirror of port | 1 | 5 | 17,000 | 17,000 | 12 wks | AVC |
| Leading-edge section set (1560) | STRK6-LED-010 | Eight carbon-BMI hot-zone sections, Tg 230 °C class | 1 | 4 | 36,000 | 36,000 | 14 wks | BOM / MAG |
| DSI bump, port (1560) | STRK6-BMP-001-P | Fixed-geometry 3D bump with FSS-compatible surface | 1 | 3 | 42,000 | 42,000 | 20 wks | MAG |
| DSI bump, starboard (1560) | STRK6-BMP-001-S | Mirror of port; 0.94 supersonic recovery design point | 1 | 3 | 42,000 | 42,000 | 20 wks | MAG |
| Vertical tail, port (1560) | STRK6-TAL-001-P | 35° canted carbon-epoxy fin with RAM edge treatment | 1 | 3 | 39,000 | 39,000 | 18 wks | AVC / BOM |
| Vertical tail, starboard (1560) | STRK6-TAL-001-S | Mirror of port | 1 | 3 | 39,000 | 39,000 | 18 wks | AVC / BOM |
| Elevon set, four surfaces (1560) | STRK6-ELV-000 | Two inboard high-speed and two outboard low-speed surfaces | 1 | 4 | 96,000 | 96,000 | 14 wks | AVC |
| Rudder segment set (1560) | STRK6-RUD-001 | All-moving canted-tail segments | 2 | 4 | 13,000 | 26,000 | 12 wks | AVC |
| Bay door set (1560) | STRK6-DOR-010 | Four curved serrated doors with recycled-CF inner skins | 1 | 4 | 30,000 | 30,000 | 16 wks | BOM / AVC |
| Access panel and cover set (1560) | STRK6-PNL-000 | Forty-six passport-tracked, gap-controlled positions | 1 | 3 | 25,000 | 25,000 | 12 wks | AVC / SHI |
| Nozzle shroud facet set (1560) | STRK6-SHD-020 | Faceted edge-aligned titanium shroud with ceramic coating | 1 | 3 | 29,000 | 29,000 | 16 wks | MAG / CYC |
| Fairing set, spine and aft (1560) | STRK6-FAI-000 | Recycled-CF non-OML-critical fairings | 1 | 3 | 13,000 | 13,000 | 10 wks | AVC |
| Airframe assembly and proof test allocation (1560) | STRK6-ASSY-A | Centrebody mating, wing join, pressure/leak checks, structural proof and final assembly labour | 1 | 0 | 2,678,000 | 2,678,000 | rate | BOM / MAG |

Category A recurring allocation: CAD 4,100,000.

## 2.2 Category B — Raw materials, fasteners and shop consumables

Per-aircraft material lots and the full traceable fastener bill. Recycled feedstock implements the 482 kg first-article and 595 kg rate-production allocations in TS v6.1 §6.2, with the four exclusions of that section preserved.

Table 2-2  Category B register — Raw materials, fasteners and shop consumables

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Carbon-epoxy OoA prepreg lot (9330) | STRK6-RM-001 | High-Tg epoxy prepreg, per-aircraft structural lot | 1 | 6 | 52,000 | 52,000 | 16 wks | BOM / AVC |
| Carbon-BMI prepreg lot (9330) | STRK6-RM-002 | Hot-zone BMI prepreg for leading edges and duct surrounds | 1 | 6 | 33,000 | 33,000 | 16 wks | BOM |
| Recycled Ti-6Al-4V ingot/plate lot (9510) | STRK6-RM-010 | Closed-loop remelt feedstock; 190 kg finished-part allocation | 1 | 5 | 42,000 | 42,000 | 26 wks | ECO / CYC |
| Recycled Al-Li and 7xxx plate lot (9510) | STRK6-RM-011 | Deep-purification aerospace plate; 78 kg allocation | 1 | 5 | 14,000 | 14,000 | 18 wks | CON / CYC |
| Recycled carbon-fibre panel stock (9330) | STRK6-RM-012 | Secondary panels, bay-door inners and fairings; 76 kg allocation | 1 | 5 | 10,000 | 10,000 | 12 wks | AVC / MAG |
| Recycled Ti LPBF powder lot (9510) | STRK6-RM-013 | Powder for hinges, brackets and duct fittings; 32 kg allocation | 1 | 5 | 17,000 | 17,000 | 14 wks | ECO / CYC |
| Recycled copper conductor stock (9505) | STRK6-RM-014 | Bus-bar and braid stock; 13 kg allocation | 1 | 4 | 3,000 | 3,000 | 8 wks | QDT |
| Recycled steel stock (9505) | STRK6-RM-015 | Pins, fasteners and non-rotating fittings; 9 kg allocation | 1 | 4 | 2,000 | 2,000 | 8 wks | QDT / SHI |
| Primary structural bolt set (5306) | STRK6-FST-001 | Titanium hi-lock-class set with full traceability | 1 | 3 | 78,000 | 78,000 | 12 wks | QDT / SHI |
| Nut and nutplate set (5310) | STRK6-FST-002 | A286 and alloy-steel self-locking hardware | 1 | 3 | 29,000 | 29,000 | 10 wks | QDT / SHI |
| Shear rivet set (5320) | STRK6-FST-003 | Monel and titanium flush rivets, conductive finish | 1 | 3 | 13,000 | 13,000 | 8 wks | QDT |
| Blind fastener set (5320) | STRK6-FST-004 | Structural blind fasteners for bay and panel zones | 1 | 3 | 8,500 | 8,500 | 8 wks | QDT |
| Washer, shim and spacer set (5310) | STRK6-FST-005 | Precision shims and spacers, custom and catalogue | 1 | 3 | 6,500 | 6,500 | 6 wks | SHI |
| Clamp and P-clip set (5340) | STRK6-FST-006 | Cushioned clamps for harness and tube runs | 1 | 3 | 4,400 | 4,400 | 6 wks | QDT / SHI |
| Grommet and seal set (5325) | STRK6-FST-007 | Bulkhead grommets, conductive and plain | 1 | 3 | 2,900 | 2,900 | 6 wks | QDT |
| LO gap filler lot (8030) | STRK6-CNS-001 | Conductive polysulfide signature seam filler | 1 | 5 | 4,600 | 4,600 | 8 wks | QDT |
| Conductive fastener paste (8030) | STRK6-CNS-002 | Silver-loaded paste for RF continuity at countersinks | 1 | 5 | 3,900 | 3,900 | 8 wks | QDT |
| Structural adhesive film lot (8040) | STRK6-CNS-003 | Bonding film for co-bonded joints and doublers | 1 | 5 | 7,500 | 7,500 | 10 wks | QDT / AVC |
| RAM adhesive and primer lot (8040) | STRK6-CNS-004 | Bond system qualified for dual-layer RAM tiles | 1 | 5 | 5,600 | 5,600 | 10 wks | QDT |
| Rain-erosion tape set (9330) | STRK6-CNS-005 | Polyurethane-fluoropolymer leading-edge tape | 1 | 6 | 2,500 | 2,500 | 6 wks | QDT |
| Primer and topcoat lot (8010) | STRK6-CNS-006 | Two-tone grey-blue matte scheme and aft low-emissivity coat | 1 | 5 | 4,900 | 4,900 | 8 wks | QDT |
| Safety wire and shop kit (9505) | STRK6-CNS-007 | Lockwire, cotter pins, thread compound, wipes and solvents | 1 | 6 | 2,000 | 2,000 | 4 wks | QDT |
| Material passport and qualification allocation (9310) | STRK6-QA-B | Lot chemistry, allowables testing, coupon traceability and digital passport records | 1 | 0 | 313,700 | 313,700 | M10-M30 | MAG / ECO / CON |

Category B recurring allocation: CAD 660,000.

## 2.3 Category C — Propulsion and fuel system

The Safran M88-2 is the single engine type for Striker and Sprinter, with a shared inventory and 15% float under TS v6.1 §§4.1 and 12.3. The register covers the DSI duct, exhaust, four-tank fuel architecture, 300 L/min refuelling and the sub-2 h engine-removal interface.

Table 2-3  Category C register — Propulsion and fuel system

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Engine, Safran M88-2 (2840) | STRK6-ENG-001 | 50 kN military / 75 kN augmented, 897 kg bare, dual-channel FADEC; TS v6.1 §4.1 | 1 | 15% pooled float | 6,900,000 | 6,900,000 | 18 mo | SAF |
| FADEC unit, dual-channel (2840) | STRK6-ENG-002 | Engine-mounted, fuel-heated for −40 °C starts | 1 | 5 | 360,000 | 360,000 | 14 mo | SAF |
| Engine mount set, recycled Ti (2840) | STRK6-ENG-003 | Three-point fireproof mount and remelt titanium fittings | 1 | 3 | 60,000 | 60,000 | 20 wks | MAG / CYC |
| Y-duct, serpentine composite (2840) | STRK6-DCT-001 | Merged S-duct with full fan-face blockage | 1 | 2 | 130,000 | 130,000 | 24 wks | MAG / BOM |
| Duct RAM liner set (2840) | STRK6-DCT-002 | Temperature-rated absorber tiles for duct walls | 1 | 4 | 50,000 | 50,000 | 12 wks | QDT / MAG |
| Bypass door assembly (2840) | STRK6-DCT-003 | Subsonic spill and bleed schedule doors | 2 | 4 | 18,000 | 36,000 | 14 wks | MAG |
| Nozzle petal set, CMC (2840) | STRK6-NOZ-001 | Ceramic-matrix flaps with titanium shingles and faceted interface | 1 | 3 | 95,000 | 95,000 | 18 wks | MAG / CYC |
| Nozzle centrebody (2840) | STRK6-NOZ-002 | Film-cooled mixing centrebody | 1 | 3 | 27,000 | 27,000 | 16 wks | MAG |
| Boost pump (2840) | STRK6-FUL-001 | Pressure-feed pump; dual pumps per feed line | 4 | 6 | 12,000 | 48,000 | 10 wks | SAF / QDT |
| Transfer pump (2840) | STRK6-FUL-002 | CG sequencing transfer pump | 2 | 4 | 9,000 | 18,000 | 10 wks | QDT |
| Scavenge ejector set (2840) | STRK6-FUL-003 | Motive-flow ejectors for four tanks | 1 | 3 | 7,500 | 7,500 | 8 wks | QDT |
| Fuel valve and manifold set (2840) | STRK6-FUL-004 | Feed, transfer, defuel and vent valves | 1 | 3 | 21,000 | 21,000 | 10 wks | QDT |
| Nitrogen inerting unit (2840) | STRK6-FUL-005 | OBIGGS-class unit, 14 kg installed | 1 | 3 | 38,000 | 38,000 | 12 wks | THF / QDT |
| Fuel quantity probe set (2840) | STRK6-FUL-006 | Capacitance probes for 1,940 kg four-tank system | 1 | 3 | 9,500 | 9,500 | 8 wks | SED / QDT |
| Single-point pressure refuel adapter (2840) | STRK6-FUL-007 | 300 L/min coupling for 8-minute refuel and 45-minute hot pit | 1 | 3 | 7,000 | 7,000 | 8 wks | QDT |
| Fuel-air cooler (2840) | STRK6-FUL-008 | Dash-segment rejection top-up cooler | 1 | 3 | 24,000 | 24,000 | 12 wks | SAF / QDT |
| Tank sealant and coating kit (8030) | STRK6-FUL-009 | Integral tank sealant, JP-8 / Jet A-1 compatible | 1 | 5 | 7,000 | 7,000 | 8 wks | QDT |
| Fire detection loop set (2840) | STRK6-FIR-001 | Engine bay and bay-module detection | 1 | 3 | 13,000 | 13,000 | 10 wks | QDT / SAF |
| Fire suppression bottle (2840) | STRK6-FIR-002 | Engine bay and bay-module suppression | 2 | 4 | 10,000 | 20,000 | 10 wks | QDT |
| Engine bay insulation set (2840) | STRK6-FIR-003 | Titanium-foil thermal blankets | 1 | 3 | 12,000 | 12,000 | 10 wks | MAG |
| Engine-change rail set, airframe side (2840) | STRK6-GSE-INT-001 | Drop-through rail hardpoints enabling sub-2 h, two-technician exchange | 1 | 2 | 18,000 | 18,000 | 14 wks | MAG / HER |
| Inlet anti-ice bleed valve set (2840) | STRK6-DCT-004 | Subsonic anti-ice bleed schedule | 1 | 3 | 9,000 | 9,000 | 10 wks | SAF |
| FOD screen option kit (2840) | STRK6-DCT-005 | Austere-strip screens; 0.5% recovery penalty when fitted | 1 | 2 | 13,000 | 13,000 | 10 wks | MAG |
| Vibration and oil-debris sensor set (2840) | STRK6-ENG-004 | FADEC health monitoring and condition-based maintenance sensors | 1 | 3 | 8,000 | 8,000 | 8 wks | SAF |
| Propulsion integration and test allocation (2840) | STRK6-ASSY-C | Inlet/engine matching, fuel-system calibration, FADEC integration and acceptance test | 1 | 0 | 269,000 | 269,000 | rate | SAF / MAG |

Category C recurring allocation: CAD 8,200,000.

## 2.4 Category D — Landing gear and brakes

Tricycle gear supports the 660 m dry and 410 m augmented takeoff performance, 750 m landing roll and 25 kt crosswind target of TS v6.1 §5.2. Héroux-Devtek anchors the category in Canada.

Table 2-4  Category D register — Landing gear and brakes

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Nose gear strut assembly (1620) | STRK6-GR-N01 | Oleo-pneumatic strut for road-base operation | 1 | 3 | 92,000 | 92,000 | 26 wks | HER |
| Main gear strut assembly (1620) | STRK6-GR-M01 | Oleo-pneumatic main strut, wing-root retraction | 2 | 4 | 128,000 | 256,000 | 26 wks | HER |
| Nose wheel and tire (1630) | STRK6-GR-N02 | 400 mm class wheel and tire | 1 | 6 | 8,500 | 8,500 | 8 wks | HER / QDT |
| Main wheel and tire set (1630) | STRK6-GR-M02 | Dual-wheel main set for dispersed strips | 1 | 6 | 20,000 | 20,000 | 8 wks | HER / QDT |
| Carbon-carbon brake stack (1630) | STRK6-GR-B01 | 18 MJ capacity against 13.5 MJ RTO demand | 2 | 6 | 29,000 | 58,000 | 14 wks | HER / QDT |
| Anti-skid control unit (1630) | STRK6-GR-B02 | Contaminated-strip braking schedule | 1 | 3 | 23,000 | 23,000 | 12 wks | HER |
| Gear retract actuator set (1620) | STRK6-GR-A01 | Electromechanical retract with pneumatic backup release | 1 | 3 | 39,000 | 39,000 | 16 wks | HER |
| Nosewheel steering unit (1620) | STRK6-GR-S01 | Road-base towing and steering mode | 1 | 3 | 26,000 | 26,000 | 14 wks | HER |
| Gear door set (1560) | STRK6-GR-D01 | Serrated recycled-CF doors with conductive seals | 1 | 3 | 17,000 | 17,000 | 12 wks | AVC |
| Oleo service and seal kit (1620) | STRK6-GR-K01 | Seals, fluid and gas-charge kit | 1 | 8 | 3,800 | 3,800 | 6 wks | HER / QDT |
| Gear proof and brake qualification allocation (1620) | STRK6-ASSY-D | Gear swing, brake-energy acceptance and road-base proof testing | 1 | 0 | 76,700 | 76,700 | rate | HER / IMP |

Category D recurring allocation: CAD 620,000.

## 2.5 Category E — Avionics, sensors and geolocation

The sensor and computing fit implements the 480-element AESA, six-aperture ESM, 45 m CEP cooperative-geolocation requirement, 1,100 TOPS autonomy rack and mission recorder of TS v6.1 §§8.1–8.3 and 10.2. Supplier selections avoid US-controlled silicon and software.

Table 2-5  Category E register — Avionics, sensors and geolocation

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| AESA antenna array, 480 elements (5841) | STRK6-RDR-001 | X-band GaN array, 0.55 m aperture, 125 km class against 1 m²; TS v6.1 §10.2 | 1 | 8 | 950,000 | 950,000 | 16 mo | LEO / SAA |
| AESA repositioner and drive (5841) | STRK6-RDR-002 | Nose repositioner mechanism | 1 | 3 | 88,000 | 88,000 | 12 mo | MAG / MDA |
| Frequency-selective radome (5841) | STRK6-RDR-003 | Band-pass FSS radome matched to array | 1 | 3 | 120,000 | 120,000 | 18 mo | MDA / MAG |
| EODAS aperture (5895) | STRK6-EOD-001 | Distributed MWIR/visible apertures, spherical coverage | 5 | 8 | 105,000 | 525,000 | 12 mo | WES / LEO |
| EO/IR turret, MX-10D class (5895) | STRK6-EOT-001 | Retractable visible/MWIR/SWIR turret with laser rangefinder | 1 | 6 | 450,000 | 450,000 | 12 mo | WES |
| ESM spiral antenna (5895) | STRK6-ESM-001 | Conformal aperture; six form 2.40 m effective baseline | 6 | 10 | 42,000 | 252,000 | 10 mo | LEO / HEN |
| ESM receiver bank (5895) | STRK6-ESM-002 | Wideband digital receivers and threat-library interface | 1 | 8 | 300,000 | 300,000 | 12 mo | HEN / LEO |
| Ruggedised miniaturised atomic clock (6645) | STRK6-CLK-001 | mRO-50-class two-way time-transfer anchor; 8.6 ns residual budget | 2 | 6 | 72,000 | 144,000 | 12 mo | SED |
| Two-way time-transfer radio (5895) | STRK6-GEO-001 | Timing chain supporting 20 ns RSS network budget | 2 | 6 | 110,000 | 220,000 | 12 mo | GDC / MDA |
| Inertial navigation unit (6605) | STRK6-NAV-001 | 0.3 nm/h class drift, GNSS-denied fusion core | 1 | 4 | 90,000 | 90,000 | 12 mo | SED / CMC |
| GNSS anti-jam antenna and receiver (5825) | STRK6-NAV-002 | Multi-constellation digital beamforming nulling | 1 | 4 | 78,000 | 78,000 | 10 mo | CMC |
| Radar altimeter (5841) | STRK6-NAV-003 | Low-altitude precision height reference | 1 | 3 | 39,000 | 39,000 | 8 mo | THF / QDT |
| Flush air-data system port set (6610) | STRK6-NAV-004 | Sixteen heated flush pressure ports; no external probes | 1 | 3 | 46,000 | 46,000 | 10 mo | CMC / QDT |
| IMA rack and backplane (5998) | STRK6-AVC-001 | ARINC 653-class partitioned avionics rack | 2 | 6 | 75,000 | 150,000 | 10 mo | CMC / THF |
| Autonomy compute module, 275 TOPS class (5998) | STRK6-AVC-002 | Rugged non-US-controlled module; four aggregate 1,100 TOPS | 4 | 16 | 45,000 | 180,000 | 10 mo | KON / THF |
| PikeOS safety-partition licence set (7030) | STRK6-AVC-003 | Partitioning OS and certification evidence package | 1 | 3 | 120,000 | 120,000 | 8 mo | SYS / CMC |
| Mission data recorder, 4 TB (5895) | STRK6-AVC-004 | Encrypted full-sortie and decision-trace recorder with zeroise | 1 | 4 | 62,000 | 62,000 | 8 mo | GDC |
| Rugged mission storage module (5998) | STRK6-AVC-005 | Two-TB class removable encrypted storage | 4 | 8 | 11,000 | 44,000 | 4 mo | KON / QDT |
| Cross-domain guard (5895) | STRK6-AVC-006 | Mission-data load guard for squadron station | 1 | 3 | 90,000 | 90,000 | 10 mo | GDC |
| HUMS sensor and fibre set (6625) | STRK6-HUM-001 | Fibre-optic strain channels and interrogator | 1 | 4 | 75,000 | 75,000 | 10 mo | MDA / QDT |
| Terrain-reference database appliance (7030) | STRK6-NAV-005 | Terrain store and vision-aided navigation support | 1 | 2 | 45,000 | 45,000 | 6 mo | CMC / GDC |
| Autonomy rack cold-plate chassis (5998) | STRK6-AVC-007 | Liquid-cooled rack, 2 kW rejection path | 1 | 3 | 25,000 | 25,000 | 8 mo | CYC / MAG |
| RF distribution set (5985) | STRK6-ESM-003 | ESM and geolocation RF plumbing | 1 | 3 | 7,000 | 7,000 | 8 mo | MDA |

Category E recurring allocation: CAD 4,100,000.

## 2.6 Category F — Signature materials and treatments

Dual-layer RAM, cavity treatment, edge control and low-emissivity aft treatment support the shaping-first posture of TS v6.1 §9. The package carries allocations, not certified radar-cross-section claims, until V-LO-01/02/03 complete.

Table 2-6  Category F register — Signature materials and treatments

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| RAM tile set, dual-layer (1560) | STRK6-RAM-001 | Iron-ball magnetic absorber plus dielectric FSS layer; 14.8 m² / 92 kg allocation | 1 | 4 | 240,000 | 240,000 | 14 wks | MAG / QDT |
| Conformal RAM spray lot (8030) | STRK6-RAM-002 | Spray-applied absorber for blended zones | 1 | 5 | 28,000 | 28,000 | 8 wks | QDT |
| Aperture blank panel, conductive (1560) | STRK6-RAM-003 | Avionics-bay EMI/RF shield cover | 1 | 3 | 12,000 | 12,000 | 10 wks | AVC |
| Edge treatment kit (1560) | STRK6-RAM-004 | Conductive tapes and gap-control strips for doors and panels | 1 | 5 | 18,000 | 18,000 | 8 wks | QDT / SHI |
| Duct and cavity absorber lot (1560) | STRK6-RAM-005 | Cavity tiles for inlets, bays and gear wells | 1 | 4 | 42,000 | 42,000 | 10 wks | QDT / MAG |
| IR-suppression topcoat, aft section (8010) | STRK6-RAM-006 | Low-emissivity aft-body and shroud coating | 1 | 5 | 14,000 | 14,000 | 8 wks | QDT |
| FSS radome feedstock and loading kit (1560) | STRK6-RAM-007 | Frequency-selective surface manufacture kit | 1 | 2 | 62,000 | 62,000 | 16 wks | MDA |
| Signature test coupon set (1560) | STRK6-RAM-008 | Lot coupons for reflectometry and compact-range acceptance | 1 | 5 | 12,000 | 12,000 | 8 wks | MAG |
| LO process qualification allocation (1560) | STRK6-QA-F | Coupon, panel and repair-process qualification supporting PV-02 | 1 | 0 | 392,000 | 392,000 | M12-M44 | MAG / QDT |

Category F recurring allocation: CAD 820,000.

## 2.7 Category G — Electronic warfare and self-protection

The internal jammer, expendables and towed-decoy fit closes mission D-2 and the vulnerability-reduction measures of TS v6.1 §§9.3 and 10.3. Annual library renewals after first-year activation sit in sustainment, not flyaway cost.

Table 2-7  Category G register — Electronic warfare and self-protection

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| DRFM jammer unit (5865) | STRK6-EW-001 | 2–18 GHz DRFM-class technique generator; 12 kW peak electrical load | 1 | 6 | 420,000 | 420,000 | 15 mo | LEO / HEN |
| Jammer power amplifier (5865) | STRK6-EW-002 | GaN amplifier set for bay-door and tail-cap apertures | 4 | 8 | 60,000 | 240,000 | 12 mo | HEN / MDA |
| Jammer transmit antenna (5865) | STRK6-EW-003 | Conformal sector transmit aperture | 4 | 8 | 23,000 | 92,000 | 10 mo | MDA / LEO |
| Towed-decoy round (5865) | STRK6-EW-004 | Reusable/attritable RF decoy; two high-threat sortie fit | 2 | 8 | 55,000 | 110,000 | 10 mo | LEO |
| Tow reel and cutter assembly (5865) | STRK6-EW-005 | Deploy, recover and cut mechanism in tail-cone installation | 2 | 4 | 31,000 | 62,000 | 12 mo | MAG / HER |
| Countermeasure magazine (5865) | STRK6-EW-006 | Mixed allied chaff/flare magazine set | 4 | 8 | 11,000 | 44,000 | 8 wks | CHE / QDT |
| EW pod shell (5865) | STRK6-EW-010 | Tail-cone and aperture shell structure for decoy/EW fit | 2 | 4 | 19,000 | 38,000 | 12 wks | AVC / MAG |
| Initial technique-library licence (7030) | STRK6-EW-009 | Mission-data file and reactive-mode library; first-year activation | 1 | 2 | 260,000 | 260,000 | 12 mo | LEO / HEN |
| EW integration and electromagnetic test allocation (5865) | STRK6-ASSY-G | Jammer integration, aperture calibration, EMC and technique-library load | 1 | 0 | 34,000 | 34,000 | rate | HEN / GDC |

Category G recurring allocation: CAD 1,300,000.

## 2.8 Category H — Bay, launch and weapons interface

Two 585 L bays and two 3.80 m reinforced chine stations carry loadouts L1–L7. Hardware supports the Mach 0.95–1.20 interim Meteor release envelope and the Mach 1.40 PV-09 separation campaign of TS v6.1 §10.5.

Table 2-8  Category H register — Bay, launch and weapons interface

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Trapeze-ejector unit (1560) | STRK6-BAY-001 | 0.10 m stroke, 4.4 kN peak, 2.6 m/s ejection; TS v6.1 §10.1 | 2 | 4 | 165,000 | 330,000 | 14 mo | MAG / HER |
| Chine rail, reinforced (1560) | STRK6-BAY-002 | 3.80 m Meteor/IRIS-T-class semi-conformal rail | 2 | 4 | 58,000 | 116,000 | 12 mo | MAG / CYC |
| IRIS-T rail adapter set (1560) | STRK6-BAY-003 | Adapter and umbilical set for IRIS-T station fit | 1 | 4 | 24,000 | 24,000 | 10 mo | DIE / MAG |
| Bay door linear actuator (1560) | STRK6-BAY-004 | High-rate actuator supporting sub-4 s cold-soak sequence | 4 | 6 | 31,000 | 124,000 | 12 mo | HER |
| Store management unit (5895) | STRK6-BAY-005 | MIL-STD-1760-class power/data interface for bays and chines | 2 | 4 | 48,000 | 96,000 | 10 mo | CMC / GDC |
| Store umbilical and connector set (1560) | STRK6-BAY-006 | Bay and chine harnesses and connectors | 1 | 4 | 20,000 | 20,000 | 8 mo | QDT / GDC |
| Pallet adapter rack (1560) | STRK6-BAY-007 | 12 kg adapter lets each bay host two Sprinter-class pallets | 2 | 3 | 38,000 | 76,000 | 12 wks | MAG / AVC |
| Modular mission panel set (1560) | STRK6-BAY-008 | Reversible-role bay panel interfaces | 1 | 3 | 23,000 | 23,000 | 10 wks | AVC |
| SPEAR 3-class ejector interface kit (1560) | STRK6-BAY-009 | Twin-store trapeze arrangement and sway braces | 1 | 3 | 31,000 | 31,000 | 12 mo | MBD / MAG |
| Separation gas-generator set (1377) | STRK6-BAY-010 | Ejector cartridges and stores-release chain | 1 | 6 | 13,000 | 13,000 | 10 mo | QDT / MBD |
| Ballistic liner set, bay walls (1560) | STRK6-BAY-011 | Recycled-CF sandwich bay liners | 1 | 3 | 17,000 | 17,000 | 10 wks | AVC |
| Boresight and sway-brace kit (1560) | STRK6-BAY-012 | Store alignment and restraint hardware | 1 | 4 | 12,000 | 12,000 | 8 wks | SHI / QDT |
| Bay integration and separation-test allocation (1560) | STRK6-ASSY-H | Door/trapeze timing, acoustic lining, fit checks and release-system acceptance | 1 | 0 | 38,000 | 38,000 | rate | MAG / MBD |

Category H recurring allocation: CAD 920,000.

## 2.9 Category I — Communications and datalinks

The suite implements the 20 Mbps mesh, Link 16, Ku SATCOM, CNPC and cross-network gateway requirements of TS v6.1 §§8.2 and 8.6. Gateway copies are software loads; development sits in NRE and no MADL terminal appears anywhere in the register.

Table 2-9  Category I register — Communications and datalinks

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wideband cooperative mesh radio (5895) | STRK6-COM-001 | 20 Mbps / 300 nm class mesh; mesh hand-off enabler | 2 | 8 | 135,000 | 270,000 | 12 mo | GDC / AIR |
| EuroMIDS Link 16 terminal (5895) | STRK6-COM-002 | European Link 16 terminal for Gripen and F-35 gateway path | 1 | 6 | 210,000 | 210,000 | 14 mo | EUM / SAA |
| Ku SATCOM terminal (5895) | STRK6-COM-003 | Low-profile beyond-line-of-sight command link | 1 | 6 | 165,000 | 165,000 | 12 mo | MDA / AIR |
| CNPC radio, L/S band (5895) | STRK6-COM-004 | Line-of-sight command and non-payload control | 2 | 4 | 38,000 | 76,000 | 10 mo | GDC |
| Conformal antenna array set (5985) | STRK6-COM-005 | Shared-aperture arrays for mesh, Link 16, SATCOM and CNPC | 1 | 3 | 52,000 | 52,000 | 12 mo | MDA |
| Cryptographic unit, nationally controlled (5810) | STRK6-COM-006 | Type-1-class crypto and TRANSEC through Canadian account | 2 | 4 | 62,000 | 124,000 | 12 mo | GDC |
| Voice codec and relay module (5895) | STRK6-COM-007 | Voice relay for human-machine teaming | 1 | 3 | 16,000 | 16,000 | 8 mo | GDC / CMC |
| Antenna coupler and diplexer set (5985) | STRK6-COM-008 | RF combining for shared apertures | 1 | 3 | 13,000 | 13,000 | 8 mo | MDA |
| Mesh timing module (5895) | STRK6-COM-009 | Network time synchronisation tied to atomic-clock anchors | 2 | 4 | 11,000 | 22,000 | 8 mo | GDC / SED |
| Communications harness and coax set (6150) | STRK6-COM-010 | RF and digital harnesses for all communications LRUs | 1 | 3 | 9,000 | 9,000 | 8 wks | QDT / AVC |
| Cross-network gateway software load (5895) | STRK6-COM-011 | Mesh-to-Link 16 J-series translation partition; no MADL hardware | 1 | 2 | 55,000 | 55,000 | 8 mo | GDC / CMC |
| Network integration and gateway test allocation (5895) | STRK6-ASSY-I | Link certification, gateway regression and combined-network demonstration support | 1 | 0 | 38,000 | 38,000 | rate | GDC / SAA |

Category I recurring allocation: CAD 1,050,000.

## 2.10 Category J — Electrical power

The more-electric architecture implements TS v6.1 §8.4: 90 kVA generation, 76.5 kW usable capacity, dual 270 VDC buses, 10 kWh battery and 15 kW ram-air turbine. The register carries no central hydraulic system.

Table 2-10  Category J register — Electrical power

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Main generator, 90 kVA class (2920) | STRK6-ELE-001 | Engine-mounted generator feeding dual 270 VDC buses | 1 | 3 | 130,000 | 130,000 | 12 mo | SAF / QDT |
| Generator control unit (6110) | STRK6-ELE-002 | GCU and load-management logic | 1 | 3 | 52,000 | 52,000 | 10 mo | CMC / SAF |
| Power distribution unit (6110) | STRK6-ELE-003 | Solid-state 270 VDC switching and load shedding | 2 | 4 | 58,000 | 116,000 | 10 mo | CMC / QDT |
| Li-ion battery, 10 kWh class (6140) | STRK6-ELE-004 | Main/start battery with thermal management | 1 | 5 | 39,000 | 39,000 | 8 mo | QDT |
| Ram-air turbine, 15 kW class (2920) | STRK6-ELE-005 | Emergency power with automatic deployment | 1 | 2 | 98,000 | 98,000 | 12 mo | THF |
| Contactor and relay set (6110) | STRK6-ELE-006 | High-voltage DC contactors | 1 | 4 | 17,000 | 17,000 | 6 mo | QDT |
| Wiring harness set (6150) | STRK6-ELE-007 | Forward, aft and wing shipset harnesses | 1 | 3 | 74,000 | 74,000 | 14 wks | AVC / QDT |
| Connector lot, D38999 class (5935) | STRK6-ELE-008 | Circular connector shipset with traceability | 1 | 4 | 29,000 | 29,000 | 10 wks | QDT |
| Circuit protection set (5925) | STRK6-ELE-009 | Breakers and solid-state protectors | 1 | 4 | 12,000 | 12,000 | 6 mo | QDT |
| Bonding strap and ground kit (1560) | STRK6-ELE-010 | Lightning and RF continuity bonding | 1 | 4 | 6,000 | 6,000 | 6 wks | SHI / QDT |
| Copper-mesh lightning kit (1560) | STRK6-ELE-011 | Expanded foil mesh in composite OML zones | 1 | 3 | 11,000 | 11,000 | 8 wks | QDT / MAG |
| External LED light set (6220) | STRK6-ELE-012 | Navigation, formation and anti-collision lights with covert mode | 1 | 4 | 13,000 | 13,000 | 6 mo | QDT |
| Electrical integration and bench-test allocation (6110) | STRK6-ASSY-J | Bus fault, load-shed and acceptance testing | 1 | 0 | 23,000 | 23,000 | rate | CMC |

Category J recurring allocation: CAD 620,000.

## 2.11 Category K — Flight controls and actuation

Quadruplex dissimilar flight controls, four 80°/s elevon EHAs and electromechanical rudder/bay actuation implement TS v6.1 §§3.3 and 8.5. The certified software load is the category’s long-lead item.

Table 2-11  Category K register — Flight controls and actuation

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Electrohydrostatic actuator, elevon (1650) | STRK6-ACT-001 | Primary surface EHA, 80°/s class with dual motors | 4 | 6 | 58,000 | 232,000 | 12 mo | HER / QDT |
| Electromechanical actuator, rudder (1650) | STRK6-ACT-002 | All-moving canted-tail rudder segment actuator | 2 | 4 | 32,000 | 64,000 | 10 mo | HER |
| Flight-control computer, dissimilar quad (5895) | STRK6-FCS-001 | 2+2 dissimilar redundancy and quadruplex voting | 4 | 12 | 68,000 | 272,000 | 12 mo | CMC / THC |
| Actuator control electronics (1650) | STRK6-ACT-003 | Distributed ACE units | 6 | 8 | 11,000 | 66,000 | 8 mo | CMC / QDT |
| Trim and feel system set (1650) | STRK6-ACT-004 | Trim motors and control allocation support | 1 | 3 | 15,000 | 15,000 | 8 mo | HER |
| Air-data module (6610) | STRK6-FCS-002 | FADS computation tied to flush ports | 1 | 3 | 22,000 | 22,000 | 8 mo | CMC |
| Flight-control software load (7030) | STRK6-FCS-003 | Certified DAL-A evidence package and per-tail load | 1 | 2 | 180,000 | 180,000 | 18 mo | CMC / SYS |
| Rig pin and tooling set (4920) | STRK6-FCS-004 | Surface-rigging tooling for maintenance | 1 | 2 | 8,000 | 8,000 | 6 mo | QDT / SHI |
| Gust/load alleviation sensor set (6625) | STRK6-FCS-005 | Wing-root and surface load sensors | 1 | 3 | 14,000 | 14,000 | 8 mo | MDA / QDT |
| Local backup power pack (1650) | STRK6-ACT-005 | Local backup for EHA reservoir and electronics | 1 | 2 | 18,000 | 18,000 | 10 mo | HER |
| FCS integration and rig allocation (5895) | STRK6-ASSY-K | Iron-bird integration, gain verification and acceptance testing | 1 | 0 | 29,000 | 29,000 | rate | CMC / HER |

Category K recurring allocation: CAD 920,000.

## 2.12 Category L — Thermal management

The fuel-sink-first architecture implements TS v6.1 §§7.1–7.3, including 163 MJ heat-sink capacity, 135 MJ mission rejection, ram-air ground cooling and the −40 °C Arctic preheat kit.

Table 2-12  Category L register — Thermal management

| Item / stock class | Part number | Description and TS v6.1 trace | Qty/AC | Spares | Unit cost (CAD) | Line cost (CAD) | Lead | Supplier(s) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Liquid coolant pump (1660) | STRK6-THM-001 | Glycol-loop pump; dual redundant pairs | 4 | 6 | 12,000 | 48,000 | 8 mo | QDT / SAF |
| Fuel heat exchanger (1660) | STRK6-THM-002 | Primary rejection to 1,910 kg usable-fuel heat sink | 1 | 3 | 25,000 | 25,000 | 10 mo | SAF / QDT |
| Ram-air heat exchanger (1660) | STRK6-THM-003 | Flush supplemental rejection for ground and cruise | 1 | 3 | 20,000 | 20,000 | 10 mo | QDT / MAG |
| Avionics cold-plate set (1660) | STRK6-THM-004 | IMA and autonomy rack liquid cold plates | 1 | 3 | 17,000 | 17,000 | 8 mo | CYC / QDT |
| Coolant reservoir and accumulator (1660) | STRK6-THM-005 | Loop pressurisation and expansion | 1 | 3 | 7,000 | 7,000 | 6 mo | QDT |
| Thermal valve and manifold set (1660) | STRK6-THM-006 | Loop routing and isolation | 1 | 3 | 10,000 | 10,000 | 6 mo | QDT |
| Temperature sensor set (6685) | STRK6-THM-007 | Loop and rack monitoring | 1 | 4 | 5,000 | 5,000 | 4 mo | QDT |
| Avionics bay fan (1660) | STRK6-THM-008 | Ground-cooling local air mover | 2 | 4 | 4,000 | 8,000 | 4 mo | QDT |
| Battery/FADEC preheat blanket set (1660) | STRK6-THM-009 | 3 kW / 45 min Arctic preheat support | 1 | 4 | 6,000 | 6,000 | 4 mo | QDT / CAS |
| Duct insulation and liner set (1660) | STRK6-THM-010 | Thermal and acoustic duct treatment | 1 | 3 | 7,000 | 7,000 | 6 wks | MAG |
| Thermal rig and hot-day test allocation (1660) | STRK6-ASSY-L | Fuel-sink calibration, ground cooling and V-TH-01/02 acceptance support | 1 | 0 | 227,000 | 227,000 | rate | CMC / SAF |

Category L recurring allocation: CAD 380,000.

## 2.13 Category Summary and Initial Spares Pool

Table 2-13  Category recurring and spares rollup

| Cat. | Category | Register lines | Recurring/AC (CAD M) | Initial spares pool (CAD M) |
| --- | --- | --- | --- | --- |
| A | Airframe structure | 28 | 4.10 | 9.0 |
| B | Raw materials, fasteners and shop consumables | 23 | 0.66 | 2.4 |
| C | Propulsion and fuel system | 25 | 8.20 | 70.0 |
| D | Landing gear and brakes | 11 | 0.62 | 2.8 |
| E | Avionics, sensors and geolocation | 23 | 4.10 | 26.0 |
| F | Signature materials and treatments | 9 | 0.82 | 2.0 |
| G | Electronic warfare and self-protection | 9 | 1.30 | 9.0 |
| H | Bay, launch and weapons interface | 13 | 0.92 | 4.2 |
| I | Communications and datalinks | 12 | 1.05 | 7.0 |
| J | Electrical power | 13 | 0.62 | 3.0 |
| K | Flight controls and actuation | 11 | 0.92 | 6.5 |
| L | Thermal management | 11 | 0.38 | 1.4 |
| — | Subtotal, Categories A–L | 188 | 23.69 | 143.3 |
| — | Spares pipeline and readiness reserve | — | — | 0.7 |
| — | Initial spares pool total | — | — | 144.0 |

The CAD 144.0M spares pool is the variable component of the 48-aircraft initial support line. The remaining CAD 68.0M funds support activation, training-and-support services, shelters, support engineering and initial consumables. Together they produce the Part IX formula: CAD 68M + CAD 3.0M per aircraft.

# Part III — Weapons and Stores Provisioning

Weapons remain a separate account outside recurring flyaway cost, NRE and initial spares/support. The package uses only Canadian-allied, non-US sources and mirrors the loadouts of TS v6.1 §§5.1 and 10.1. Quantities below show the 48-aircraft reference case; the decision model scales each weapon class linearly at 1× Meteor, 2× SPEAR 3-class, 2× SmartGlider Light, 2× IRIS-T and 2× towed-decoy rounds per aircraft.

Table 3-1  Weapons and expendables initial provisioning — 48-aircraft reference

| Store | Part number | Description | Scale basis | Qty | Unit cost (CAD) | Line total (CAD) | Supplier |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Meteor-class ER-AAM | STRK6-WPN-001 | 3.70 m / 190 kg class; reinforced chine fit; D-4 HVA play | 1 / aircraft | 48 | 2,850,000 | 136,800,000 | MBD |
| SPEAR 3-class standoff weapon | STRK6-WPN-002 | D-1 primary effect; bay trapeze fit | 2 / aircraft | 96 | 1,550,000 | 148,800,000 | MBD |
| SmartGlider Light | STRK6-WPN-003 | 120 kg class compact glide weapon; L3/L5/L7 fits | 2 / aircraft | 96 | 920,000 | 88,320,000 | MBD |
| IRIS-T | STRK6-WPN-004 | Close self-defence on chine stations; 95 kg per station including rail | 2 / aircraft | 96 | 620,000 | 59,520,000 | DIE |
| Towed-decoy rounds | STRK6-WPN-005 | High-threat sortie expenditure stock | 2 / aircraft | 96 | 75,000 | 7,200,000 | LEO |
| Standard initial effects total | — | Mixed inventory supporting D-1, D-2, D-4 and training | 9.18 CAD M / aircraft | — | — | 440,640,000 | — |

Separation status follows TS v6.1 §§10.1 and 10.5: bay stores use the Mach 1.20 / 3.0 g trapeze envelope, subject to PV-04 acoustic confirmation; Meteor-class separation at Mach 1.40 remains PV-09. The interim Mach 0.95–1.20 release envelope preserves D-21 geometry with a reduced-reach profile. No US-origin SDB, AIM-9X or AIM-120 line appears in this v6.1 package.

# Part IV — Ground Support Equipment

GSE supports the 268.6-minute full turnaround, 45-minute hot pit, two-technician road-base detachment, sub-2 h engine removal and 2.4-sortie surge day of TS v6.1 §§4.4, 11.1, 11.4 and 12.4. Quantities provision one main operating base and four forward operating locations at the 48-aircraft reference.

Table 4-1  Ground support equipment provisioning

| Equipment | Part number | Description | Qty | Unit cost (CAD) | Line total (CAD) | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Mission control element shelter | STRK6-GSE-001 | Deployable planning/control shelter; four operators | 4 | 1,750,000 | 7,000,000 | GDC / CAE |
| Mission planning station | STRK6-GSE-002 | Corridor planning, mesh rehearsal and cross-domain load | 8 | 520,000 | 4,160,000 | CAE / GDC |
| Tow tractor, 5-tonne class | STRK6-GSE-003 | Airfield and road-base tow | 6 | 210,000 | 1,260,000 | QDT |
| Weapons loading cart | STRK6-GSE-004 | Bay and chine store loading, one L1 loadout | 8 | 95,000 | 760,000 | MAG / HER |
| Engine-change rail and hoist set | STRK6-GSE-005 | Drop-through M88-2 change; sub-2 h target | 4 | 260,000 | 1,040,000 | MAG / HER |
| Ground power unit, 270 VDC | STRK6-GSE-006 | Hangar and flight-line power | 8 | 58,000 | 464,000 | QDT |
| Preheat cart, Arctic kit | STRK6-GSE-007 | 3 kW battery/FADEC preheat, −40 °C | 6 | 52,000 | 312,000 | QDT / CAS |
| LO repair field kit | STRK6-GSE-008 | RAM panel, gap-filler and edge-tape repair | 12 | 33,000 | 396,000 | QDT / MAG |
| Signature reflectometry test set | STRK6-GSE-009 | Handheld panel-health and bond-line verification | 8 | 76,000 | 608,000 | QDT |
| Jack and cradle set | STRK6-GSE-010 | Airframe jacking and gear-swing support | 4 | 66,000 | 264,000 | HER |
| Brake service cart | STRK6-GSE-011 | Carbon-brake change and service | 4 | 25,000 | 100,000 | QDT |
| FOD screen install kit | STRK6-GSE-012 | Austere-strip screen tooling | 4 | 16,000 | 64,000 | MAG |
| Intake/exhaust cover set | STRK6-GSE-013 | Environmental protection and storage | 12 | 9,000 | 108,000 | QDT |
| Battery service station | STRK6-GSE-014 | Charge, test and thermal check | 4 | 30,000 | 120,000 | QDT |
| Composite NDT kit | STRK6-GSE-015 | Pulse-echo and thermography field inspection | 4 | 120,000 | 480,000 | QDT |
| HUMS download station | STRK6-GSE-016 | Strain-data retrieval and fleet trending | 4 | 88,000 | 352,000 | MDA / CAE |
| GSE total | — | Main operating base plus four forward locations | — | — | 17,488,000 | — |

GSE is procured as a deployable capability set, not as a per-aircraft flyaway line. Flight-line items amortise inside the recurring fee/GSE allowance; mission-control shelters and planning stations ride the support-activation line; depot duplicates appear in Part X only where they add depot capability.

# Part V — Training System

Training piggybacks on the Gripen syllabus per TS v6.1 §11.4: quarterback crews rehearse teaming and consent, maintenance crews share approximately 60% of tasks with Sprinter, and type-specific modules cover bays, RAM panels, EW and engine change. CAE anchors the Canadian training package.

Table 5-1  Training system provisioning

| Item | Part number | Description | Qty | Unit cost (CAD) | Line total (CAD) | Supplier |
| --- | --- | --- | --- | --- | --- | --- |
| Full-mission simulator, Striker–Gripen networked | STRK6-TRN-001 | MUM-T rehearsal, mesh hand-off and D-1 to D-4 mission sets | 2 | 6,600,000 | 13,200,000 | CAE |
| Part-task trainer, mission systems | STRK6-TRN-002 | AESA, ESM, EW and cooperative-geolocation procedures | 2 | 2,200,000 | 4,400,000 | CAE |
| Maintenance trainer, airframe/propulsion | STRK6-TRN-003 | LRU swap, engine change, LO repair and Arctic servicing | 2 | 2,600,000 | 5,200,000 | CAE / IMP |
| Initial courseware package | STRK6-TRN-004 | Operator, quarterback and maintainer syllabi | 1 | 3,400,000 | 3,400,000 | CAE |
| Synthetic environment licence, 5-year | STRK6-TRN-005 | Opening Doors scenarios, threat libraries and gateway events | 1 | 2,100,000 | 2,100,000 | CAE |
| Instructor cadre and first two course iterations | STRK6-TRN-006 | Pilot, coordinator, safety-pilot and maintainer qualification | 1 | 2,300,000 | 2,300,000 | CAE / IMP |
| Training system total | — |  | — | — | 30,600,000 | — |

# Part VI — Facilities and Infrastructure

Facilities are programme capital items. The 48-aircraft reference case equals CAD 176.4M and matches the decision-model formula CAD 150M + CAD 0.55M per aircraft. Mirabel is the production anchor; depot and main-base choices remain subject to site competition and government approval.

Table 6-1  Facilities and infrastructure — 48-aircraft reference

| Facility | Location | Description | Qty | Unit cost (CAD) | Line total (CAD) |
| --- | --- | --- | --- | --- | --- |
| Main operating base hangar, four-bay | Cold Lake / Comox class | Climate-controlled hangar, LO repair booth, secure planning spaces | 2 | 25,000,000 | 50,000,000 |
| Forward operating location kit | Road-base class strip | Deployable shelter, preheat, fuel interface and communications mast | 4 | 4,500,000 | 18,000,000 |
| Depot line activation | IMP Halifax or Cascade Abbotsford | 600 h inspections, composite repair, NDT and avionics benches | 1 | 24,000,000 | 24,000,000 |
| Composite manufacturing cell | Mirabel, QC | OoA ovens, clean rooms, automated layup and mating jig | 1 | 62,000,000 | 62,000,000 |
| Recycled-materials processing agreement | Canada–France closed loop | Scrap return, certified remelt, material passports and lot traceability | 1 | 7,000,000 | 7,000,000 |
| Secure software and gateway integration centre | Ottawa / Montreal class | Autonomy, mesh, gateway, cyber and mission-data release environment | 1 | 12,000,000 | 12,000,000 |
| Fleet-capacity allowance | 48-aircraft reference | Aprons, storage, support-space fit-out and utility growth | 1 | 3,400,000 | 3,400,000 |
| Facilities total | — |  | — | — | 176,400,000 |

# Part VII — Supplier Directory and Outreach Pathways

Every supplier code in Parts II–VI resolves below. Canadian suppliers lead where capability exists; allied sources are limited to France, Sweden, Germany, the United Kingdom, Italy, Austria and other close Canadian allies outside the United States. Supplier naming identifies a credible engagement pathway, not a commitment or sole-source award. Each line still requires qualification, export-control screening and contract competition or direction under Canadian procurement rules.

Table 7-1  Supplier directory

| Code | Supplier and location | Public domain | Role in programme |
| --- | --- | --- | --- |
| BOM | Bombardier Aerostructures, Mirabel, QC (Canada) | bombardier.com | Large composite shells, co-cured structures, final-assembly-scale facilities |
| AVC | Avcorp Industries, Delta, BC (Canada) | avcorp.com | Composite structures, bonded assemblies, secondary structure |
| MAG | Magellan Aerospace, Winnipeg, MB / Mississauga, ON (Canada) | magellan-aerospace.com | Composite and metallic aerostructures, machined assemblies, engine-adjacent structures |
| HER | Héroux-Devtek, Longueuil, QC (Canada) | herouxdevtek.com | Landing gear, actuation, gear machining and aftermarket support |
| CYC | Cyclone Manufacturing, Mississauga, ON (Canada) | cyclonemfg.com | Five-axis titanium and aluminium machining, fittings and housings |
| SHI | Shimco, Markham, ON (Canada) | shimco.com | Precision shims, washers, spacers and small flight hardware |
| CMC | CMC Electronics, Montreal, QC (Canada) | cmcelectronics.ca | Military avionics, GNSS anti-jam, mission computers and integration |
| MDA | MDA, Brampton, ON (Canada) | mda.space | Conformal antennas, RF structures, satellite and timing assemblies |
| GDC | General Dynamics Mission Systems–Canada, Ottawa, ON (Canada) | gd-ms.ca | Secure communications, crypto integration, Link 16 systems and cross-domain guards |
| THC | Thales Canada, Montreal, QC / Toronto, ON (Canada) | thalesgroup.com/canada | Canadian avionics, mission systems, training support and secure integration |
| WES | Wescam, Burlington, ON (Canada) | wescam.com | MX-class EO/IR turrets; Canadian manufacturing and support |
| CAE | CAE, Montreal, QC (Canada) | cae.com | Training systems, constructive simulation and synthetic environments |
| IMP | IMP Aerospace and Defence, Halifax, NS (Canada) | impaerospace.com | Depot-level MRO, structural repair and avionics lines |
| CAS | Cascade Aerospace, Abbotsford, BC (Canada) | cascadeaerospace.com | Field-level MRO, western support node and component repair |
| STD | StandardAero, Winnipeg, MB (Canada) | standardaero.com | Canadian engine MRO partner under Safran licence and data agreement |
| QDT | Qualified distributor channel, Canada / allied stocking sites | AS9120-registered distributors | Traceable standard hardware, connectors, seals, adhesives and consumables |
| SAF | Safran Aircraft Engines, Paris / Villaroche (France) | safran-group.com | M88-2 engine, FADEC, modules, technical data and OEM support |
| SED | Safran Electronics & Defense, France | safran-group.com | Inertial navigation, timing, clocks and avionics support |
| ECO | EcoTitanium, Saint-Georges-de-Mons (France) | ecotitanium.com | Closed-loop recycled titanium ingot and certified remelt |
| CON | Constellium, France (allied operations) | constellium.com | Aerospace aluminium plate and closed-loop aluminium routes |
| TAR | Tarmac Aerosave, France / Spain | tarmacaerosave.com | Aircraft recycling, controlled scrap streams and material passports |
| MBD | MBDA, France / United Kingdom / Italy / Germany | mbda-systems.com | Meteor, SPEAR 3-class and SmartGlider-class weapons and integration data |
| DIE | Diehl Defence, Überlingen (Germany) | diehl.com/defence | IRIS-T weapons, launcher interfaces and support |
| LEO | Leonardo, Italy / United Kingdom | leonardo.com | AESA candidate, ESM, electronic attack and self-protection systems |
| SAA | Saab, Linköping (Sweden) / Saab Canada, Ottawa | saab.com | Gripen E interface, AESA candidate and tactical-network integration |
| HEN | HENSOLDT, Germany | hensoldt.net | ESM, EW receivers, sensor processing and spectrum systems |
| THF | Thales, France | thalesgroup.com | Mission computing, communications and avionics equipment |
| SYS | SYSGO, Germany | sysgo.com | PikeOS partitioning operating system and certification evidence |
| KON | Kontron, Austria / Germany | kontron.com | Rugged non-US-controlled compute modules and avionics integration |
| AIR | Airbus Defence and Space, France / Germany / Spain | airbus.com | Secure networking, C2 integration and coalition gateway support |
| CHE | Chemring Countermeasures, United Kingdom | chemring.com | Allied chaff, flare and expendable countermeasure supply |
| EUM | EuroMIDS consortium, France / Germany / Italy / Spain | euromids.com | Link 16 terminal supply through European consortium channels |

## 7.1 Standard Engagement Sequence

- Issue request for information through the supplier portal or public-domain contact; identify Canadian content, allied content and any US-origin content before technical data exchange.

- Execute an NDA, complete controlled-goods and facility-clearance screening, and exchange only the controlled TS v6.1 extract needed for quotation.

- Run the export-control classification matrix of Part XI before releasing drawings, software, weapon interfaces, crypto details or geolocation timing data.

- Issue RFQ with AS9100, AS9102, AS9120, NADCAP, counterfeit-prevention, material-passport and data-rights flow-downs as applicable.

- Qualify the source through site audit, first-article planning, special-process review, cybersecurity review and sustainment-capacity review.

- Place the line on contract through the route in Part VIII, register Canadian workshare and industrial-benefit credit, and open the repair-data and spares pipeline at contract award.

# Part VIII — Acquisition Strategy and Procurement Routes

## 8.1 Route by Line Type

Table 8-1  Procurement route by line type

| Line type | Route | Contract form |
| --- | --- | --- |
| Canadian airframe, gear, GSE, training and support | PSPC competitive or directed source under Canadian industrial-benefit policy | Firm-fixed-price production lots with priced options |
| M88-2 engine and modules | Government-endorsed direct commercial agreement with Safran; Canadian MRO licence through StandardAero | FFP with engine-pool annex and support options |
| European weapons | Government-to-government arrangements through DND/PSPC with MBDA and Diehl export approvals | G2G arrangement with integration data and offsets |
| COMSEC-controlled items | Canadian COMSEC account and controlled-goods channels; no commercial substitution | Government account transfer |
| Standard hardware and consumables | AS9120-registered Canadian/allied distributors | Blanket purchase agreements with buffer stock |
| Recycled feedstock streams | Direct long-term agreements with EcoTitanium, Constellium-route chain and Tarmac Aerosave | Ten-year closed-loop agreement with scrap-return annex |
| European avionics, EW and mission systems | Competitive tender or directed source with Canadian integration workshare | FFP plus integration-support and data-licence line |
| Software and mission data | Direct licence from SYSGO, CMC, GDC, CAE or European mission-system supplier; classification review first | Per-tail and enterprise licences with escrow/data-rights clauses |
| Depot and engine maintenance | Competitive Canadian MRO selection: IMP, Cascade and StandardAero roles under OEM licences | Availability-based support contract with repair TAT incentives |

## 8.2 Industrial and Canadian Priority Rule

The acquisition strategy applies a three-step source test. First, qualify a Canadian supplier and register the workshare. Second, if no qualified Canadian capability exists, qualify a Canadian operation or Canadian integrator for final assembly and support. Third, if domestic capability still does not exist, source from a close Canadian ally outside the United States and secure repair data, licensed manufacture or Canadian sustainment rights. A US-origin substitution requires programme-office waiver, export-control reclassification and a documented reason no compliant source can close the requirement.

## 8.3 Competition Posture

Three genuine competitions remain open: AESA array (Leonardo versus Saab), depot lead (IMP Halifax versus Cascade Abbotsford), and Canadian air-vehicle integrator workshare allocation among Bombardier, Magellan and IMP. Engine, weapons and COMSEC items follow government-endorsed or government-account routes because the technical baseline and sovereignty objectives make arbitrary commercial substitution counterproductive.

# Part IX — Cost Analysis and Fleet Economics

## 9.1 Recurring Unit-Cost Reconciliation

Table 9-1  Recurring unit-cost build-up at 48-aircraft reference

| Cat. | Build-up line | CAD M / aircraft |
| --- | --- | --- |
| A | Airframe structure | 4.10 |
| B | Raw materials, fasteners and shop consumables | 0.66 |
| C | Propulsion and fuel system | 8.20 |
| D | Landing gear and brakes | 0.62 |
| E | Avionics, sensors and geolocation | 4.10 |
| F | Signature materials and treatments | 0.82 |
| G | Electronic warfare and self-protection | 1.30 |
| H | Bay, launch and weapons interface | 0.92 |
| I | Communications and datalinks | 1.05 |
| J | Electrical power | 0.62 |
| K | Flight controls and actuation | 0.92 |
| L | Thermal management | 0.38 |
| — | Categories A–L subtotal | 23.69 |
| — | Programme fee, acceptance and flight-line GSE amortisation | 0.61 |
| — | Recurring unit cost at 48-aircraft reference | 24.30 |

The category build-up prices the larger v6.1 aircraft, the real M88-2 engine, the dual-bay and reinforced-chine configuration, the circular-materials chain, the 480-element AESA, the EW fit and the non-US computing baseline. It contains no hidden growth allowance; the 140 kg remaining mass allowance in TS v6.1 §2.3 remains an engineering margin, while price uncertainty sits in programme contingency.

## 9.2 Non-Recurring Programme Cost

Table 9-2  Non-recurring engineering and programme-readiness build-up

| NRE line | CAD M | Content |
| --- | --- | --- |
| Design maturation, systems engineering and configuration control | 420 | CDR-to-qualification engineering, digital thread, safety case |
| Aerodynamics, inlet, propulsion and altitude-facility verification | 360 | V-AE and V-PR campaigns; M88-2 installation closure |
| Structures, materials and recycled allowables | 285 | FEA, ground vibration, flutter, fatigue, PV-05 database |
| Signature, thermal and environmental qualification | 230 | V-LO, V-TH, V-EN, lightning/HIRF and repair-process evidence |
| Mission systems, autonomy, mesh hand-off and gateway | 410 | V-AV series, 50,000-scenario assurance, Link 16 gateway |
| Weapons interface and separation campaigns | 180 | Bay acoustics, captive carry, V-MB-03 PV-09 campaign |
| Flight test and operational test | 295 | V-FT-01..06 and V-OT-01 through IOC |
| Production tooling and manufacturing readiness | 200 | Mirabel cell activation, mating jig, supplier FAIs and rate-readiness |
| Non-recurring programme total | 2,380 | Fixed allocation across all fleet sizes |

## 9.3 Fleet-Quantity Cost Model

The model is deliberately simple and auditable. Unit recurring cost U(N) = CAD 24.30M × (N/48)^b, where b = ln(0.92)/ln(2). Initial spares/support S(N) = CAD 68M + CAD 3.0M × N. Core programme acquisition C(N) = N × U(N) + CAD 2.380B + S(N). All values below are CAD millions, rounded to 0.1M; totals may differ by rounding.

Table 9-3  Seventeen comparable fleet-size scenarios — core programme economics

| Aircraft quantity | Recurring unit cost | Total aircraft procurement | Allocated NRE | Initial spares/support | Total core programme acquisition |
| --- | --- | --- | --- | --- | --- |
| 10 | 29.3 | 293.5 | 2,380.0 | 98.0 | 2,771.5 |
| 15 | 27.9 | 419.2 | 2,380.0 | 113.0 | 2,912.2 |
| 20 | 27.0 | 540.0 | 2,380.0 | 128.0 | 3,048.0 |
| 25 | 26.3 | 657.1 | 2,380.0 | 143.0 | 3,180.1 |
| 28 | 25.9 | 726.0 | 2,380.0 | 152.0 | 3,258.0 |
| 30 | 25.7 | 771.4 | 2,380.0 | 158.0 | 3,309.4 |
| 35 | 25.2 | 883.4 | 2,380.0 | 173.0 | 3,436.4 |
| 38 | 25.0 | 949.7 | 2,380.0 | 182.0 | 3,511.7 |
| 40 | 24.8 | 993.6 | 2,380.0 | 188.0 | 3,561.6 |
| 45 | 24.5 | 1,102.0 | 2,380.0 | 203.0 | 3,685.0 |
| 50 | 24.2 | 1,209.0 | 2,380.0 | 218.0 | 3,807.0 |
| 55 | 23.9 | 1,314.8 | 2,380.0 | 233.0 | 3,927.8 |
| 58 | 23.8 | 1,377.7 | 2,380.0 | 242.0 | 3,999.7 |
| 60 | 23.7 | 1,419.4 | 2,380.0 | 248.0 | 4,047.4 |
| 65 | 23.4 | 1,522.9 | 2,380.0 | 263.0 | 4,165.9 |
| 70 | 23.2 | 1,625.5 | 2,380.0 | 278.0 | 4,283.5 |
| 72 | 23.1 | 1,666.3 | 2,380.0 | 284.0 | 4,330.3 |

Figure 9-1  Fleet quantity effect on recurring unit cost and core programme acquisition

## 9.4 Decision-Basis Adders

The decision summary in Part XIV adds three separable lines to the core model: standard initial effects package W(N) = CAD 9.18M × N; infrastructure I(N) = CAD 150M + CAD 0.55M × N; and contingency = 10% of C(N) + W(N) + I(N). Lifecycle support is estimated separately at CAD 1.400B + CAD 31M × N over 15 years. This treatment keeps aircraft economics comparable while still giving decision-makers the complete acquisition exposure.

Figure 9-2  48-aircraft reference acquisition breakdown

## 9.5 Cost Sensitivity and Control Points

Table 9-4  Planning sensitivities at the 48-aircraft reference

| Driver | Planning swing | 48-aircraft exposure | Control point |
| --- | --- | --- | --- |
| M88-2 engine price or support terms | ±10% of installed engine value | ±CAD 33M recurring procurement | Government-endorsed Safran agreement, pooled float and Canadian MRO licence |
| AESA competition result | ±15% of sensor category | ±CAD 29M recurring procurement | Fund Leonardo and Saab risk-reduction through CDR down-select |
| NRE growth | ±10% | ±CAD 238M programme | Stage NRE against verification events; no scope addition without change control |
| Allied export-permit delay | No direct price model; schedule exposure | Potential long-lead slip | Permit packages at M6; substitutions prohibited without waiver |
| Recycled-stream yield shortfall | +CAD 0.25M per aircraft planning case | +CAD 12M at 48 | Dual-source remelt and primary-stock fallback with zero mass delta |
| Learning curve worsens from 92% to 95% | Unit 10 rises; unit 72 rises | Approximately +CAD 90M recurring across 48 | Rate-production tooling, stable configuration and lot options |
| Contingency policy | 5% / 10% / 15% | CAD 219M / 438M / 656M at reference decision basis | Hold 10% until CDR evidence converts pending items |

# Part X — Sustainment Package

Sustainment translates TS v6.1 requirements into people, equipment, spares and money. The package below supports the 268.6-minute full turnaround, 45-minute hot pit, sub-2 h engine removal, 22-LRU architecture, 92% built-in-test coverage, 150 h phased interval, 600 h depot event, 1,200 h life and 2.0/2.4 sorties per aircraft-day.

## 10.1 Requirement-to-Resource Translation

Table 10-1  Technical requirement translated into sustainment resources

| TS v6.1 requirement | Procurement resource response | Cost treatment |
| --- | --- | --- |
| 268.6 min full turnaround; 45 min hot pit (§§11.1, 12.4) | Two-technician launch/recovery team per road-base pair; reload cart with one L1 loadout; 300 L/min refuel; preheat and ground power; pre-staged mission-data loads | Part IV GSE; support activation; manpower |
| Engine exchange under 2 h by two technicians (§4.4) | Airframe rail set plus depot/field rail-and-hoist kits; pooled M88-2 float; StandardAero/Safran Canadian repair path | Category C; GSE; engine-pool support |
| 22 LRUs at 15 min class; 92% BIT coverage (§11.1) | Rotable pool by LRU; BIT scripts; bench-test equipment; 30-day repair-turnaround target | Category spares; Part X repair pipeline |
| 150 h phased / 600 h depot / 1,200 h life (§11.1) | Phased inspection kits, NDT, composite repair, LO reflectometry and depot line activation | Facilities; sustainment labour; depot equipment |
| LO upkeep ≤12% of maintenance hours at maturity (§9.4) | One dedicated LO technician per four aircraft for first two years; modular RAM panel stock; passport-controlled repairs | Manpower; Category F spares; training |
| −40 °C cold soak and 45 min preheat (§§2.1, 11.2) | Preheat carts, battery/FADEC blankets, cold-soak consumables and Arctic kit spares | GSE; Category L; operating consumables |
| 2.0 sustained / 2.4 surge sorties per aircraft-day (§12.4) | Two full turn teams per four-aircraft flight; attrition reserve; decoy and expendable re-stock pipeline | Manpower; weapons/expendables account |
| Mission recorder sync under 10 min (§10.4) | Squadron planning station, guarded maintenance link and encrypted storage pool | GSE; software support |

## 10.2 Initial Spares and Repairable Pool

Table 10-2  Initial spares package at 48-aircraft reference

| Category | Scope | CAD M |
| --- | --- | --- |
| A | Airframe structure | 9.0 |
| B | Raw materials, fasteners and shop consumables | 2.4 |
| C | Propulsion and fuel system | 70.0 |
| D | Landing gear and brakes | 2.8 |
| E | Avionics, sensors and geolocation | 26.0 |
| F | Signature materials and treatments | 2.0 |
| G | Electronic warfare and self-protection | 9.0 |
| H | Bay, launch and weapons interface | 4.2 |
| I | Communications and datalinks | 7.0 |
| J | Electrical power | 3.0 |
| K | Flight controls and actuation | 6.5 |
| L | Thermal management | 1.4 |
| — | Spares pipeline and readiness reserve | 0.7 |
| — | Initial spares pool total | 144.0 |

- Engine float: 15% shared M88-2 pool with the Sprinter fleet; Striker’s 48-aircraft share rounds to eight installed-spare equivalents, with recoverable attrition engines returned to the pool where practical.

- LRU float: rotables sized to the 22-LRU architecture, 15-minute removal target and 30-day repair-pipeline objective; BIT isolation avoids line removal where a software or connector fault is indicated.

- Signature stock: modular RAM panels, edge tape, gap filler, conductive paste and reflectometry coupons align to the 46-panel maintenance map and material passport.

- Arctic stock: preheat blankets, seals, hydraulics-free actuation service kits, brake/tire stock and contaminated-strip consumables support dispersed operation.

- Expendables: towed-decoy rounds, allied chaff/flare, separation cartridges and shop consumables sit outside flyaway cost and re-stock by usage.

## 10.3 Depot Equipment and Repair Pipeline

Table 10-3  Depot equipment and repair pipeline

| Capability | Planned provider | Resource | Turnaround / capacity target |
| --- | --- | --- | --- |
| 600 h depot inspection and structural repair | IMP Halifax (primary candidate); Cascade Abbotsford (competitive alternate) | Composite repair shop, NDT, structural jigs, LO booth | Two-aircraft induction capacity at rate |
| M88-2 module maintenance | StandardAero Winnipeg under Safran licence; Safran France for OEM escalation | Engine test-cell access, module tooling, FADEC bench and QEC kit | 30-day module pipeline; sub-2 h aircraft exchange |
| Avionics and mission-system repair | CMC / GDC / Thales Canada with European OEM escalation | IMA, autonomy, ESM, mesh and gateway benches | 15-day field swap; 30-day rotable return |
| LO panel and coating repair | Magellan / Avcorp / IMP | Panel bond line, reflectometry and material passport records | 24 h field structural repair; full signature restoration at depot |
| Software and mission-data support | GDC / CMC / CAE / SYSGO | Signed build pipeline, gateway regression, technique-library and mission-data update cell | Monthly patch cadence; urgent operational release process |
| Training and synthetic support | CAE Montreal | Simulator updates, courseware revision and opening-doors scenario library | Concurrent with each software block |

## 10.4 Software, Data and Consumables Support

- Software support covers the certified safety layer, behaviour tree, 50,000-scenario regression set, mesh hand-off protocol, cross-network gateway, mission recorder tools and cyber patching. Source access and build evidence are escrowed in Canada where supplier rights permit.

- Mission-data support covers emitter libraries, jammer techniques, terrain/vision databases, weapon launch-acceptability tables and Opening Doors planning models.

- Consumables support covers RAM tape, gap filler, sealants, conductive paste, filters, tires, brakes, cartridges, decoy spools, chaff/flare and Arctic servicing kits.

- Data rights objective: Crown-owned interface control, mission-data schema, material passport, maintenance records and training scenarios; supplier-owned foreground IP remains licensed for Canadian use, repair and export to approved partners.

## 10.5 Support Manpower

Table 10-4  Expected support manpower by selected fleet size

| Function | Scaling rule | 10 aircraft | 25 aircraft | 48 aircraft | 72 aircraft |
| --- | --- | --- | --- | --- | --- |
| Line maintenance | 1.5 per aircraft | 15 | 38 | 72 | 108 |
| Dedicated LO technicians, first two years | 1 per 4 aircraft | 3 | 7 | 12 | 18 |
| Engine specialists | 4 + 0.2 per aircraft | 6 | 9 | 14 | 19 |
| Avionics, EW and gateway specialists | 3 + 0.25 per aircraft | 6 | 10 | 15 | 21 |
| Weapons and release-system technicians | 2 + 0.15 per aircraft | 4 | 6 | 10 | 13 |
| Supply, QA and configuration control | 3 + 0.18 per aircraft | 5 | 8 | 12 | 16 |
| Mission planning, safety pilot and coordinators | 6 + 0.35 per aircraft | 10 | 15 | 23 | 32 |
| Field support subtotal | Formula sum | 49 | 93 | 158 | 227 |
| Depot and enterprise support | Fixed programme cadre | 45 | 45 | 45 | 45 |
| Software, training and mission-data cell | Fixed programme cadre | 18 | 18 | 18 | 18 |
| Total support manpower | Planning estimate | 112 | 156 | 221 | 290 |

The manpower model treats one Gripen crew as quarterback for two wingmen in standard packages and up to four in surge only with a supervising second crewmember, consistent with TS v6.1 §11.5. Military operator authorisations are outside this contractor-support count.

## 10.6 Sustainment Cost Estimate

The 15-year lifecycle estimate uses CAD 1.400B fixed programme support plus CAD 31M per aircraft. At the 48-aircraft reference this yields CAD 2.888B, allocated approximately as follows. The estimate excludes fuel, combat weapon expenditure, infrastructure renewal, disposal and inflation after 2026.

Table 10-5  15-year lifecycle support allocation — 48-aircraft reference

| Lifecycle line | CAD M | Content |
| --- | --- | --- |
| Support manpower and operating organisation | 930 | Line, LO, engine, weapons, mission support and programme office |
| Engine maintenance and module pipeline | 520 | M88-2 repair, float management, test-cell and OEM escalation |
| LRU repair and spares replenishment | 610 | Rotables, attrition stock, BIT support and repair pipeline |
| Software, cyber, gateway and mission data | 300 | Safety baseline, autonomy regression, Link 16 gateway and technique libraries |
| Training system and course currency | 210 | Simulator updates, instructor cadre and synthetic environment |
| LO, depot, Arctic and shop consumables | 318 | RAM panels, coatings, tires/brakes, preheat and repair materials |
| 15-year lifecycle total, 48 aircraft | 2,888 | Planning estimate; excludes weapons expenditure and disposal |

# Part XI — ITAR and Export-Control Strategy

TS v6.1 deliberately describes propulsion and mission systems in non-US-controlled terms. Procurement turns that design decision into a sourcing rule: the default bill of material must not depend on US-origin defence articles, US technical data, US manufacturing know-how or US persons for release authority. The strategy below treats export control as a configuration-control function, not as a legal afterthought.

The planning conclusion is that the baseline can be procured as an ITAR-free configuration. That conclusion remains conditional on disciplined screening of embedded software, commercial-off-the-shelf RF parts, encryption/key-management material, repair data and any substituted component during production. A single uncontrolled substitution can reclassify an otherwise clean assembly and interrupt delivery.

## 11.1 Control Classification Matrix

Table 11-1  Export-control classification matrix

| Procurement area | Default sourcing path | Principal control exposure | Release authority | Programme treatment |
| --- | --- | --- | --- | --- |
| Airframe structure and metallic allowables | Canada; France; EU alloy and recycling chain | Canadian Controlled Goods Program; EU dual-use where applicable | Canadian programme security office; supplier export-control officer | Qualify material passports and recycled-content data under Canadian controlled-goods handling; no US data package required. |
| M88-2 propulsion and hot-section modules | Safran Aircraft Engines, France; Canadian maintenance through StandardAero-class channel | French defence export approval; EU dual-use for some test equipment | French DGA-supported export process and Safran export office | Engine, modules, test data and altitude-cell support are licensed as a complete propulsion package before long-lead commitment. |
| AESA, ESM and RF geolocation | Canadian integration with European sensor and MMIC chains | EU/French/German/Swedish defence controls; semiconductor end-use screening | Supplier national authority plus Canadian import/security review | Control aperture data, calibration files and geolocation algorithms as technical data even when hardware itself is commercially classified. |
| EW, countermeasures and towed decoys | MBDA/Diehl/Leonardo/Saab/HENSOLDT/Chemring-class sources | National defence export licences; pyrotechnic and energetic transport rules | Supplier state export authority | Keep expendables and technique libraries in the same approval package as the host EW computer. |
| Weapons and launch interfaces | Meteor, SPEAR 3-class, SmartGlider Light, IRIS-T; non-US launch hardware | Missile-technology and national defence export controls; weapon safety certification | UK/France/Germany/Sweden as applicable plus Canadian acceptance | Separate weapon procurement contracts with common interface-control documents; no US-origin missile or launcher is baselined. |
| Datalinks and gateway | Canadian gateway integration; EuroMIDS-class Link 16 terminal path | Link 16 crypto/keying release, COMSEC handling, spectrum and interoperability approvals | Canadian COMSEC authority and alliance key-management process | The aircraft hosts a mesh-to-Link-16 gateway only; no MADL is procured. Crypto modules are handled through Canadian-controlled key management. |
| Autonomy, mission software and mission data | Canadian software cell with SYSGO/Kontron-class European RTOS/board support | Cyber, encryption, dual-use computing and supplier open-source licence obligations | Canadian programme authority with supplier export screening | Treat behaviour trees, safety cases, model weights, simulation scenarios and recorded mission data as controlled technical data. |
| Commercial fasteners, bearings, seals and shop consumables | Qualified Canadian distributors; EU/UK/Japan/Switzerland where required | Mostly commercial, but end-use and re-export screening still applies | Distributor certification plus receiving inspection | Use lot traceability and end-use certificates; prohibit silent substitution into US-controlled equivalents. |

## 11.2 Country and Regime Analysis

The sourcing map avoids the United States by design. It still requires approvals from Canada and from the supplier states that own the controlled technology. The practical risk is not one regulator; it is the stack of approvals needed when an aircraft contains a French engine, a multinational missile, European RF hardware, Canadian software and alliance keying material.

Table 11-2  Jurisdiction and approval analysis

| Jurisdiction | Relevant regime | Expected Striker involvement | Lead-time planning allowance | Primary mitigation |
| --- | --- | --- | --- | --- |
| Canada | Controlled Goods Program, Contract Security Program, Export and Import Permits Act where re-export applies | Design authority, final assembly, software cell, depot, in-service support and any re-export to an allied operator | Registration before controlled data transfer; facility clearance before production data receipt | Stand up the Canadian controlled-goods enclave before receipt of supplier technical data; segregate Canadian, supplier-state and alliance data. |
| France | French defence export approval and EU dual-use rules | M88-2 engine, engine modules, selected sensors, mission-system components and recycled titanium/alloy chain | 9–15 months for complete propulsion licence package | Bundle engine, spares, test equipment, technical data and training in one approval request; avoid piecemeal amendments. |
| United Kingdom | UK defence export licensing | Meteor participation, SPEAR 3-class integration data, selected RF or mission-system inputs | 6–12 months after interface freeze | Freeze bay interface and separation cases early; keep UK data in a dedicated project enclave. |
| Germany | German defence export controls and EU rules | IRIS-T, Diehl-class EW or self-protection items, selected sensors and actuators | 6–12 months after store configuration freeze | Use German-approved technical data packages and prohibit unapproved local modification of store-management software. |
| Sweden | Swedish defence export controls | Saab-class EW/mission-system options and Gripen interoperability practices | 4–9 months for data and support approvals | Reuse mature Gripen-adjacent support concepts without importing US-controlled data. |
| Italy/EU | Italian national controls and EU dual-use/export rules | Leonardo-class sensors/EW, selected avionics and EU research supply chain | 4–10 months depending on item | Classify each LRU at part-number level and maintain an EU dual-use annex for test equipment. |
| Alliance key management | Link 16 crypto/keying and COMSEC processes | Gateway terminal, key loading, interoperability test and network participation | Approval path begins before terminal purchase; key material is never a commercial line item | Procure terminals through approved alliance channels; separate hardware delivery from crypto release and network design approval. |

## 11.3 Canadian Controlled-Goods and Security Implementation

- Register the prime integrator, Mirabel final-assembly site, engine-support site, avionics repair sites and software cell under the Controlled Goods Program before controlled technical data is received.

- Use a single programme data-rights index that tags every drawing, model, test result, software repository, failure report and mission-data file by owner, control regime, releasability and storage location.

- Apply Contract Security Program personnel and facility screening to design, final assembly, depot, training-device and software-sustainment organisations. Subcontractors inherit the same flow-downs.

- Keep supplier-state data in logically separate enclaves. French propulsion data, UK weapon data, German store data, Swedish support data, alliance keying material and Canadian operational data must not be merged merely because the same aircraft uses them.

- Use a release gate for every technical-data transfer outside Canada. The gate confirms classification, end user, end use, licence scope, data sanitisation and record retention before transmission.

- Maintain a no-US-person rule for controlled design and production data unless a specific licence or exemption is granted. Commercial logistics staff may handle uncontrolled hardware only after screening confirms that no controlled technical data is exposed.

## 11.4 No-ITAR Recurring BOM Claim and Boundaries

The recurring BOM claim is limited and precise: the production air vehicle, baseline weapons listed in Part III, GSE, training equipment and sustainment pipeline are planned without US-origin defence articles or US-controlled technical data. The claim does not assert that every commercial raw material, machine tool, cloud service, test instrument or financial service is free of US content. It asserts that no US export licence, US technical-assistance agreement or US manufacturing licence is required to build, field or sustain the defined Striker configuration.

Table 11-3  No-ITAR claim boundaries

| Included in claim | Excluded from claim | Required evidence |
| --- | --- | --- |
| Air vehicle part numbers in Categories A–L as baselined in Part II | General-purpose factory machinery and uncontrolled commercial IT infrastructure | Part-number-level control classification and supplier declaration |
| M88-2 engine, modules, float engines, test-cell support and engine technical data | Any future US engine alternate or US-controlled engine accessory | French licence scope and Safran export-control confirmation |
| Baseline Meteor, SPEAR 3-class, SmartGlider Light, IRIS-T and allied expendables | Any future US-origin weapon, launcher, fuze, seeker or data-link module | Weapon contract schedules and interface documents marked by supplier state |
| Mesh radio, Striker-hosted gateway and EuroMIDS-class terminal path | Crypto/key material itself, which is released through alliance COMSEC rather than ordinary export sale | COMSEC account, network design approval and keying plan |
| Canadian software, mission-data and training baseline | Operational intelligence products and national mission data belonging to the customer | Configuration item list and software bill of materials |

## 11.5 Substitution and Waiver Control

Any substitution that introduces US origin, US technical data, US manufacturing know-how or a US-person release dependency is a Class I configuration change. It is not approved by engineering convenience. The waiver package must identify the operational need, non-US alternatives considered, cost and schedule effect, affected part numbers, export-control classification, data-flow map, security impact, reversibility and approval authority. Approval requires the programme manager, chief engineer, security authority, export-control officer and customer representative.

Table 11-4  Substitution screening gates

| Gate | Question | Evidence | Disposition |
| --- | --- | --- | --- |
| G1 — origin screen | Is the item, software, data or service US-origin or US-controlled? | Supplier certificate, ECCN/USML-equivalent statement, country-of-origin and data-rights declaration | Clean items proceed; uncertain items held. |
| G2 — technical-data screen | Will installation, test, repair or integration expose US-controlled technical data? | Data-flow map, work instructions, repair manual review and software dependency scan | Controlled exposure requires redesign or licence. |
| G3 — sustainment screen | Can Canada sustain the item without US-person release authority? | Depot plan, spares path, OEM repair terms and update mechanism | No uncontrolled US sustainment dependency is accepted. |
| G4 — configuration screen | Does the substitution change signature, safety, weapons separation, cyber or interoperability? | Delta qualification, safety case and regression evidence | Class I change board approval required. |
| G5 — waiver record | Is a waiver still proposed? | Cost/schedule/operational rationale and approval signatures | Waiver logged, tracked and reviewed at each baseline audit. |

## 11.6 Licence Workflow and Data-Release Gates

Table 11-5  Export-control workflow

| Step | Owner | Action | Output |
| --- | --- | --- | --- |
| 1 | Procurement | Assign control classification and sourcing state to every requirement before solicitation release. | Controlled requirements register |
| 2 | Export-control office | Screen supplier, item, data, software, service and end-use path. | Classification memorandum |
| 3 | Security authority | Confirm facility, personnel, network and COMSEC readiness. | Security readiness certificate |
| 4 | Engineering | Freeze interface-control data and identify technical-data package needed for licence. | Licence data package |
| 5 | Supplier state | Review and issue export authorisation or conditions. | Licence/approval record |
| 6 | Programme configuration board | Verify that approval scope matches contracted configuration. | Release-to-contract certificate |
| 7 | Receiving and configuration control | Check delivered hardware, software and data against approved scope. | Receipt and releasability record |
| 8 | In-service support | Re-screen repairs, software updates, mission-data changes and vendor substitutions. | Continuing-compliance file |

The export-control file is a deliverable at every major review: system requirements review, preliminary design review, critical design review, first-article readiness, production-readiness review, initial operational capability and each annual sustainment audit. Failure to keep the file current is a stop-ship condition for controlled data and controlled hardware.

# Part XII — Industrial and Canadian Workshare Plan

The industrial plan is built around a Canadian prime integrator, Mirabel-class final assembly, Canadian component manufacture where capacity exists, and non-US allied supply only where Canada cannot field the capability in the required time. The plan is deliberately practical: it does not pretend that Canada will manufacture the M88-2 hot section, a Meteor motor or an alliance crypto module. It concentrates Canadian content where it creates sovereign control, industrial value and sustainment resilience.

The recurring-cost workshare model prices Canadian content at CAD 12.4185M of the CAD 24.30M reference unit, or 51.1% at first article. The rate-production objective is 60% Canadian content by value, with sustainment labour at or above 70% Canadian once the depot and software cells reach steady state.

## 12.1 Prime and Integrator Structure

Table 12-1  Programme organisation and workshare allocation

| Role | Planned Canadian lead | Scope | Industrial benefit |
| --- | --- | --- | --- |
| Prime contractor and air-vehicle integrator | Bombardier Aerostructures, Mirabel, QC, with a programme-specific Canadian integration company | System engineering, air-vehicle integration, final assembly, acceptance, configuration control and customer delivery | Creates Canadian design authority for integration, change control and fleet upgrades. |
| Mission-system and software integrator | General Dynamics Mission Systems–Canada with CMC Electronics, MDA and Thales Canada participation | Mission computer integration, mesh/gateway, geolocation processing, cyber, ground mission planning and training data | Builds a Canadian mission-software and interoperability base. |
| Training-system integrator | CAE, Montréal, QC | Full-mission simulation, part-task trainers, courseware, synthetic threat environment and training-device support | Anchors long-term training revenue and course-currency work in Canada. |
| Depot and in-service support lead | IMP Aerospace & Defence with Cascade Aerospace and StandardAero participation | Depot induction, structural/LO repair, engine-channel management, component repair and fleet technical support | Retains high-value sustainment work and surge capacity in Canada. |
| Propulsion OEM partner | Safran Aircraft Engines, France | M88-2 supply, modules, overhaul standards, test-cell acceptance and engineering escalation | Provides the non-US propulsion baseline while enabling Canadian module management. |

## 12.2 Canadian Assembly and Component Manufacture

Table 12-2  Canadian manufacturing participation by Category

| Category | Canadian candidate workshare | Candidate companies | Rate-production objective |
| --- | --- | --- | --- |
| A — Airframe structure | Composite shells, bonded assemblies, chine structures, bay doors, final assembly tooling and airframe test | Bombardier Aerostructures; Avcorp; Magellan Aerospace; Cyclone Manufacturing; Shimco | 90% of category value in Canada |
| B — Materials and shop consumables | Fastener kitting, sheet/plate distribution, sealants, adhesives, shop consumables and material-passport handling | Qualified Canadian distributors; Magellan; Shimco; EcoTitanium/Constellium material chain for upstream alloy | 75% of category value managed or manufactured in Canada |
| C — Propulsion and fuel system | Fuel-system integration, external fuel hardware, ground test support, module management and selected engine externals | StandardAero; IMP; Magellan; Safran OEM for core engine | 15% initial category value, rising through MRO and module management |
| D — Landing gear and brakes | Gear integration, actuation, wheels/brakes support and overhaul | Héroux-Devtek; Magellan; IMP | 90% of category value |
| E — Avionics and sensors | Mission computers, displays/control interfaces, navigation, RF distribution, test and integration | CMC Electronics; MDA; General Dynamics Mission Systems–Canada; Thales Canada; HENSOLDT/Leonardo/Safran sensor OEMs | 45% initial, rising with software and test work |
| F — Signature materials | RAM panel finishing, gap treatment, coatings application, inspection and repair | Magellan; Avcorp; IMP; Canadian coatings suppliers | 70% of recurring application and repair value |
| G — EW and self-protection | EW integration, antenna installation, decoy loading systems, test and technique-data production | MDA; General Dynamics Mission Systems–Canada; CMC; Thales Canada; EW OEM data licences | 40% initial, with Canadian technique-data growth |
| H — Bay and launch interface | Bay mechanisms, rails, ejectors, harnesses, separation-test rigs and weapons integration support | Magellan; Héroux-Devtek; Avcorp; Cyclone; MBDA/Diehl interface licences | 75% of category value |
| I — Communications and datalinks | Mesh integration, gateway, antennas, ground support and network test | General Dynamics Mission Systems–Canada; CMC; MDA; EuroMIDS terminal channel | 65% of category value |
| J — Electrical power | Power distribution, harnesses, battery/charger support, generator control integration and test | CMC; Magellan; Canadian electrical distributors; Safran/Thales components | 75% of category value |
| K — Flight controls and actuation | Actuator installation, control-surface support, rigging, test stands and overhaul | Héroux-Devtek; Magellan; IMP; Saab/Liebherr-class OEM data | 80% of category value |
| L — Thermal management | Ducting, heat-exchanger installation, environmental-control integration and Arctic preheat support | Magellan; Avcorp; IMP; Canadian thermal distributors | 85% of category value |

## 12.3 Domestic-Content Objectives

Table 12-3  Domestic-content ladder

| Stage | Aircraft/production state | Canadian content objective | Measurement |
| --- | --- | --- | --- |
| First article | First 4 aircraft | 51.1% by recurring value | Category A–L priced BOM with supplier-origin codes and audited invoices |
| Early rate production | Aircraft 5–24 | 55% by recurring value | Quarterly BOM audit plus local value-added certification |
| Rate production | Aircraft 25 onward | 60% by recurring value | Annual content audit and corrective plan for every category below target |
| Sustainment steady state | After initial two-year LO-intensive period | ≥70% of support labour in Canada | Labour-hour recording by site, trade, nationality of facility and supplier invoice |
| Upgrade programmes | Block upgrades and obsolescence projects | Canadian design authority preferred | Change-board approval requires Canadian-content and sovereign-support assessment |

## 12.4 Technology-Transfer Assumptions

- Safran transfers sufficient M88-2 maintenance, module-management, test-cell and technical-publication capability for Canada to run the fleet pool and perform approved depot tasks; hot-section manufacture remains French.

- Weapon OEMs transfer interface-control, separation, safety, mission-planning and launch-acceptability data needed for Canadian integration; seeker, motor and warhead manufacture remain supplier-state work.

- Sensor and EW OEMs license test, calibration, technique-library and maintenance data to Canadian repair centres; classified design algorithms remain supplier-controlled where licences require.

- Canadian firms receive manufacturing data for composite shells, bays, doors, chine fittings, harnesses, power-distribution assemblies, GSE and training devices where Canada is the selected source.

- Software transfer covers build tools, interface specifications, regression environments, safety-case artefacts and mission-data production; no assumption is made that supplier proprietary source code is transferred unless separately priced.

- All transfer packages include Canadian training, data-rights schedules, export-control markings and a defined obsolescence path. Technology transfer that cannot be used by a cleared Canadian facility is not counted as industrial benefit.

## 12.5 Potential Participating Companies

The following list is a sourcing and outreach set, not a commitment. Participation is conditional on capability, security clearance, export-control status, price, delivery and quality.

Table 12-4  Potential Canadian participants

| Company | Planned participation | Industrial benefit pathway |
| --- | --- | --- |
| Bombardier Aerostructures | BOM | Large composite shells, co-cured structures, final-assembly-scale facilities |
| Avcorp Industries | AVC | Composite structures, bonded assemblies, secondary structure |
| Magellan Aerospace | MAG | Composite and metallic aerostructures, machined assemblies, engine-adjacent structures |
| Héroux-Devtek | HER | Landing gear, actuation, gear machining and aftermarket support |
| Cyclone Manufacturing | CYC | Five-axis titanium and aluminium machining, fittings and housings |
| Shimco | SHI | Precision shims, washers, spacers and small flight hardware |
| CMC Electronics | CMC | Military avionics, GNSS anti-jam, mission computers and integration |
| MDA | MDA | Conformal antennas, RF structures, satellite and timing assemblies |
| General Dynamics Mission Systems–Canada | GDC | Secure communications, crypto integration, Link 16 systems and cross-domain guards |
| Thales Canada | THC | Canadian avionics, mission systems, training support and secure integration |
| Wescam | WES | MX-class EO/IR turrets; Canadian manufacturing and support |
| CAE | CAE | Training systems, constructive simulation and synthetic environments |
| IMP Aerospace and Defence | IMP | Depot-level MRO, structural repair and avionics lines |
| Cascade Aerospace | CAS | Field-level MRO, western support node and component repair |
| StandardAero | STD | Canadian engine MRO partner under Safran licence and data agreement |

## 12.6 Industrial and Technological Benefits

Table 12-5  Industrial-benefit commitments to be priced in final contracts

| Benefit area | Commitment | Verification |
| --- | --- | --- |
| High-value work in Canada | Final assembly, mission-system integration, training-system development, depot activation and software sustainment performed in Canada | Contract work breakdown structure and audited place-of-performance records |
| Supplier development | Qualify at least two Canadian sources for each producible commodity where volume supports it | Approved supplier list and qualification reports |
| Skills and workforce | Create apprenticeship, composite, avionics, LO repair, engine-module and software-sustainment training paths tied to the manpower model in Part X | Training records and annual workforce report |
| Technology insertion | Fund Canadian upgrades to mesh networking, geolocation processing, synthetic training and depot diagnostics | Upgrade project register and IP/data-rights schedule |
| Regional participation | Distribute work across Québec, Ontario and Atlantic/Western Canadian support sites where capability exists | Subcontract placement and regional value report |
| Allied market access | Use Canadian-built structure, training and support packages in allied export campaigns where supplier-state approvals permit | Export-campaign workshare annexes |

The industrial plan is treated as a contract deliverable with remedies. If a supplier misses a Canadian-content objective, the programme first requires a corrective sourcing plan; persistent shortfalls affect progress payments, future work allocation and supplier eligibility for upgrades.

# Part XIII — Schedule and Long-Lead Procurement Plan

The schedule is expressed in programme months because contract award, budget release and export-approval dates are not yet fixed. The pacing items are the M88-2 engine and modules, multinational weapons, AESA/ESM apertures, Link 16 gateway approvals, signature-material qualification and training-system software. The plan assumes a 48-aircraft reference buy but can be re-baselined to any fleet quantity in Part IX.

## 13.1 Programme Milestones

Table 13-1  Schedule baseline

| Month | Milestone | Required exit evidence |
| --- | --- | --- |
| M0 | Programme authority to proceed and controlled-goods implementation start | Funding release; programme management plan; supplier-state engagement plan |
| M3 | Requirements and data-rights baseline | TS v6.1 trace matrix; export-control register; supplier declaration template |
| M6 | Long-lead requests for proposal released | Engine, weapons, AESA/ESM, gateway, signature material and training RFPs issued |
| M9 | Export-licence packages submitted | Complete propulsion, weapon, RF, gateway, training and depot data packages delivered to supplier states |
| M12 | Long-lead contract placement | M88-2, modules, weapons interfaces, AESA/ESM and gateway terminal contracts signed |
| M15 | Critical design review | Configuration frozen for bay, chine rail, gateway, signature panels, engine installation and Arctic kit |
| M18 | Shared M88-2 pool agreement | Sprinter/Striker pool, 15% float, module ownership and repair-pipeline rules signed |
| M21 | First major structures delivered to Mirabel | Composite shells, chines, bays, landing gear and harnesses received with material passports |
| M24 | First aircraft final assembly start | Production-readiness review; controlled-goods enclave; tooling and first-article inspection active |
| M30 | First engine installation and ground runs | French licence conditions verified; engine acceptance and test-cell records complete |
| M33 | First flight | Flight clearance, telemetry, chase, safety case and emergency procedures approved |
| M36–M48 | Flight and mission-system test | Envelope, signature, bay separation, mesh hand-off, gateway, EW, Arctic and turnaround demonstrations |
| M48 | Production-readiness decision | Category cost audit; supplier quality rating; no-ITAR BOM audit; training and depot activation status |
| M54 | Initial operational capability | 8 aircraft, trained crews, support manpower, spares pool, gateway approval and weapons-release envelope |
| M60–M84 | Rate deliveries and fleet growth | Delivery rate adjusted to selected quantity; sustainment metrics meet 2.0/2.4 sortie targets |

## 13.2 Long-Lead Items

Table 13-2  Long-lead procurement register

| Item | Planned lead time | Order no later than | Reason |
| --- | --- | --- | --- |
| M88-2 engines and initial modules | 24–30 months | M12 | Single-engine configuration, shared Sprinter pool and 15% float require early OEM slotting. |
| AESA aperture shipsets and RF calibration equipment | 18–24 months | M12 | 480-element GaN array, calibration files and ESM timing performance drive acceptance. |
| Gateway terminals and COMSEC support path | 18–30 months | M9–M12 | Terminal hardware, alliance network design and keying approval run on separate clocks. |
| Meteor/SPEAR-class weapons and interface data | 24–36 months | M12 | Weapon production and separation-data approvals must align with bay freeze. |
| Composite autoclave/bond tooling and first-article panels | 12–18 months | M15 | Mirabel final assembly cannot start without qualified tooling and inspection fixtures. |
| Signature panels, coatings and repair kits | 12–18 months | M15 | 46-panel shipset, repair stock and LO upkeep target require qualified process control. |
| Full-mission simulator and synthetic environment | 18–24 months | M15 | Training-system software must track flight-test configuration and mission-data drops. |
| Depot test benches and M88-2 module tooling | 15–21 months | M18 | Depot activation and 30-day repair pipeline require equipment before first heavy maintenance. |

## 13.3 Delivery and Rate Planning

The reference plan reaches eight aircraft by initial operational capability and then sustains approximately one aircraft per month during early rate production, with a two-aircraft monthly peak only after composite, propulsion, mission-system and signature acceptance metrics are stable. A 72-aircraft programme therefore runs beyond the 48-aircraft reference schedule; procurement should extend rate tooling, spares and supplier capacity rather than compress acceptance testing.

# Part XIV — Procurement Risk, Quality and Compliance

## 14.1 Top Programme Risks

Table 14-1  Risk register

| Risk | Probability | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Export approval arrives late or with restrictive conditions | Medium | High | Submit complete packages by M9; maintain European alternate sources; prohibit US substitution without waiver | Export-control officer |
| M88-2 pool conflict with Sprinter demand | Medium | High | Binding shared-pool agreement by M18; 15% float; quarterly pool board | Propulsion manager |
| Composite rate or recycled-content allowables fail qualification | Medium | High | Material passports, coupon allowables, dual-source prepreg/resin path and first-article inspection | Structures lead |
| AESA/ESM geolocation misses timing or calibration targets | Medium | High | Early chamber testing, six-aperture calibration rig, supplier factory acceptance and margin tracking | Mission-systems lead |
| Weapon separation or launch-acceptability data delayed | Medium | High | Freeze bay and store interface at M15; contract OEM support through flight clearance | Weapons lead |
| Gateway/Link 16 network approval slips | Medium | High | Separate terminal delivery from crypto release; begin alliance process before terminal purchase | Communications lead |
| Signature upkeep exceeds ≤12% maintenance-hour target | Medium | Medium | 46-panel repair stock, one LO technician per four aircraft initially, field repair kits and process audit | Sustainment lead |
| Canadian content objective is not met | Medium | Medium | Category workshare targets, audited invoices, corrective sourcing and industrial-benefit remedies | Industrial benefits lead |
| Cost growth in mission systems or propulsion | Medium | High | 10% contingency, category control accounts, option pricing and annual re-estimate | Cost control lead |
| Arctic support underestimated | Low | Medium | Preheat, battery, lubricant, shelter and consumables kit verified in −40 °C test | Operations lead |

## 14.2 Quality Standards and Verification

- Aerospace quality flow-down: suppliers operate under AS9100/ISO 9001-equivalent quality systems; special processes use approved sources and controlled travellers.

- Configuration control: TS v6.1 is the controlling baseline. Every Category A–L part, software item, GSE item and training item carries a trace code to the applicable v6.1 paragraph.

- Material traceability: metallic, composite, recycled-content and signature materials carry lot, batch, process, inspection and recycled-content records.

- Flight safety: software, autonomy, release systems and engine integration use independent verification, hazard tracking and regression evidence before flight clearance.

- Cyber and COMSEC: mission software, gateway, recorder tools and maintenance laptops use controlled accounts, signed builds, vulnerability management and key-control procedures.

- Acceptance: each aircraft passes dimensional, signature, weight, engine, mission-system, datalink, bay, EW, brake/gear and ground-run acceptance before delivery.

## 14.3 Traceability and Records

The programme record set includes the immutable compilation matrix, TS v6.1 trace register, supplier declarations, export-control classifications, licences, material passports, first-article inspections, acceptance records, concession log, software bill of materials, mission-data version record, support-metric dashboard and annual Canadian-content audit. The record set is retained in the Canadian programme data vault with supplier-state enclaves preserved.

# Part XV — Appendices and Procurement Reference Tables

## Appendix A — Cost Formulas

Table A-1  Fleet-economic formulas

| Line | Formula | Meaning |
| --- | --- | --- |
| Recurring unit cost | U(N) = 24.30 × (N / 48)^b; b = ln(0.92) / ln(2) | 92% learning curve from 48-aircraft reference, CAD M |
| Aircraft procurement | A(N) = N × U(N) | Recurring flyaway cost, CAD M |
| Initial spares/support | S(N) = 68 + 3.0N | Fixed pool activation plus per-aircraft pool, CAD M |
| Core programme | C(N) = A(N) + 2,380 + S(N) | Aircraft + NRE + initial spares/support, CAD M |
| Initial effects | W(N) = 9.18N | Baseline weapon/effects package, CAD M |
| Infrastructure | I(N) = 150 + 0.55N | Facilities and ground infrastructure, CAD M |
| Contingency | R(N) = 0.10 × [C(N)+W(N)+I(N)] | Programme contingency, CAD M |
| Total acquisition | T(N) = 1.10 × [C(N)+W(N)+I(N)] | Acquisition including contingency, CAD M |
| Lifecycle estimate | L(N) = 1,400 + 31N | 15-year sustainment planning estimate, CAD M |

## Appendix B — Supplier Directory

Table B-1  Supplier directory and outreach pathway

| Code | Supplier and location | Reference | Planned scope |
| --- | --- | --- | --- |
| BOM | Bombardier Aerostructures, Mirabel, QC (Canada) | bombardier.com | Large composite shells, co-cured structures, final-assembly-scale facilities |
| AVC | Avcorp Industries, Delta, BC (Canada) | avcorp.com | Composite structures, bonded assemblies, secondary structure |
| MAG | Magellan Aerospace, Winnipeg, MB / Mississauga, ON (Canada) | magellan-aerospace.com | Composite and metallic aerostructures, machined assemblies, engine-adjacent structures |
| HER | Héroux-Devtek, Longueuil, QC (Canada) | herouxdevtek.com | Landing gear, actuation, gear machining and aftermarket support |
| CYC | Cyclone Manufacturing, Mississauga, ON (Canada) | cyclonemfg.com | Five-axis titanium and aluminium machining, fittings and housings |
| SHI | Shimco, Markham, ON (Canada) | shimco.com | Precision shims, washers, spacers and small flight hardware |
| CMC | CMC Electronics, Montreal, QC (Canada) | cmcelectronics.ca | Military avionics, GNSS anti-jam, mission computers and integration |
| MDA | MDA, Brampton, ON (Canada) | mda.space | Conformal antennas, RF structures, satellite and timing assemblies |
| GDC | General Dynamics Mission Systems–Canada, Ottawa, ON (Canada) | gd-ms.ca | Secure communications, crypto integration, Link 16 systems and cross-domain guards |
| THC | Thales Canada, Montreal, QC / Toronto, ON (Canada) | thalesgroup.com/canada | Canadian avionics, mission systems, training support and secure integration |
| WES | Wescam, Burlington, ON (Canada) | wescam.com | MX-class EO/IR turrets; Canadian manufacturing and support |
| CAE | CAE, Montreal, QC (Canada) | cae.com | Training systems, constructive simulation and synthetic environments |
| IMP | IMP Aerospace and Defence, Halifax, NS (Canada) | impaerospace.com | Depot-level MRO, structural repair and avionics lines |
| CAS | Cascade Aerospace, Abbotsford, BC (Canada) | cascadeaerospace.com | Field-level MRO, western support node and component repair |
| STD | StandardAero, Winnipeg, MB (Canada) | standardaero.com | Canadian engine MRO partner under Safran licence and data agreement |
| QDT | Qualified distributor channel, Canada / allied stocking sites | AS9120-registered distributors | Traceable standard hardware, connectors, seals, adhesives and consumables |
| SAF | Safran Aircraft Engines, Paris / Villaroche (France) | safran-group.com | M88-2 engine, FADEC, modules, technical data and OEM support |
| SED | Safran Electronics & Defense, France | safran-group.com | Inertial navigation, timing, clocks and avionics support |
| ECO | EcoTitanium, Saint-Georges-de-Mons (France) | ecotitanium.com | Closed-loop recycled titanium ingot and certified remelt |
| CON | Constellium, France (allied operations) | constellium.com | Aerospace aluminium plate and closed-loop aluminium routes |
| TAR | Tarmac Aerosave, France / Spain | tarmacaerosave.com | Aircraft recycling, controlled scrap streams and material passports |
| MBD | MBDA, France / United Kingdom / Italy / Germany | mbda-systems.com | Meteor, SPEAR 3-class and SmartGlider-class weapons and integration data |
| DIE | Diehl Defence, Überlingen (Germany) | diehl.com/defence | IRIS-T weapons, launcher interfaces and support |
| LEO | Leonardo, Italy / United Kingdom | leonardo.com | AESA candidate, ESM, electronic attack and self-protection systems |
| SAA | Saab, Linköping (Sweden) / Saab Canada, Ottawa | saab.com | Gripen E interface, AESA candidate and tactical-network integration |
| HEN | HENSOLDT, Germany | hensoldt.net | ESM, EW receivers, sensor processing and spectrum systems |
| THF | Thales, France | thalesgroup.com | Mission computing, communications and avionics equipment |
| SYS | SYSGO, Germany | sysgo.com | PikeOS partitioning operating system and certification evidence |
| KON | Kontron, Austria / Germany | kontron.com | Rugged non-US-controlled compute modules and avionics integration |
| AIR | Airbus Defence and Space, France / Germany / Spain | airbus.com | Secure networking, C2 integration and coalition gateway support |
| CHE | Chemring Countermeasures, United Kingdom | chemring.com | Allied chaff, flare and expendable countermeasure supply |
| EUM | EuroMIDS consortium, France / Germany / Italy / Spain | euromids.com | Link 16 terminal supply through European consortium channels |

## Appendix C — Standards and Compliance Reference

Table C-1  Standards and compliance set

| Area | Reference family | Procurement application |
| --- | --- | --- |
| Quality management | AS9100 / ISO 9001-equivalent aerospace quality systems | Supplier qualification, production and repair |
| Airworthiness and safety | National military airworthiness authority process; safety-case and hazard-log practice | Flight clearance and continuing airworthiness |
| Software | Safety-critical software assurance, signed builds, independent verification and configuration control | Autonomy, mission systems, gateway and training |
| Cyber | Canadian protected/controlled network practice and supplier-state conditions | Mission data, maintenance laptops, software vault and gateway |
| Export/security | Canadian Controlled Goods Program, Contract Security Program, supplier-state export approvals and alliance COMSEC | All controlled technical data and hardware |
| Environment and materials | Material passports, recycled-content tracking, hazardous-material controls and waste handling | Category B/F materials and depot operations |
| Training | Canadian training-system acceptance and course-currency control | CAE-led devices, courseware and synthetic environment |

## Appendix D — Assumptions and Exclusions

- All values are 2026 CAD rough-order planning estimates, not vendor quotations.

- The United States is excluded as a sourcing path for controlled articles. Any exception requires the waiver process in Part XI.

- Fuel, combat weapon expenditure, munitions storage construction beyond the stated infrastructure allowance, personnel pay, base operations, inflation after 2026, disposal and allied deployment costs are excluded.

- Crypto/key material is treated as an alliance release process, not a commercial price line.

- The 48-aircraft reference is an economic anchor; the 17 requested fleet sizes range from 10 to 72 aircraft and include neither a 48-row requirement nor any special status for that quantity in the final comparison table.

- All technical requirements trace to TS v6.1. Where procurement planning converts a requirement into a quantity, labour estimate or cost, the conversion is stated as an assumption.

## Appendix E — Compilation Certification

This package was compiled under the immutable matrix rules: no obsolete v5.0 baseline data, no USD pricing, no US-controlled default sourcing, no unsupported technical claims, no silent category mismatch, no orphaned cost line, no missing fleet scenario and no final summary that omits a requested decision column. The document remains preliminary planning data until contracts, export approvals, security clearances and customer airworthiness direction are issued.

# Part XVI — Procurement Decision Summary

The decision table below is the acquisition baseline for the requested fleet comparison. Values are 2026 CAD millions. “Recurring aircraft” is quantity multiplied by estimated recurring unit cost; “initial support” is the initial spares/support line; “weapons” is the standard initial effects package; “lifecycle” is the 15-year sustainment planning estimate and is not included in total acquisition. The 48-aircraft recurring unit anchor is CAD 24.30M; it is used to calculate the 92% learning curve but is not one of the requested comparison rows.

Decision rule: quantities at or above 38 aircraft materially reduce recurring unit cost and spread NRE efficiently; quantities below 28 aircraft carry a materially higher unit burden and should be treated as a minimum-capability decision rather than an economic optimum. A 48–60 aircraft buy is the planning sweet spot for unit cost, fleet utility and support scale.

Reference anchor — 48-aircraft economics (2026 CAD M)

| Line | CAD M |
| --- | --- |
| Estimated recurring unit cost | 24.300 |
| Recurring aircraft procurement | 1,166.4 |
| Allocated non-recurring programme cost | 2,380.0 |
| Initial spares/support | 212.0 |
| Initial effects/weapons package | 440.6 |
| Infrastructure | 176.4 |
| Contingency | 437.5 |
| Total acquisition | 4,813.0 |
| 15-year lifecycle estimate | 2,888.0 |

Table 16-1  Final procurement decision comparison — 2026 CAD M

| Qty | Unit | Recurring aircraft | NRE | Initial support | Weapons | Infrastructure | Contingency | Total acquisition | 15-year lifecycle |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 10 | 29.346 | 293.5 | 2,380.0 | 98.0 | 91.8 | 155.5 | 301.9 | 3,320.6 | 1,710.0 |
| 15 | 27.949 | 419.2 | 2,380.0 | 113.0 | 137.7 | 158.2 | 320.8 | 3,529.0 | 1,865.0 |
| 20 | 26.999 | 540.0 | 2,380.0 | 128.0 | 183.6 | 161.0 | 339.3 | 3,731.8 | 2,020.0 |
| 25 | 26.284 | 657.1 | 2,380.0 | 143.0 | 229.5 | 163.8 | 357.3 | 3,930.7 | 2,175.0 |
| 28 | 25.928 | 726.0 | 2,380.0 | 152.0 | 257.0 | 165.4 | 368.0 | 4,048.5 | 2,268.0 |
| 30 | 25.713 | 771.4 | 2,380.0 | 158.0 | 275.4 | 166.5 | 375.1 | 4,126.4 | 2,330.0 |
| 35 | 25.241 | 883.4 | 2,380.0 | 173.0 | 321.3 | 169.2 | 392.7 | 4,319.7 | 2,485.0 |
| 38 | 24.993 | 949.7 | 2,380.0 | 182.0 | 348.8 | 170.9 | 403.1 | 4,434.6 | 2,578.0 |
| 40 | 24.839 | 993.6 | 2,380.0 | 188.0 | 367.2 | 172.0 | 410.1 | 4,510.8 | 2,640.0 |
| 45 | 24.489 | 1,102.0 | 2,380.0 | 203.0 | 413.1 | 174.8 | 427.3 | 4,700.2 | 2,795.0 |
| 50 | 24.181 | 1,209.0 | 2,380.0 | 218.0 | 459.0 | 177.5 | 444.4 | 4,887.9 | 2,950.0 |
| 55 | 23.905 | 1,314.8 | 2,380.0 | 233.0 | 504.9 | 180.2 | 461.3 | 5,074.2 | 3,105.0 |
| 58 | 23.753 | 1,377.7 | 2,380.0 | 242.0 | 532.4 | 181.9 | 471.4 | 5,185.4 | 3,198.0 |
| 60 | 23.656 | 1,419.4 | 2,380.0 | 248.0 | 550.8 | 183.0 | 478.1 | 5,259.3 | 3,260.0 |
| 65 | 23.430 | 1,522.9 | 2,380.0 | 263.0 | 596.7 | 185.8 | 494.8 | 5,443.2 | 3,415.0 |
| 70 | 23.222 | 1,625.5 | 2,380.0 | 278.0 | 642.6 | 188.5 | 511.5 | 5,626.1 | 3,570.0 |
| 72 | 23.143 | 1,666.3 | 2,380.0 | 284.0 | 661.0 | 189.6 | 518.1 | 5,699.0 | 3,632.0 |