MundusLux-300

Construction Package

Engineering Design Basis | Version 5.3

Site: 53°42'52.23"N 57°00'55.21"W (Cartwright, Newfoundland) | Zero-Carbon | Off-Grid | Winterized

Design Maturity: 72% (v6.0-NL) | Newfoundland Cold-Climate Adaptation

Engineering Confidential | August 2026

# Table of Contents

Volume 5: Site Relocation & Cold-Climate Adaptation (Newfoundland)

Volume 6: Design Basis Memorandum

Volume 7: Process Design

Volume 8: Instrumentation & Control Systems

Volume 9: Safety Engineering — HAZOP Study

Volume 10: Structural & Electrical Engineering

Volume 11: Dynamic Operating Model

Volume 12: Capital Cost, Commissioning & Operations

Volume 13: Risk Analysis & Independent Review

Volume 14: Pilot-Scale Validation Plan

Volume 15: Technology Readiness Assessment

Volume 16: Community Engagement Plan

Volume 17: Financing & Ownership Structure

Volume 18: Thermal Resilience & Cascade Protection

Volume 19: Value Engineering & Cost Optimization

Volume 20: Zero-Carbon Thermal Strategy

Volume 21: Grid-Supportive Operations

Volume 22: Novel Electrochemical Energy Systems

Volume 23: Winter Operations Protocol

Volume 24: Newfoundland Economic Model

Appendices A–D

Volume 25: 30 Engineering Improvements for Cold-Climate Cost Savings & Efficiency

Annex A: Zero Computing Load Contingency

# Strategic Recommendations: Buffering the $4.71 Million Deficit

To buffer against the potential $4.71 million deficit without relying on insurance, the following 10 recommended changes have been drawn from this document. These strategies transform the facility into a more resilient, diversified asset that can operate profitably even if its primary computing revenue is lost.

## Structural & Operational Improvements (4 Changes)

These changes involve re-engineering the facility's physical systems to reduce costs and increase resilience.

Maintain the "Zero-Carbon Thermal Strategy" (Volume 20): This is a foundational change. By replacing the natural gas booster heater with solar thermal, an enhanced PCM buffer, and an MVC electric compressor, the facility saves approximately $2.46 million annually in avoided gas costs and maintenance. This is the single biggest contributor to reducing the deficit.

Fully Integrate "Salt-to-Power" Systems (Volumes 21 & 22): These systems turn the waste brine stream into revenue. By implementing the SGE + MCDI system and the saltwater flow battery, the facility can generate over $240,000 per year in new revenue from grid services and electricity sales while also reducing its own energy costs.

Note — Pilot Validation Required: SGE + MCDI and saltwater battery revenues are contingent on successful pilot validation (Vol 14, Months 14–22). Go/no-go gates at Month 18 will determine whether these revenues materialize. Early engagement with technology partners (Appendix D) is recommended to accelerate de-risking.

Note — ZADB Pilot Not a Deficit Buffer: The zinc-air desalination battery (ZADB) is a TRL 4 demonstration project (Vol 22). It is not relied upon for deficit buffering at pilot scale — its value is R&D, publications, and optional commercial scale-up in Year 5+.

Operate as a Grid-Supportive Asset (Volume 21): This shifts the facility from being a passive load to an active contributor to grid stability. By participating in demand response programs, providing microgrid islanding, and offering thermal storage grid services, it can generate an additional $500,000+ per year in revenue.

Embrace the 0% GPU Load Survival Mode: The document's strategy for a zero-computing-load scenario is crucial. The plan allows the facility to operate as a standalone desalination and power plant, producing water and revenue even without GPUs, reducing the annual deficit by $3.07 million compared to the baseline.

## Financial & Strategic Improvements (4 Changes)

These changes involve how the project is financed and how its revenue streams are structured.

Secure a "Green Bond" for Resilient Infrastructure: The project already includes $50 million from a Canada Infrastructure Bank bond at a low 4.2% interest rate. This low-cost, long-term debt reduces the project's cost of capital and improves its financial resilience.

Establish a Multi-Year Water Supply Agreement + Tiered Revenue Model: A 10–15 year water supply agreement with Cartwright and coastal Labrador communities for 50–130K GPD at $2.80–3.50/Kgal creates a stable revenue floor. Stack this with NL Hydro capacity payments (if interconnection available) so that water + grid = $1.2M+ annual revenue even at 0% GPU load. This de-risks the revenue stream by guaranteeing base payments from the grid (for capacity) and for water, with additional revenue from computing and energy sales being variable.

Secure a Technology Offtake Partner: Engage a utility, desalination operator, or industrial water user (e.g., Cargill, Veolia) to prepay for rights to the SGE/MCDI, saltwater battery, or ZADB technology package in exchange for upfront capital. This de-risks the novel electrochemical systems while providing $5–10M in non-dilutive funding.

## Operational Efficiency Improvements (2 Changes)

These changes focus on reducing operating expenses to improve the bottom line.

Reduce Labor During Low-Demand Periods: The document outlines a plan to reduce staffing from 45 FTE to 20 FTE during a 0% GPU load scenario, saving $1.6 million annually in labor costs. This is a key element of the survival strategy.

Optimize Maintenance & Spare Parts Inventory: The document proposes a reduction in maintenance and parts costs during low-demand periods. Shifting to a "run-to-fail" or reduced maintenance schedule on non-critical systems is a cost-saving measure.

## Bottom Line: Total Deficit Reduction

| Strategy Category | Annual Deficit Reduction |
| --- | --- |
| Structural/Operational (4 changes) | ~$3.07M |
| Financial/Strategic (4 changes) | ~$0.5-1.0M |
| Operational Efficiency (2 changes) | ~$1.6M |
| TOTAL POTENTIAL BUFFER | ~$5.2-5.7M |

The $4.71M deficit is fully covered with margin. These strategies transform MundusLux-300 into a resilient, diversified asset capable of operating profitably even without its primary computing revenue.

## Next Steps

The following actions should be initiated to execute these recommendations:

Month 1: Initiate water supply agreement discussions with Cartwright and Paradise River municipal authorities.

Month 3: Issue RFP for SGE + MCDI technology partnership (Voltea/Tokuyama).

Month 6: Pilot validation go/no-go (Vol 14) determines timing for saltwater battery CAPEX.

Year 1: Execute grid services agreement with NL Hydro for $50–100K/yr DR revenue (if interconnection available; limited remote capacity).

Year 2: Confirm geothermal resource; if positive, proceed with production wells.

# Volume 5: Site Relocation & Cold-Climate Adaptation (Newfoundland)

This volume documents the comprehensive redesign required for relocation of the MundusLux-300 facility from Monterey Bay, California (36°N, Mediterranean climate) to a subarctic coastal site near Cartwright, Newfoundland (53°42'52.23"N 57°00'55.21"W). At 53°42'N, the facility faces extreme cold, ice accretion, permafrost, limited winter solar, and restricted grid access. All 20 changes below align with Newfoundland's Provincial Green Energy Plan and leverage synergies with Project Nujio'qonik (4 GW wind-to-hydrogen initiative).

## 5.1 Structural & Civil Redesign (4 Changes)

Winterized Building Envelope (ICF Walls): Replace standard construction with Insulated Concrete Form (ICF) walls rated R-40+ with built-in thermal mass. ICF foundations provide passive thermal energy storage, showing 33-43% higher performance vs. conventional systems in Canadian climates. Building envelope achieves 0.6 ACH@50Pa (Passive House-level airtightness) with heat recovery ventilation. CAPEX add: $4.2M.

Seismic to Ice-Load Design: Switch from ASCE 7-22 seismic design (1.5g, Site Class D) to NBCC 2020 ice-load and snow-load design. At 53°42'N, winter ice accretion on structures is the primary design driver. Design for 2.0 kPa ground snow load, 1.5 kPa ice accretion on exposed members, and 150 km/h wind gusts. All structural steel upgraded to CSA G40.21 50W with Class C atmospheric corrosion protection (marine subarctic).

Drilled Piers to Frost-Protected Foundations: Move from 60-80 ft drilled piers to deep frost-protected shallow foundations with 1.2 m insulation below grade (XPS rigid board). Designed for discontinuous permafrost and seasonal freeze-thaw cycles to 2.5 m depth. Thermosyphon cooling loops prevent permafrost degradation under heated building footprints. CAPEX add: $1.8M (net savings vs. deep drilled piers in bedrock).

Critical Systems Enclosure: Co-locate all critical equipment — instruments, DCS/PLC racks, water treatment skids, BESS, and hydrogen systems — inside the conditioned building envelope. The California design had significant outdoor equipment; this is no longer viable at -25°C design minimum. Building expands from 60,000 SF to 78,000 SF (45,000 computing + 20,000 desal/process + 13,000 mechanical/electrical). Heating load: 850 kW design (winter).

## 5.2 Process & Thermal Redesign (4 Changes)

MED Feed Preheat with Waste Heat: Use GPU rack waste heat and heat recovery ventilation to preheat RO feedwater from near-freezing (0-2°C) seawater to 15-20°C. Research shows feed temperature increases from 20°C to 40°C can boost permeate flow by ~60%. This compensates for cold seawater and maintains design capacity year-round. Feed heating duty: 1.2 MW (winter design).

ICF-Integrated Thermal Storage: Integrate the building's ICF foundation wall system (1,850 m² surface area) as passive thermal energy storage. Excess daytime heat (GPU waste heat, solar thermal when available) is absorbed by the concrete mass and released at night, offsetting heat loss. Demonstrated effective in cold-climate Canadian buildings — reduces heating energy by 25-35%. Storage capacity: ~4,200 kWh (sensible, 8-hr discharge).

Doubled Insulation & Heat Recovery: All process piping upgraded to pre-insulated HDPE carrier pipe with 100 mm PU foam insulation and heat trace (self-regulating, 15 W/m). All equipment enclosures rated NEMA 4X with 50 mm insulation. High-efficiency heat recovery ventilation (sensible recovery 85%, enthalpy 75%) captures heat from GPU racks and process equipment. Annual heat recovery: 3,200 MWh.

Anti-Icing Systems: Install comprehensive anti-icing on seawater intake (submerged intake with bubbler system, 25 m offshore in 8 m depth), brine outfall (diffuser with continuous flow minimum 5 L/s to prevent freeze-up), and all above-grade piping (heat trace + insulation, 25 W/m design). Seawater intake structure: concrete caisson with heated deck. Annual anti-icing energy: 340 MWh. CAPEX: $2.1M.

## 5.3 Energy & Power Redesign (4 Changes)

Off-Grid/Microgrid Architecture: Shift from grid-supportive (PG&E) to mostly off-grid design. Newfoundland's grid is hydro-dominated but remote coastal sites face reliability challenges. The facility operates as a self-contained microgrid with 800V DC bus, MGC-701 controller, and seamless islanding (<500 ms transfer). Grid connection (if available) limited to 1 MW backup import. Design philosophy: generate >95% on-site year-round.

Increased On-Site Generation: More than double on-site generation: 3.5 MW wind (upgraded from 2.25 MW) with cold-climate rated turbines (IEC 61400 Class I, -30°C operation, de-icing systems), 1.5 MW solar (down from 2.5 MW due to latitude; bifacial panels with snow-shedding racks), and 500 kW diesel backup (winter peaking). Annual generation: 18,200 MWh (wind 72%, solar 15%, diesel 13%).

Large-Scale Battery Storage: Expand BESS from 8 MWh to 24 MWh LiFePO₄ (72-hour autonomy at critical load). Cold-weather battery enclosures with active heating maintain 15-25°C cell temperature. Additional 48 MWh saltwater flow battery (Vol 22) provides seasonal storage. Total storage: 72 MWh — sufficient for 5-day winter autonomy at reduced load. CAPEX: $14.2M (BESS) + $2.8M (saltwater battery).

Hydrogen-Ready Systems: Integrate wind-to-hydrogen capability aligned with Project Nujio'qonik. 2 MW electrolyzer (PEM, -20°C rated), 5,000 kg metal hydride storage (30 bar, ambient), 2 MW fuel cell for winter peaking. Strategic partnership with World Energy GH2 for offtake. Hydrogen serves triple role: (1) long-duration energy storage, (2) winter peaking fuel, (3) export revenue ($2.5M+/yr at scale). CAPEX: $8.5M (electrolyzer + storage + fuel cell).

## 5.4 Water & Desalination Redesign (4 Changes)

RO as Primary Desalination: Shift from MED (thermal, 160K GPD primary) to RO as the primary desalination process at 240K GPD (3 trains × 80K GPD). RO is less affected by cold seawater temperatures and requires less energy per m³ (3.2 kWh/m³ vs. 5.8 kWh/m³ for MED at reduced temperature). MED retained as secondary/seasonal operation (80-160K GPD, summer peaking) using waste heat when available. Total capacity: 320-400K GPD (summer), 240-320K GPD (winter).

High-Pressure RO (1000 psi / 69 bar): Adopt high-pressure RO systems to compensate for colder, denser feedwater. The California design's 58 bar is insufficient for sustained winter operation at 0-2°C feed. Upgraded to 69 bar (1,000 psi) with energy recovery (PX-Q300, 95% efficiency) and waste heat preheat to maintain 15-20°C feed temperature. Membranes: Toray TM820M-400, rated to 70 bar, 40°C max. Winter flux maintained at 95% of design.

Controlled Feed Temperature: Use GPU rack waste heat (7.5 MW available at 55°C) and heat recovery ventilation to maintain RO feed temperature at 15-20°C year-round. Feed heating system: plate-and-frame heat exchanger (2.5 MW duty) with 3-way temperature control valve. Temperature below 10°C triggers flux decline alarms; below 5°C triggers automatic turndown. Annual waste heat utilized: 5,800 MWh (70% of available).

Winterized Brine Management: Design brine discharge for subarctic conditions. Brine outfall: submerged diffuser at 12 m depth (below winter thermocline), 500 m offshore, with continuous minimum flow of 5 L/s to prevent freeze-up. Outfall pipe: 200 mm HDPE SDR11 with 75 mm insulation and heat trace. Marine impact monitoring required (3-year program, $180K/yr). Brine concentration: 165 ppt (winter) to 120 ppt (summer) depending on blend ratio.

## 5.5 Operational & Maintenance Redesign (4 Changes)

Remote Operations Capability: Enable full remote operations for winter months when site access is challenging (November-April). DCS/SCADA system upgraded for secure remote access with satellite backup communications (Starlink + Iridium). On-site staff reduced from 45 FTE to 25 FTE core (engineers, operators, maintenance) with 15 remote support staff. Annual labor savings: $1.3M. Remote ops center: St. John's, NL (existing facility).

Winterized Logistics Plan: Establish resupply and equipment handling procedures for icy conditions. Primary access: Port of Stephenville (year-round deep-water, used by Project Nujio'qonik) with weekly barge service (May-November) and monthly ice-class vessel (December-April). On-site fuel storage: 60-day diesel reserve (150,000 L) in heated underground tank. Critical spare parts inventory expanded to 6-month supply (vs. 3-month California design) due to extended lead times. Logistics CAPEX: $1.4M (fuel storage + heated warehouse).

Extended Equipment Spares: Increase spare parts inventory from $1.29M (3-month) to $2.8M (6-month supply) for critical equipment. Key items: RO membranes (6 sets), wind turbine blades (2 sets, ice-rated), BESS modules (24 units), heat trace cable (5,000 m), diesel engine parts (overhaul kit). Lead times: 8-16 weeks for most items (vs. 2-4 weeks in California). Warehouse: heated, 2,000 SF with humidity control.

Stakeholder & Regulatory Alignment: Proactive engagement with Newfoundland & Labrador regulators and communities. Key requirements: (1) Water Use License under NL Water Resources Act for industrial seawater withdrawal, (2) Environmental Assessment under CNLR 1141/01, (3) Engagement with NunatuKavut Community Council (Indigenous rights holders in the region), (4) Alignment with Provincial Green Energy Plan and Project Nujio'qonik infrastructure sharing, (5) Canada-NL Infrastructure Program funding eligibility. Community benefits agreement: 40% local hiring, $200K/yr community fund, marine monitoring program.

# Volume 6: Design Basis Memorandum

Fundamental design parameters for MundusLux-300 Newfoundland adaptation. Site relocated to subarctic coastal Labrador (53°42'N). All systems redesigned for ice-load, permafrost, and year-round cold-climate operation. All deviations require written Engineering Manager approval.

## 6.1 Design Life & Availability

| Asset | Design Life | Replacement | Basis |
| --- | --- | --- | --- |
| Building structure | 50 yr | N/A | NBCC 2020, Ice Load + Snow Load, Permafrost Zone |
| GPU clusters | 7 yr | 4-yr refresh | 2x perf/2yr cadence |
| RO membranes | 7 yr | 5.5 yr | Mfr warranty + fouling |
| MED tubes | 20 yr | N/A | Ti, anti-scalant |
| BESS LiFePO4 | 20 yr | 15-yr capacity | 6,000 cycles, 80% DoD |
| Solar PV | 30 yr | 25-yr inverter | 0.45%/yr degrad |
| Wind (HAWT) | 20 yr | 10-yr bearings | IEC 61400 Class III |

## 6.2 Availability Targets

| System | Target | Downtime/yr | Basis |
| --- | --- | --- | --- |
| GPU (core) | 99.95% | 4.4 hr | Tier III |
| RO desal | 99.0% | 87.6 hr | 3-train N+1 |
| MED desal | 97.5% | 219 hr | N+1 vacuum |
| Thermal storage | 99.9% | 8.8 hr | 5-tank 4+1 |
| Safety (SIS) | 99.99% | 0.9 hr | SIL-2/3 per IEC 61511 |
| SCADA | 99.9% | 8.76 hr | Tier III historian |
| Overall facility | 99.5% | 43.8 hr | Revenue-weighted |

## 6.3 Codes & Standards

| Code | Edition | Application |
| --- | --- | --- |
| ASME BPVC VIII-1 | 2023 | Pressure vessels, HX |
| ASME B31.3 | 2022 | Process piping |
| API 650/620 | 13th/12th | Storage tanks |
| IEC 61511/62443 | 2016/2018 | SIS / Cybersecurity |
| CEC Part 1 / NFPA 72 | 2024/22 | Electrical / Fire / IT (cold-climate rated) |
| NBCC 2020 | 2022 | Ice load, snow load, permafrost |
| CSA S16 / CSA A23.3 | 2016/2019 | Steel / Concrete (ICF where noted) |
| NL OHS + CNLR 1196/01 | — | PSM |
| ISA S5.1 | 2009 | Instrumentation |

# Volume 7: Process Design

Process flow diagrams, equipment specifications, and pipe specifications for the integrated data center-desalination facility. Cold-climate adaptation: RO is now primary (240K GPD), MED is seasonal secondary (80-160K GPD). All systems winterized with heat trace, insulation, and anti-icing.

## 7.1 Process Overview

[SEAWATER INTAKE] → [Anti-Ice Screen] → [RO Pre-treatment + Waste Heat Preheat]
         ↓
  [GPU RACKS] 55°C coolant → [PCM Buffer] → [MED Thermal Feed (backup)]
         ↓                                    ↓
  [Heat Recovery Ventilation]        [MED 6-Effect] → [Distillate (seasonal)]
         ↓                                    ↓
  [RO High-Pressure 1000psi] → [PX] → [RO Permeate] → [IX Polish]
         ↓                                    ↑
  [Product Water] ← [500K gal Storage] ← [RO Primary + MED Seasonal]

## 7.2 Equipment Specifications

| Equipment | Tag | Specification | Duty |
| --- | --- | --- | --- |
| RO Train A | RO-101 | SWRO-HP, 80K GPD, 1000 psi | Cold seawater → permeate (waste heat preheat to 15°C) |
| RO Train B | RO-102 | SWRO, 80K GPD | Seawater → permeate |
| RO Train C | RO-103 | SWRO, 80K GPD | Backup/train maintenance |
| MED Unit | MED-301 | 6-effect, Ti tubes (seasonal, summer-peaking) | 160K GPD distillate (summer peak); 80K GPD (winter minimum) |
| PCM Buffer | TES-401 | 120 m³, Al-foam enhanced | 180-min thermal protection |
| Thermal Storage | TES-402 | 500K gal stratified | Diurnal load matching |
| PX Energy Recovery | PX-Q300 | Isobaric, 95% efficiency | RO concentrate pressure recovery |
| MVC Concentrator | MVC-501 | 800 kW electric | Brine ZLD |
| Booster Heater | H-101 | 1.5 MW (zero-carbon backup) | MED thermal stabilization |

## 7.3 Pipe Specifications (Selected)

| Line | Size | Material | Service | Temp/Press |
| --- | --- | --- | --- | --- |
| SW-101 | 16in | FRP | Seawater intake | 0-2°C / 2 bar (ice-protected intake) |
| RO-201 | 8in | 316L SS | RO permeate | 15°C / 2 bar |
| RO-202 | 10in | Duplex 2205 | RO concentrate | 15°C / 69 bar (1000 psi, heated feed) |
| MED-301 | 12in | Duplex 2205 | MED feed | 58°C / 1.5 bar (waste heat boosted) |
| MED-302 | 10in | Duplex 2205 | MED brine reject | 40°C / 1.2 bar (insulated + traced) |
| CL-501 | 8in | HDPE DC | GPU coolant | 55°C / 10 bar (heat traced, insulated) |
| FW-601 | 8in | HDPE | Freshwater distrib | 20°C / 4 bar |
| BR-702 | 6in | FRP | Brine to crystallizer | 35°C / 1 bar |

# Volume 8: Instrumentation & Control Systems

142 instrument tags across 14 safety instrumented functions (SIFs). ISA S5.1 nomenclature. IEC 62443 SL-2 cybersecurity.

## 8.1 Instrument Count by Type

| Type | Count | Key Applications |
| --- | --- | --- |
| Temperature (RTD/Thermocouple) | 42 | PCM buffer, MED effects, thermal storage, GPU coolant |
| Pressure | 28 | RO high-pressure, MED vacuum, gas lines |
| Flow (magnetic/ultrasonic) | 24 | Seawater, permeate, brine, coolant |
| Level (radar/dp) | 18 | Storage tanks, MED effects |
| Conductivity/pH | 12 | Water quality monitoring |
| Vibration | 10 | Pumps, compressors, wind turbines |
| Gas detection | 8 | H2, CH4, H2S monitoring |

## 8.2 Control System Architecture

Distributed Control System (DCS) with triple-redundant safety PLC. Six-zone cybersecurity per IEC 62443: Zone 0 (Safety), Zone 1 (Process Control), Zone 2 (Operations), Zone 3 (Corporate), DMZ (Data Exchange), Zone 4 (External).

## 8.3 Key Control Loops

| Loop | Tag | Type | Setpoint | Action |
| --- | --- | --- | --- | --- |
| MED feed temp | TIC-201 | Cascade | 58°C ± 2°C | Modulate mixing valve TV-601 |
| RO feed pressure | PIC-101 | Single | 58 bar | Modulate VFD on HP pump |
| PCM charge level | QIC-401 | Feedforward | 95-100% | Prioritize GPU waste heat |
| Thermal margin | TMI-501 | Safety | 0.35-1.00 | Auto-turndown at TMI < 0.35 |
| Vacuum control | PIC-301 | Cascade | 0.15 bar | Modulate vacuum pump speed |

# Volume 9: Safety Engineering — HAZOP Study

HAZOP per IEC 61882 with 6 nodes, 30 deviations, and 8 action items. FMEA per MIL-STD-1629A.

## 9.1 HAZOP Nodes

| Node | Description | Deviations | Actions |
| --- | --- | --- | --- |
| GPU coolant loop | D2C cooling, 55°C, 10 bar | No flow, high temp, leak | 3 actions: leak detection SIL-3, auto-isolation, emergency cooling |
| MED thermal feed | 6-effect, 58°C, 1.5 bar | Low temp, vacuum loss, brine leak | 2 actions: TMI controller, PCM backup activation |
| RO high-pressure | 58 bar, 240K GPD | Overpressure, membrane rupture | 1 action: relief valves + pressure trip |
| Brine handling | 165 ppt, ZLD | Overflow, crystallizer failure | 1 action: secondary containment + alarm |
| Gas systems | H2 (electrolyzer), CH4 backup | Leak, ignition | 1 action: gas detection + ESD |

## 9.2 Safety Instrumented Functions

| SIF | Sensor | Logic Solver | Final Element | SIL |
| --- | --- | --- | --- | --- |
| SIF-01: GPU overtemp | TT-501A/B/C | Triconex | XV-501 coolant divert | SIL-3 |
| SIF-02: MED vacuum loss | PT-301A/B | Triconex | XV-302 steam isolation | SIL-2 |
| SIF-03: RO overpressure | PT-101A/B | Triconex | PSV-101 + XV-103 | SIL-2 |
| SIF-04: Gas leak | GT-701/702 | Triconex | XV-701 fuel isolation | SIL-3 |
| SIF-05: Brine overflow | LT-601A/B | Triconex | P-601 shutdown + XV-602 | SIL-2 |

# Volume 10: Structural & Electrical Engineering

## 10.1 Structural Design

| Parameter | Value | Code |
| --- | --- | --- |
| Ice/snow load design | NBCC 2020, 2.0 kPa snow load, 1.5 kPa ice accretion | NBCC 2020 |
| Base isolation | Lead-rubber bearings, 2.5s period | ASCE 41-17 |
| Wind load | 150 km/h 3-sec gust with ice accretion | ASCE 7-22 |
| Foundation | Frost-protected foundations, 1.2 m XPS insulation, 15-25 m depth | NBCC 2020 + CSA S16 |
| Building SF | 45,000 sq ft computing + 20,000 sq ft desal + 13,000 mech | NBCC 2020 |

## 10.2 Electrical Single-Line

12.47 kV utility service → 5 MVA transformer → 480V switchgear. On-site generation: 2.5 MW solar, 2.25 MW wind, 8 MWh BESS, 500 kW diesel. DC-coupled 800V bus for GPU racks.

## 10.3 Protection Coordination

| Device | Rating | Setting | CT Ratio |
| --- | --- | --- | --- |
| Utility relay | 5 kA interrupt | 51V, 67N, 79 | 2000:5 |
| Main breaker | 6.3 kA | LSIG, ZSI | — |
| BESS breaker | 2.5 kA | 51, 27/59, 81O/U | 800:5 |
| Solar breaker | 1.6 kA | 51, 27/59 | 600:5 |

## 10.4 Geotechnical Site Characterization — Cartwright

The following geotechnical parameters are based on preliminary site investigations, regional geological surveys, and analogies with similar subarctic coastal sites in Labrador. A detailed geotechnical survey (Appendix A) is required during detailed design.

Bedrock depth: Bedrock encountered at 8–18 m depth below ground surface. The overburden consists of glacial till (sandy silty clay) with cobbles and boulders. Bedrock is Precambrian granite gneiss with RQD 65–85%. Foundation design: steel pipe piles socketed 3 m into bedrock where structural loads exceed frost-protected shallow foundation capacity.

Permafrost characteristics: Discontinuous permafrost zone. Permafrost encountered in 30–40% of test pits, typically at 1.5–2.5 m depth in sheltered/vegetated areas. Active layer thickness: 1.2–1.8 m (summer maximum). Permafrost temperature: -1°C to -2.5°C (warm permafrost, thermally unstable). Ground ice content: 15–30% by volume in frozen layers. Thermosyphon cooling loops installed under all heated building footprints to prevent permafrost degradation.

Frost heave potential: High frost susceptibility in silty clay till layers (F2–F3 classification per CSA S16). Frost heave rate: 25–50 mm/year observed in local infrastructure. Mitigation: (1) All piles include polyethylene bond breakers to prevent adfreeze (frost-jacking); (2) Foundations placed below active layer (2.5 m minimum); (3) 1.2 m XPS rigid insulation under all slab-on-grade construction; (4) Elevated structural pads (0.6 m above natural grade) for mechanical equipment.

Iceberg scouring depth: Nearshore seabed at 8–15 m depth (within the intake/outfall zone). Historical iceberg scouring depth: up to 2 m below mudline in 12 m water depth. Design protection: intake caisson anchored to bedrock with 12 m steel H-piles; outfall pipe trenched 1.5 m below mudline for 200 m offshore with concrete mattress protection on exposed sections. International Ice Patrol (IIP) monitoring with 5 km exclusion zone for bergs >10,000 tonnes.

# Volume 11: Dynamic Operating Model

Three representative days with hourly thermal and electrical balances.

## 11.1 Summer Peak Day (July 15)

| Hour | GPU Load | Waste Heat | Solar | Wind | BESS | Grid Import | MED Output |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 06:00 | 85% | 6.4 MW | 0.8 MW | 0.4 MW | 0 | 1.3 MW | 160K GPD |
| 10:00 | 92% | 6.9 MW | 2.1 MW | 0.6 MW | -0.5 MW | 0 | 160K GPD |
| 14:00 | 95% | 7.1 MW | 2.5 MW | 0.8 MW | -1.2 MW | 0 | 160K GPD |
| 18:00 | 78% | 5.9 MW | 1.2 MW | 0.9 MW | 0 | 1.4 MW | 155K GPD |
| 22:00 | 65% | 4.9 MW | 0 | 1.0 MW | 0 | 2.1 MW | 145K GPD |

## 11.2 Winter Low Day (January 20)

| Hour | GPU Load | Waste Heat | Solar | Wind | BESS | Grid Import | MED Output |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 06:00 | 70% | 5.3 MW | 0.2 MW | 1.1 MW | 0.5 MW | 1.4 MW | 140K GPD |
| 10:00 | 75% | 5.6 MW | 0.8 MW | 1.3 MW | 0 | 1.2 MW | 148K GPD |
| 14:00 | 80% | 6.0 MW | 1.0 MW | 1.2 MW | 0 | 1.3 MW | 152K GPD |
| 18:00 | 72% | 5.4 MW | 0 | 1.0 MW | 0.3 MW | 1.8 MW | 142K GPD |

## 11.3 GPU Outage Day (0% Load)

| Hour | GPU Load | Waste Heat | Solar Thermal | PCM | MVC | Grid Import | MED Output |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 06:00 | 0% | 0 MW | 0.4 MW | Discharging | Standby | 2.1 MW | 110K GPD |
| 10:00 | 0% | 0 MW | 1.2 MW | Charging | Standby | 1.0 MW | 145K GPD |
| 14:00 | 0% | 0 MW | 1.5 MW | 100% | Standby | 0.8 MW | 160K GPD |
| 18:00 | 0% | 0 MW | 0.6 MW | Discharging | Standby | 1.8 MW | 120K GPD |
| 22:00 | 0% | 0 MW | 0 MW | Discharging | Active | 2.3 MW | 95K GPD |

## 16.2 Local Employment & Workforce Development

With a population of approximately 500, Cartwright is a small coastal community with a predominantly fishing-based economy. The facility will prioritize local hiring, with 25 FTE on-site and 15 remote positions. Realistic locally fillable roles include:

On-site roles (25 FTE): Facilities maintenance (5), security (4), RO/MED plant operators (6), marine logistics coordinator (2), environmental monitor (2), kitchen/food services (3), administrative support (3). These roles require technical training but not advanced degrees, and can be filled through local workforce development programs.

Remote roles (15 FTE): Software engineers, data scientists, financial analysts, and project managers can be based in St. John's, Happy Valley-Goose Bay, or other NL centres with high-speed internet connectivity.

## 16.3 Training & Skills Development

Local hires will receive comprehensive training through partnerships with:

Memorial University: Canada's easternmost comprehensive university offers programs in oceanography, environmental science, and engineering technology. Partnership for marine monitoring and R&D collaboration.

College of the North Atlantic (CNA): Multiple campuses across NL offer trades programs (electrical, plumbing, welding, industrial mechanics) and process operations diplomas relevant to desalination plant operations.

NunatuKavut Training Partnership: Collaborative skills training with the NunatuKavut Community Council for environmental monitoring, traditional ecological knowledge integration, and cultural heritage protocols.

## 16.4 NunatuKavut Community Council Engagement

The NunatuKavut Community Council (NCC) represents the Indigenous rights holders in the Cartwright area. As the elected governing body for Inuit-Metis of southern and central Labrador, the NCC must be consulted on all major projects affecting traditional lands and waters.

Key engagement principles: (1) Early and ongoing consultation — engagement initiated in pre-feasibility phase, not post-design; (2) Free, prior, and informed consent (FPIC) for any activities affecting traditional use areas; (3) Co-management of marine monitoring and environmental stewardship; (4) Preference for NCC-affiliated businesses in contracting and procurement; (5) Protection of culturally significant sites and species (Atlantic salmon, caribou, seabird colonies); (6) Annual community meetings in Cartwright with NCC leadership and local harvesters.

Specific NCC concerns to address: impact on LFA 14 lobster fishery (shared fishing grounds near intake/outfall), effects on salmon rivers (Paradise River is nearby), noise and visual impact on coastal landscapes, and benefits sharing for community infrastructure (roads, broadband, water supply upgrades).

## 16.5 Local Economic Integration

Cartwright's economy is based on fishing (lobster, crab, cod), small-scale tourism, and government services. The facility will integrate through:

Fishing sector: No overlap between facility operations and active fishing grounds — intake located outside primary lobster fishing areas. Facility will purchase fresh seafood for staff cafeteria, supporting local fishers.

Tourism: The public visitor center (Year 3) will become an eco-tourism destination, showcasing cold-climate renewable energy, desalination, and ocean stewardship. Potential for guided tours, educational programs, and research partnerships.

Infrastructure: $200K/year community fund will support road maintenance, broadband expansion, and emergency services. Water surplus (50–130K GPD) provided at cost to Cartwright and Paradise River.

# Volume 12: Capital Cost, Commissioning & Operations

## 12.1 Revised Capital Cost Estimate (Post Value Engineering)

| Item | Baseline ($M) | Revised ($M) | Change |
| --- | --- | --- | --- |
| Data center (GPU, cooling, elec) | $165.0 | $165.0 | $0 |
| RO desalination | $48.0 | $42.0 | -$6.0 |
| MED desalination | $52.0 | $38.0 | -$14.0 |
| Brine management (outfall) | $38.0 | $8.0 | -$30.0 |
| Thermal storage & distrib | $28.0 | $19.0 | -$9.0 |
| Renewable generation | $32.0 | $24.0 | -$8.0 |
| BESS & backup power | $18.0 | $18.0 | $0 |
| Building & civil | $12.0 | $8.0 | -$4.0 |
| Piping & materials (cold-climate) | $4.5 | $4.5 | +$4.5 |
| Instrumentation & SCADA | $8.9 | $7.4 | -$1.5 |
| Zero-carbon thermal (Vol 20) | $0 | $6.7 | +$6.7 |
| Grid-supportive systems (Vol 21) | $0 | $4.4 | +$4.4 |
| Salt-to-power systems (Vol 22) | $0 | $3.2 | +$3.2 |
| SUBTOTAL | $401.9 | $354.7 | -$47.2 |
| Contingency (15%) | $60.3 | $53.2 | -$7.1 |
| TOTAL PROJECT COST | $462.2 | $407.9 | -$54.3 |

## 12.2 Commissioning Phases

14-phase commissioning over 18 months: Phase 1 (civil/structural), Phase 2-4 (mechanical systems), Phase 5-7 (electrical/controls), Phase 8 (RO/MED wet testing), Phase 9 (GPU integration), Phase 10 (thermal resilience validation), Phase 11 (zero-carbon systems), Phase 12 (grid services), Phase 13 (salt-to-power), Phase 14 (performance guarantee testing).

## 12.3 O&M Summary

| Category | Annual Cost | Notes |
| --- | --- | --- |
| Labor (25 FTE core + 15 remote) | $3.2M | Reduced on-site crew; remote ops capability |
| Electricity (net) | $0.125M | Down from $1.2M (grid-supportive) |
| Chemicals (reduced) | $0.18M | 90% reduction via FO pre-treatment |
| Maintenance | $1.8M | 4.5% of direct CAPEX |
| Insurance | $2.5M | $165M property + $50M BI |
| Spare parts | $1.29M | Critical spares inventory |
| TOTAL OPEX | $10.4M | Down from $14.2M baseline |

# Volume 13: Risk Analysis & Independent Review

## 13.1 Permit Matrix

| Permit | Agency | Timeline | Status | Risk |
| --- | --- | --- | --- | --- |
| NL Environmental Assessment | NL Environment & Climate Change | 18-24 mo | Required | Medium — ocean outfall simplifies vs onshore discharge |
| NL Water Resources Act Discharge | NL Water Resources | 12-18 mo | Required | Low — diffuser design proven |
| Air Quality (SOFC) | NL ECC | 6-12 mo | Year 7 | Low — zero-emission by Year 8 |
| Local Building | NL Environment & Climate Change | 6-9 mo | Required | Low — standard process |
| Transport Canada Aviation | FAA | 3-6 mo | Required | Low — ice-rated wind turbines <200 ft |

## 13.2 Monte Carlo Simulation (10,000 iterations)

| Metric | P10 | P50 | P90 |
| --- | --- | --- | --- |
| NPV ($M) | $420 | $685 | $1,050 |
| IRR | 14.2% | 18.5% | 24.1% |
| Payback (yr) | 9.2 | 7.1 | 5.4 |
| LCOE ($/MWh) | $85 | $72 | $58 |

## 13.3 Red Team Review

18 attack scenarios evaluated including: seismic + tsunami, multi-year AI winter, membrane supply chain disruption, cyberattack on SCADA, and regulatory reversal. All scenarios have documented response protocols. Worst credible case: $15.6M deficit over 24 months (AI winter + structural repair) — covered by $50M business interruption insurance.

## 13.4 Environmental Assessment — Baseline Studies & Cumulative Effects

The NL Environmental Assessment (CNLR 1141/01) requires comprehensive baseline studies and cumulative effects assessment. The following studies are required for the Cartwright site:

Marine mammals: Baseline survey of harbour seals, harp seals, and minke whales in the intake/outfall zone (May–October). Hydrophone deployment for 12 months to characterize underwater noise. Critical: breeding season (March–June) restrictions on pile driving and vessel traffic.

Migratory birds: Baseline survey of seabird colonies (murres, puffins, Arctic terns) within 5 km of outfall. Nesting season (April–August) operational restrictions. Collision risk assessment for wind turbines (avian radar 2-year study).

Fisheries: Baseline assessment of lobster (LFA 14), snow crab, and groundfish populations near intake/outfall. Entrainment/impingement study at design intake velocity (0.5 m/s). Brine plume dispersion modeling (Delft3D) to confirm 100:1 dilution at 100 m. Atlantic salmon parr survey in Paradise River (1 km from site) — electrofishing and habitat assessment.

Species at risk: The following COSEWIC-assessed species may occur in the project area: Atlantic salmon (Special Concern, inner Bay of Fundy population Endangered), woodland caribou (Threatened — Labrador population), harlequin duck (Special Concern), and red-necked phalarope (Special Concern). Habitat offset plan required if any critical habitat is affected.

Cumulative effects: Project Nujio'qonik (4 GW wind-to-hydrogen, Stephenville, 150 km west) is the primary cumulative effects consideration. Interaction assessment: (1) Shared marine shipping corridor — coordinated vessel traffic management; (2) Combined brine discharge — cumulative salinity modeling in Sandwich Bay; (3) Shared workforce — peak construction period overlap (Year 2) may strain skilled labor availability; (4) Grid interconnection — both projects seeking NL Hydro connection; coordinated transmission planning recommended. The two projects are complementary: Nujio'qonik provides large-scale hydrogen export infrastructure; MundusLux-300 provides distributed desalination and computing services.

# Volume 14: Pilot-Scale Validation Plan

$18.7M, 5% scale, 24-month program with go/no-go gates at Month 6, 12, and 18.

## 14.1 Pilot Modules

| Module | Scale | Cost | Duration |
| --- | --- | --- | --- |
| RO desalination | 8K GPD | $2.1M | Months 1-6 |
| MED thermal | 8K GPD | $3.8M | Months 3-9 |
| PCM buffer | 2.4 m³ | $1.2M | Months 4-8 |
| Solar thermal | 210 m² PTSC | $1.8M | Months 6-12 |
| DC microgrid | 250 kW | $1.5M | Months 8-14 |
| Thermal resilience (all 3) | Pilots above | $2.4M | Months 12-18 |
| SGE + MCDI (Vol 22) | 5 m² RED + 1 m³/h MCDI | $1.2M | Months 14-22 |
| Saltwater flow battery | 10 kW / 50 kWh | $0.8M | Months 16-22 |
| Structural/seismic | 1:10 scale pier | $0.9M | Months 1-8 |
| Go/No-Go Gates | — | $3.0M | Months 6, 12, 18 |

# Volume 15: Technology Readiness Assessment

NASA TRL scale assessment of 13 subsystems. Four subsystems on critical path below TRL 7.

| Subsystem | TRL | Risk | Path to TRL 9 |
| --- | --- | --- | --- |
| RO desalination (58 bar) | 9 | Low | Proven technology |
| MED 6-effect (low temp) | 8 | Low | Pilot validates |
| PCM Al-foam enhanced | 7 | Medium | Pilot Month 4-8 |
| Solar thermal PTSC + TES | 8 | Low | Proven, site-adapt |
| DC-coupled microgrid | 7 | Medium | Pilot Month 8-14 |
| MVC vapor compression | 8 | Low | Proven technology |
| SGE + MCDI integrated | 5 | High | Pilot Month 14-22 critical |
| Saltwater flow battery | 5 | High | Pilot Month 16-22 critical |
| LAD-Flex DR software | 8 | Low | Code integration |
| Hydrogen storage (metal hydride) | 6 | Medium | Vendor qualification |

# Volume 16: Community Engagement Plan

10 stakeholder groups, 36-month timeline, $1.7M budget. Key groups: NunatuKavut Community Council, Port of Stephenville Authority, NL Department of Environment & Climate Change, Memorial University (oceanography), Project Nujio'qonik partnership team, local fish harvesters (LFA 14), nearby coastal communities (Cartwright, Paradise River).

## 16.1 Commitments

| Commitment | Value | Timeline |
| --- | --- | --- |
| Local hiring preference | 40% of 25 FTE from Labrador Coast + 15 remote from NL | Year 1 |
| Water surplus for community | 50-130K GPD at cost to coastal communities (Cartwright, Paradise River) | Year 2 |
| Marine monitoring program | $120K/yr independent monitoring | Ongoing |
| Public visitor center | Educational facility on desal + renewables + cold-climate microgrids | Year 3 |
| Emergency water reserve | 1M gal storage for community water security / emergency supply | Year 1 |

# Volume 17: Financing & Ownership Structure

$407.9M capital stack (revised v5.3).

## 17.1 Capital Stack

| Source | Amount ($M) | Terms | Return |
| --- | --- | --- | --- |
| Senior debt | $250 | 7.5% fixed, 15-yr | 1.7x MOIC |
| Tax equity | $45 | ITC + depreciation | 2.3x MOIC |
| Strategic partner | $35 | 24% equity | 6.5x MOIC |
| Management | $5 | Sweat equity | 10.4x MOIC |
| Canada Infrastructure Bank green bond | $50 | 4.2% tax-exempt | 1.4x MOIC |
| Clean Hydrogen ITC + Clean Electricity ITC | $17.8 | Upfront credits | N/A |
| TOTAL | $402.8 | — | — |

## 17.2 Cash Flow Summary

| Year | Revenue ($M) | OpEx ($M) | Debt Service ($M) | Net CF ($M) |
| --- | --- | --- | --- | --- |
| 1-2 (construction) | $0 | $2.1 | $0 | -$2.1 |
| 3 (ramp) | $28.5 | $8.4 | $18.8 | $1.3 |
| 5 (steady-state) | $42.0 | $10.4 | $18.8 | $12.8 |
| 10 (mature) | $48.5 | $10.4 | $0 | $38.1 |
| 15 (exit) | $52.0 | $11.2 | $0 | $40.8 |

# Volume 18: Thermal Resilience & Cascade Protection Engineering

Three-intervention system eliminates thermal cascade stall risk — the facility's single most critical operational vulnerability.

## 18.1 Threat Analysis

| Scenario | Temp Drop Rate | Time to Stall | Consequence |
| --- | --- | --- | --- |
| Full GPU rack outage (25%) | -8°C / 3 min | 12-18 min | MED vacuum break, 4-hr restart |
| Scheduled maintenance (50%) | -4°C / 5 min | 25-35 min | Reduced output, booster ramp |
| AI batch completion | -6°C / 2 min | 15-20 min | Thermal shock to tubes |
| Cooling pump failure (N) | -10°C / 5 min | 10-15 min | Full MED trip |

## 18.2 PCM Thermal Buffer

142,000 kg Na2SO4·10H2O in 120 m³ tank with 3D-printed Al foam inserts (20× conductivity boost). Phase change at 52.5°C, latent heat 254 kJ/kg.

| Parameter | Baseline | Enhanced (v5.3) |
| --- | --- | --- |
| Latent heat capacity | 10,100 kWh | 13,200 kWh |
| Discharge duration | 92 min | 180 min |
| Total buffer (latent + sensible) | 138 min | 270 min |
| Full recharge time | 3.8 hr | 2.7 hr |
| Charging rate | 6.5 MW | 9.2 MW |

## 18.3 Forward Osmosis Pre-Treatment

8,400 m² TFC hollow fiber FO modules. 95% ion reduction (Ca²⁺ 97%, Mg²⁺ 96.5%, SO₄²⁻ 96.6%). MED cleaning interval extends from 14 to 90 days. Net negative OpEx: -$12K/year.

## 18.4 Thermo-Vapor Compressor

2.3:1 entrainment ratio, 500 kW steam generator, 30-sec startup. Extends thermal envelope to 48°C minimum GPU coolant. 7°C envelope extension. Net negative OpEx: -$222K/year.

## 18.5 Integrated Architecture

[GPU RACKS] 55°C coolant out → 7.5 MW
       ↓
  [PCM BUFFER] 180-min @ 52.5°C (Al-foam enhanced)
       ↓
  [FO PRE-TREATMENT] 95% ion reduction
       ↓
  [MED EFF 1] ← [TVC] 62°C boost (steam ejector)
       ↓
  [MED EFFS 2-6] Standard cascade
       ↓
  [THERMAL REGENERATOR] → FO draw recovery
       ↓
  [PRODUCT WATER] 345,000 GPD

## 18.6 Summary

| Intervention | CAPEX | Net Annual OpEx | Key Benefit |
| --- | --- | --- | --- |
| PCM Thermal Buffer | $1.2M | $28K | 180-min passive protection |
| FO Pre-Treatment | $2.61M | -$12K | 95% scaling elimination |
| TVC Steam Ejector | $1.00M | -$222K | 7°C envelope extension |
| TOTAL | $3.61M | -$234K/year | Cascade stall: ELIMINATED |

# Volume 19: Value Engineering & Cost Optimization

20-proposal review. 12 approved, 4 conditional, 2 rejected, 2 deferred. 18% CAPEX reduction achieved.

## 19.1 Approved (12 Proposals)

| # | Proposal | Savings | Notes |
| --- | --- | --- | --- |
| 1 | Ocean outfall (vs UIC well) | $48-72M | 100:1 dilution at 100m — proven (Carlsbad) |
| 3 | Duplex 2205 (vs Ti) MED lines | $6-10M | PREN 35 sufficient at 35-50°C |
| 6 | RO pressure 65→58 bar | $239K/yr | Modern membranes at 55-58 bar |
| 7 | 316L SS (vs Duplex) permeate | $1-2M | <200 ppm TDS = benign service |
| 8 | HDPE (vs DI) freshwater lines | $0.5-1M | 50-yr life, zero corrosion |
| 10 | GPU refresh 3→4 yr | $4.5M/yr | Reserve: $18M → $13.5M |
| 11 | HAWT (vs VAWT) wind | $3-5M + $180K/yr | 22% vs 14% capacity factor |
| 12 | Remove solar crystallizer pond | $5-8M | Land cost exceeds salt revenue |
| 13 | Reduce insulation thickness | $1-2M | Minimal energy impact |
| 15 | HDPE dual-containment coolant | $2-4M | PE100 PN16 rated for 12.6 bar @ 50°C |
| 17 | Passive intake (vs traveling) | $1-2M | 90% entrainment reduction |
| 19 | FRP (vs Duplex) brine <40°C | $1-3M | 1/6th weight, 30-yr life |

## 19.2 Conditionally Approved (4)

| # | Proposal | Savings | Condition |
| --- | --- | --- | --- |
| 4 | Thermal storage 500K→250K gal | $6-9M net | Confirm fire flow or add 150K fire tank |
| 9 | RO redundancy 3N→2+1 | $5-8M | Customer accepts 270K GPD during maint. |
| 14 | SCADA 99.95%→99.9% (HMI only) | $1-2M | SIS/DCS maintain 99.95%+ |
| 16 | MED 12→6 effects | $4-7M | Update HAZOP + PCM buffer calc |

## 19.3 Rejected (2)

Proposal 2 (replace MED with RO-2+MVC): REJECTED — destroys integrated energy model. Converts facility to two standalone plants. Proposal 5 (remove booster heater H-101): REJECTED — eliminates 0% GPU survival mode ($12M+/yr risk).

## 19.4 Revised CAPEX

|  | Baseline | Revised |
| --- | --- | --- |
| Direct costs | $401.9M | $329.4M |
| Contingency (15%) | $60.3M | $49.4M |
| TOTAL | $462.2M | $378.8M |

# Volume 20: Zero-Carbon Thermal Strategy & Fossil Fuel Elimination

Replaces the 1.5 MW natural gas booster heater with four independent renewable thermal sources. Eliminates 2,640 tCO2/year Scope 1 emissions entirely. Newfoundland adaptation: MED feed preheat with GPU waste heat (1.2 MW), ICF thermal storage, and hydrogen-ready SOFC.

## 20.1 Thermal Diversity Architecture

| Source | Capacity | Role | TRL |
| --- | --- | --- | --- |
| Solar thermal (PTSC) | 1.5 MW + 500 kWh TES | Primary daytime; 18-hr storage | 8 |
| Enhanced PCM buffer | 18,200 kWh | 180-min load-drop protection | 7 |
| MVC electric compression | 800 kW → 2.4 MW therm | Electric backup; BESS-powered | 8 |
| Geothermal well | 0.5-1.5 MW (pending) | 24/7 baseload if confirmed | 5 |

## 20.2 Solar Thermal Array

4,200 m² parabolic trough collectors (14 loops × 300 m²). 1.2 MW thermal at 55% peak efficiency (winter, low-angle sun). Dowtherm A transfer fluid. 65 m³ pressurized water TES (500 kWh) for 6-hr winter daylight + hydrogen fuel cell overnight. Net cost: $5.12M CAPEX, -$511K/year OpEx (gas elimination).

## 20.3 Enhanced PCM Buffer

120 m³ tank with 3D-printed Al foam inserts + spinel nano-ceramic coating. 20× thermal conductivity boost. 13,200 kWh latent heat = 180 minutes at full MED load. Alternative PCM for Year 10+: dimethyl terephthalate (67°C phase change, 165 kJ/kg).

## 20.4 MVC Expansion

800 kW centrifugal vapor compressor (VC-401) in parallel with TVC. 85% motor+compressor efficiency vs. 28% ejector. 15-sec startup. Powered by BESS during outages. CAPEX: $950K.

## 20.5 Geothermal Exploration

$2.8M slim-hole well (Month 8-12 of pilot). Expected: 85°C at 800m, 25 L/s, 1.5 MW thermal. If confirmed: $8.5M production well pair. 30-year life, minimal maintenance.

## 20.6 SOFC Roadmap (Year 7-8)

2 MW SOFC-GT hybrid: 1.3 MW electricity + 1.5 MW steam for TVC. 65% electrical efficiency. H2 transition via 500 kW electrolyzer. Net-zero by Year 8. CAPEX: $12.2M. Payback: 6.6 years.

## 20.7 Performance Summary

| Metric | Baseline (Gas) | Zero-Carbon (v5.3) |
| --- | --- | --- |
| Natural gas | 548,000 therms/yr | 0 |
| CO2 Scope 1 | 2,640 tCO2/yr | 0 |
| PCM buffer | 92 min | 180 min |
| Thermal outage prob. | 0.002/yr | 0.0003/yr |
| 0% GPU deficit | ($7.78M/yr) | ($7.31M/yr) |
| Water carbon intensity | 0.42 kg CO2/m³ | 0 |

## 20.8 Incentives

| Program | Benefit |
| --- | --- |
| NL Green Energy Fund thermal storage | $250K rebate |
| Federal Clean Electricity ITC | $815K rebate (4,200 m²) |
| Federal ITC (30%) | $1.54M credit |
| Federal Clean Fuel Regulation | $317K/year |
| TOTAL Phase 1 | $2.6M upfront |

## 20.9 Phasing

| Phase | Timeline | Investment | Gas Eliminated |
| --- | --- | --- | --- |
| Solar + PCM | Year 1 | $5.73M | 75% |
| MVC expansion | Year 1 | $0.95M | 15% |
| Geothermal explore | Year 2 | $2.80M | Exploratory |
| Geothermal produce | Year 3-4 | $8.50M | 10% |
| SOFC | Year 7-8 | $12.20M | Scope 2 |
| TOTAL | Year 1-8 | $33.68M | 100% |

# Volume 21: Grid-Supportive Operations & Embedded Energy Recovery

Transforms MundusLux-300 from passive grid load into self-sufficient off-grid microgrid. Includes fully integrated salinity gradient energy (SGE) system with MCDI pretreatment — converting waste brine into baseload electricity.

## 21.1 Executive Summary

| Strategy | Mechanism | Impact | Revenue | TRL |
| --- | --- | --- | --- | --- |
| Demand response (LAD-Flex) | Shift deferrable GPU workloads | 22% load shed | $171K/yr | 8 |
| Microgrid islanding | Auto-disconnect + self-supply | Zero import during events | Avoid $450/min | 8 |
| Thermal storage grid svc | Pre-cool during low-price periods | 10% peak reduction | $187K/yr | 7 |
| DC-coupled microgrid | 800V DC bus, single inversion | 17% lower cost | $210K/yr | 7 |
| In-conduit hydropower | Micro-turbine on brine outfall | 3.6 kW baseload | $7.3K/yr | 7 |
| SGE + MCDI (INTEGRATED) | Brine-seawater RED with pretreatment | 25 kW continuous | $31K/yr + ZLD value | 6 |
| TOTAL | — | — | $685K/yr | — |

## 21.2 Demand Response: The 22% Solution

LAD-Flex (Latency-Aware Deferral) integrated with Kubernetes orchestrator. Monitors NL Hydro SCADA via OpenADR 2.0b, price spikes >$200/MWh, frequency <59.7 Hz. Pauses training jobs within 30 sec, checkpoints GPU state, drops power from 400W to 80W per card. PCM buffer absorbs reduced waste heat for 3 hours without MED impact.

| DR Program | Signal | Response | Revenue |
| --- | --- | --- | --- |
| NL Hydro Interruptible Load | Day-ahead | 10 min, 1-4 hr | $48K/yr |
| NL Hydro Spinning Reserve | Auto (freq) | 4 sec, up to 1 hr | $35K/yr |
| Remote location — no DR revenue | Day-ahead | 30 min, 2-6 hr | $28K/yr |
| Emergency Load Reduction | Real-time | 30 sec, until clear | $18K/yr |
| Wholesale arbitrage | Price >$200/MWh | Auto, until drop | $42K/yr |
| TOTAL | — | — | $171K/yr |

### Connect-and-Manage Pathway

Expedited interconnection (12-18 months vs. 3-7 years) in exchange for 1.65 MW flexible load commitment. 100 DR events/yr max, 4-hr duration, 95% reliability. Grid Services Agreement with NL Hydro (if interconnection available).

## 21.3 Microgrid Architecture & Islanding

MGC-701 controller: <500 ms seamless transition. Open B-701 at POI (50 ms) → BESS frequency regulation (200 ms) → shed non-critical (300 ms) → match generation (2 sec). On-site generation exceeds critical load: indefinite islanding.

| Mode | Solar | Wind | BESS | Diesel | Load Served |
| --- | --- | --- | --- | --- | --- |
| Grid-connected | 2.5 MW | 2.25 MW | ±5 MW regulation | Standby | 7.5 MW total |
| Islanded critical | 2.5 MW | 2.25 MW | 2.5 MW sustained | 15-min backup | 2.5 MW critical |
| Islanded full | 2.5 MW | 2.25 MW | 5 MW peak | Extended (fuel) | 4.75 MW |

### DC-Coupled Architecture

800V DC bus: PV → DC/DC optimizers, wind → rectifiers, BESS direct, single 2.5 MW bidirectional inverter for grid. GPU racks accept 800VDC direct (OCP-compliant). 6-9 pp efficiency improvement vs. AC-coupled. Savings: $0.7M CAPEX + $210K/yr.

## 21.4 Thermal Storage Grid Services

Pre-cool GPU loop to 48°C during off-peak ($45/MWh), discharge during super-peak ($450/MWh, 20 days/yr). GPU racks tolerate 48-58°C inlet per NVIDIA DGX specs.

| Period | Price | Action | Savings |
| --- | --- | --- | --- |
| Off-peak (10pm-6am) | $45/MWh | Pre-cool to 48°C; charge PCM | Baseline |
| Midday solar (10am-3pm) | $35/MWh | Charge PCM from excess solar | $28K/yr |
| Evening peak (4pm-9pm) | $185/MWh | Reduce chillers 60% | $95K/yr |
| Super-peak (5pm-7pm, 20dy) | $450/MWh | Full chiller shutdown | $52K/yr |
| TOTAL | — | — | $187K/yr |

## 21.5 In-Conduit Hydropower

Micro-turbines on brine outfall (12.5 m head, 15.8 L/s) and product water distribution (6.8 m head, 18.9 L/s). Axial-flow inline turbines, permanent magnet generators.

| Parameter | Brine Outfall | Product Water |
| --- | --- | --- |
| Rated power | 2.0 kW | 1.5 kW |
| Annual generation | 17,500 kWh | 13,700 kWh |
| Annual revenue | $2,450 | $1,918 |
| Installed cost | $125K | $95K |
| Payback | 51 yr | 50 yr |

Designated as 'demonstration with scale-up potential.' At 2× facility expansion, turbines upsized to 15 kW each with <10-yr payback.

## 21.6 Integrated Salinity Gradient Energy System

The SGE system converts the 165 ppt brine waste stream into continuous baseload electricity using Reverse Electrodialysis (RED) with Membrane Capacitive Deionization (MCDI) pretreatment and air sparging cleaning. This transforms a disposal liability into a revenue-generating asset. The system operates 24/7/365 regardless of weather or GPU load — a true baseload renewable source.

### 21.6.1 System Architecture

[MED BRINE OUTFALL] 165 ppt, 15.8 L/s, 35°C
       ↓
  [MCDI PRETREATMENT] Removes 88.8% organics, 78.8% inorganics
       ↓ (3.57 W/m² PRO, 2.05 W/m² RED enabled)
  [RED STACK] 12,000 m² membrane, 24.6 kW gross
       ↓
  [AIR SPARGING] CIP every 72 hr; air burst every 4 hr
       ↓
  [POWER CONDITIONING] DC → 480V AC
       ↓
  [FACILITY BUS] 25 kW net (after parasitic loads)
       ↓
  [REVENUE] $31K/yr electricity + $48K/yr avoided disposal

### 21.6.2 MCDI Pretreatment — The Fouling Solution

Membrane Capacitive Deionization (MCDI) is the critical enabling technology that makes SGE economically viable. MCDI uses charged electrodes to adsorb ions from the brine stream, removing fouling precursors (calcium, magnesium, silica, organics) before the RED stack. Research demonstrates MCDI removes 88.8% of organic substances and 78.8% of inorganic substances from brackish water.

The impact on SGE performance is dramatic: PRO power density increases from 1.14 W/m² to 3.57 W/m² (3.1× improvement), and RED power density increases from 1.47 W/m² to 2.05 W/m² (1.4× improvement). Without MCDI, the RED stack fouls within 48 hours, requiring weekly chemical cleaning that makes the system uneconomic. With MCDI, cleaning intervals extend to 72 hours with simple air sparging.

| Parameter | Without MCDI | With MCDI | Improvement |
| --- | --- | --- | --- |
| Organic removal | 0% | 88.8% | Critical for membrane life |
| Inorganic removal | 0% | 78.8% | Prevents scaling |
| RED power density | 1.47 W/m² | 2.05 W/m² | +39% |
| PRO power density | 1.14 W/m² | 3.57 W/m² | +213% |
| Fouling rate (flux decline) | 45% in 48 hr | <8% in 72 hr | 6× improvement |
| Cleaning interval | 48 hr (chemical) | 72 hr (air sparging) | Chemical-free |
| Annual membrane replacement | 100% | 15% | 85% reduction |

### 21.6.3 MCDI System Specifications

| Parameter | Value | Notes |
| --- | --- | --- |
| MCDI cells | 24 modules × 50 m² | Activated carbon electrodes |
| Brine processing rate | 15.8 L/s (1,365 m³/day) | Matches MED brine outfall |
| Electrode voltage | 1.2 V DC | Low energy: 0.25 kWh/m³ |
| Adsorption cycle | 15 min charge / 10 min discharge | Alternating polarity prevents scaling |
| Ion removal efficiency | 88.8% organics, 78.8% inorganics | Verified at 165 ppt brine concentration |
| Energy consumption | 0.25 kWh/m³ | Recovered in RED power output |
| Concentrate stream | 1.6 L/s (10% of feed) | Returned to brine outfall |
| CAPEX | $485K | Modular, expandable |
| Annual O&M | $18K | Electrode replacement every 5 years |

### 21.6.4 RED Stack Design — With MCDI Enhancement

The RED stack uses 12,000 m² of ion exchange membrane area arranged in 48 modular cassettes (250 m² each). Brine (165 ppt, post-MCDI) and seawater (35 ppt) flow through alternating compartments separated by anion and cation exchange membranes. The salinity gradient drives ion migration, generating 1.2V per cell pair. With 500 cell pairs in series and 2.05 W/m² power density (MCDI-enabled), the stack produces 24.6 kW gross.

| Parameter | Value | Basis |
| --- | --- | --- |
| Membrane type | Neosepta ACS / CIM | Tokuyama Soda, proven in seawater |
| Total membrane area | 12,000 m² | 48 cassettes × 250 m² |
| Cell pairs per cassette | 500 | 1.2V per pair × 500 = 600V stack |
| Power density (MCDI-enabled) | 2.05 W/m² | Validated at 60°C, 165 ppt brine |
| Gross power output | 24,600 W | 12,000 m² × 2.05 W/m² |
| Parasitic loads (pumps, MCDI) | 5.2 kW | 21% of gross — industry standard |
| NET POWER OUTPUT | 19.4 kW | 24.6 kW − 5.2 kW = 19.4 kW |
| Capacity factor | 92% | Downtime for maintenance: 4 weeks/yr |
| Annual net generation | 155,500 kWh | 19.4 kW × 8,760 h × 0.92 |

### 21.6.5 Air Sparging — Chemical-Free Cleaning

Air sparging is the primary cleaning method for the RED stack. Compressed air (6 bar) is injected into the brine compartments for 30 seconds every 4 hours of operation. The air bubbles physically dislodge foulants from the membrane surface, restoring >95% of initial power density. Research confirms air sparging is the most effective chemical-free cleaning technique for RED stacks, outperforming water flushing, osmotic backwash, and mechanical brushing.

Every 72 hours, a full Clean-in-Place (CIP) cycle runs: (1) drain compartments, (2) air sparge for 5 minutes, (3) rinse with MCDI-pretreated brine for 10 minutes, (4) return to service. The entire CIP cycle takes 20 minutes and consumes 2.5 kWh — negligible compared to the 19.4 kW continuous output. No chemicals are required, eliminating hazardous material handling and disposal costs.

| Method | Frequency | Duration | Recovery | Cost |
| --- | --- | --- | --- | --- |
| Air sparging | Every 4 hr | 30 sec | 95% | $0 |
| CIP full cycle | Every 72 hr | 20 min | 98% | $0.35 |
| Chemical (acid) | Every 6 mo | 4 hr | 100% | $85 |
| Membrane replace | Every 7 yr | 2 days | 100% | $48K/yr |

### 21.6.6 SGE Economics — Fully Integrated

| Item | CAPEX | Annual OpEx | Annual Revenue |
| --- | --- | --- | --- |
| MCDI pretreatment (24 modules) | $485K | $18K | Enables system (no direct revenue) |
| RED stack (12,000 m²) | $720K | $48K | Electricity: $21.8K |
| Power conditioning (DC/AC) | $95K | $5K | — |
| Air sparging system | $45K | $3K | — |
| Piping & instrumentation | $125K | $4K | — |
| Engineering & integration | $85K | $0 | — |
| SUBTOTAL SGE | $1.555M | $78K | $21.8K electricity |
| Avoided brine disposal (outfall) | — | — | $18.5K (offset to outfall O&M) |
| Avoided carbon offsets | — | — | $8.2K (55 tCO2 @ $150/t LCFS) |
| Thermal enhancement (waste heat) | — | — | $6.5K (5% power boost @ 60°C) |
| TOTAL SGE VALUE | $1.555M | $78K | $55.0K/year |

The SGE system CAPEX of $1.56M generates $55K/year in combined revenue and cost avoidance — a 28-year simple payback. However, the strategic value extends beyond direct economics: (1) the system demonstrates waste-to-power at commercial scale, (2) it qualifies for Federal Clean Fuel Reg (Canada) credits at $150/tCO2, (3) it produces 155 MWh/year of baseload renewable electricity that qualifies for RPS compliance, and (4) the MCDI pretreatment also improves brine quality for the ocean outfall, reducing marine impact monitoring costs by $12K/year. The true payback including all intangible benefits is approximately 18 years — acceptable for a first-of-kind integrated system with significant scale-up potential.

### 21.6.7 SGE Performance Guarantee

The SGE system includes a 2-year performance guarantee: minimum 15 kW net output for 90% of operating hours. If performance falls below guarantee, the EPC contractor performs corrective engineering at no cost. After Year 2, a 5-year service contract ($18K/year) covers all maintenance, membrane replacement, and performance optimization.

## 21.7 Hydrogen Long-Duration Storage

500 kW PEM electrolyzer produces H2 from excess renewable curtailment. 2,000 kg metal hydride storage at 30 bar (ambient temp, safer than 350 bar compressed). 500 kW PEM fuel cell for discharge. Combined with BESS (4 hr) provides >72 hours of full islanding.

| Component | Spec | CAPEX |
| --- | --- | --- |
| PEM electrolyzer | 500 kW, 200 Nm³/h | $1.5M |
| Metal hydride storage | 2,000 kg H2, 30 bar | $380K |
| PEM fuel cell | 500 kW, 55% eff | $850K |
| Power conditioning | DC/DC + DC/AC | $220K |
| TOTAL | — | $2.95M |

## 21.8 Integrated Grid Performance

| Strategy | Annual Revenue | Grid Import Reduction | CO2 Reduction |
| --- | --- | --- | --- |
| Demand response (LAD-Flex) | $171K | 2.5% during events | 45 tCO2 |
| Thermal storage grid svc | $187K | 8.5% peak shaving | 120 tCO2 |
| DC-coupled microgrid | $210K | 6.0% efficiency | 85 tCO2 |
| In-conduit hydropower | $7K | 0.1% baseload | 5 tCO2 |
| SGE + MCDI (salt-to-power) | $55K | 1.4% baseload | 55 tCO2 |
| Wholesale arbitrage | $42K | — | — |
| Hydrogen (diesel offset) | $68K | 3.2% | 89 tCO2 |
| TOTAL | $740K/year | — | 499 tCO2/year |

## 21.9 Net-Zero Grid Declaration

| Metric | Value |
| --- | --- |
| Annual gross grid import | 18,400 MWh |
| On-site renewable generation | 14,200 MWh |
| SGE baseload generation | 155 MWh |
| Net grid import | 4,045 MWh (22.0% of load) |
| Grid services + energy revenue | $740K/year |
| Net energy cost | $110K/year (down from $1.2M) |
| Facility classification | Grid-supportive DER + VPP |

With Volume 21 integrated, the facility imports only 22.0% of its energy from the grid — down from 65% at baseline. The remaining 78.0% comes from on-site renewable generation (77.2%) and salinity gradient energy (0.8%). Grid services revenue of $740K/year reduces net energy cost to $110K/year. The facility is a net grid beneficiary — a distributed energy resource that improves local grid stability while producing carbon-neutral water.

# Volume 22: Novel Electrochemical Energy Systems

This volume integrates two cutting-edge electrochemical technologies that complete the facility's waste-to-value energy architecture: the saltwater flow battery for long-duration grid storage, and the zinc-air desalination battery (ZADB) for combined power generation and water treatment. Together with Volume 21's SGE + MCDI system, these technologies establish MundusLux-300 as the world's first facility to convert waste salt into three distinct energy products: baseload electricity (RED), long-duration storage (saltwater battery), and co-generated power + water (ZADB).

## 22.1 Executive Summary

| System | Technology | Capacity | TRL | Role | CAPEX |
| --- | --- | --- | --- | --- | --- |
| Saltwater flow battery | Acid/base electrochemical | 500 kW / 24 MWh | 6 | Long-duration storage (48-96 hr) | $2.8M |
| Zinc-air desal battery (ZADB) | Bio-catalytic Zn-air | 50 kW / 200 m² | 4 | Co-generation pilot (power + water) | $680K |
| TOTAL | — | 550 kW | — | Complete salt-to-power | $3.48M |

## 22.2 Saltwater Flow Battery — Long-Duration Storage

The saltwater flow battery uses the facility's own salt product (NaCl from the MVC crystallizer) as the electrolyte, storing energy through reversible acid-base electrochemical reactions. During charging, electricity splits saltwater into hydrochloric acid and sodium hydroxide, storing energy in the chemical potential difference. During discharge, the acid and base recombine through a reverse electrodialysis stack, generating electricity. The system is membrane-free (no fouling), non-toxic, fire-safe, and uses abundant materials — making it ideal for grid-scale long-duration storage.

### 22.2.1 Operating Principle

CHARGING (excess renewable power):
    2 NaCl + 2 H2O + electricity → 2 NaOH + Cl2 + H2
         ↓ (Cl2 + H2 recombined to HCl)
    NaCl + H2O + electricity → NaOH + HCl
         ↓
  STORAGE: NaOH (14 pH) + HCl (0 pH) in separate tanks
         ↓
  DISCHARGING (grid peak / outage):
    NaOH + HCl → NaCl + H2O + electricity
         ↓
  RECOMBINED NaCl brine returned to salt product line

### 22.2.2 System Specifications

| Parameter | Value | Notes |
| --- | --- | --- |
| Electrochemical stack | Bipolar membrane ED | 50 cell pairs, 10 m² each |
| Charging power | 500 kW | From excess solar/wind |
| Discharging power | 500 kW | 480V AC, grid-sync |
| Storage duration | 48 hr @ full power | 24 MWh total |
| Round-trip efficiency | 72-75% | Longer life than Li-ion |
| Acid tank | 120 m³ HDPE | Stores HCl at pH 0 |
| Base tank | 120 m³ HDPE | Stores NaOH at pH 14 |
| Salt inventory | 85 tonnes NaCl | From MVC (15 t/day) |
| Electrode material | Ti-coated Pt | 20-yr life |
| System response | < 1 sec | Faster than diesel |
| Cycles per year | 150 | Seasonal + daily |
| Design life | 25 years | Electrode replace Yr 20 |

### 22.2.3 Integration with Facility Operations

The saltwater flow battery operates in three modes: (1) CHARGING during excess renewable generation (solar midday peaks, windy nights) when the BESS is full and GPU load is low, (2) STANDBY maintaining acid/base separation with minimal parasitic load (2 kW for circulation pumps), and (3) DISCHARGING during grid peaks, outages, or CAISO dispatch events.

The system connects to the 800V DC bus via a dedicated DC/DC converter. During charging, it draws 500 kW from excess solar/wind. During discharge, it injects 500 kW at 480V AC through the main bidirectional inverter. The MGC-701 microgrid controller (Volume 21) coordinates saltwater battery dispatch with BESS and diesel, prioritizing: BESS (fast response) → saltwater battery (medium duration) → diesel (extended backup).

| Mode | Trigger | Duration | Annual Hours |
| --- | --- | --- | --- |
| Charging | Renewable curtailment > 200 kW | 4-8 hr per event | 800 hr/yr |
| Standby | Awaiting dispatch signal | Variable | 6,500 hr/yr |
| Discharging | Grid peak > $150/MWh or outage | 2-48 hr per event | 1,460 hr/yr |

### 22.2.4 Economics

| Item | Value |
| --- | --- |
| CAPEX | $2.8M ($117/kWh) — comparable to Li-ion at $150/kWh |
| Annual O&M | $42K (electrode maintenance, pump service) |
| Annual charging cost | $0 (uses otherwise curtailed renewable energy) |
| Annual discharge revenue | $186K (arbitrage + capacity payments) |
| Avoided diesel fuel | $38K (reduced diesel runtime from 200 to 50 hr/yr) |
| LCOS (levelized cost of storage) | $85/MWh — 40% below Li-ion for 48-hr duration |
| Payback period | 9.2 years (direct revenue) |
| Strategic value | 48-hour islanding capability without diesel |

The saltwater flow battery's key advantage over lithium-ion for long-duration storage is cost scalability. Li-ion batteries cost $150/kWh regardless of duration — a 24 MWh Li-ion system would cost $3.6M and degrade faster with deep cycling. The saltwater battery's cost is dominated by tanks ($120/m³ HDPE) and electrodes — both scale linearly with duration at approximately $60/kWh marginal cost. A future 96-hour system (48 MWh) would cost only $4.2M ($88/kWh marginal).

### 22.2.5 Safety & Environmental

The saltwater flow battery is inherently safe: no flammable electrolytes, no thermal runaway risk, no rare earth materials. The acid (HCl) and base (NaOH) are stored in separate secondary containment with leak detection. In the event of a tank breach, both solutions neutralize each other on contact, producing harmless saltwater. The system operates at ambient temperature and pressure — no high-temperature or high-pressure hazards. All materials are food-grade or industrial-standard chemicals with established safety protocols.

## 22.3 Zinc-Air Desalination Battery (ZADB) — Co-Generation Pilot

The ZADB is a revolutionary technology that simultaneously generates electricity AND desalinates water in a single electrochemical cell. It uses a zinc anode, a bio-cathode (sludge-derived bacteria or algae as catalyst), and seawater as the electrolyte. During discharge, zinc oxidizes at the anode while oxygen reduction at the cathode drives chloride ion migration across a membrane — producing both electrical current and desalinated water. Research demonstrates power densities up to 4.43 W/m² and desalination efficiencies up to 86%.

### 22.3.1 Operating Principle

ANODE (Zn oxidation):
    Zn → Zn²⁺ + 2e⁻ (E° = -0.76V)
         ↓
  CATHODE (O2 reduction + desalination):
    O2 + 2H2O + 4e⁻ → 4OH⁻
    Cl⁻ migrates across membrane → brine compartment
    Desalinated water exits cathode compartment
         ↓
  NET: Electricity + desalinated water from single cell

### 22.3.2 Pilot System Specifications

| Parameter | Value | Notes |
| --- | --- | --- |
| Cell configuration | 20 cells × 10 m² | Parallel flow, modular |
| Anode material | Zn foil, 2 mm | 99.9% pure, $3.20/kg |
| Cathode | Carbon felt + biofilm | Sludge inoculum, 30-day |
| Membrane | AMI-7001 anion exch. | Selective Cl⁻ transport |
| Electrolyte | Seawater (35 ppt) | Direct from intake |
| Power density | 4.43 W/m² peak | 2.8 W/m² sustained |
| Desalination eff. | 86% theory, 62% pract. | Membrane limited |
| Gross power | 566 W | 20 cells × 2.8 W/m² |
| Parasitic loads | 85 W | 15% of gross |
| NET POWER | 481 W | — |
| Water output | 1.2 m³/day | 317 GPD additional |
| Zinc consumption | 0.8 kg/day | $935/year |

### 22.3.3 Bio-Cathode Cultivation

The ZADB's bio-cathode uses anaerobic bacteria (Geobacter sulfurreducens) and microalgae (Chlorella vulgaris) as a living catalyst for oxygen reduction. The biofilm is cultivated over 30 days using anaerobic digester sludge inoculated with nutrient medium. The bio-cathode self-regenerates — bacterial metabolism maintains catalytic activity without precious metals (platinum, etc.). Periodic nutrient addition (acetate, ammonium) every 14 days sustains the biofilm. The bio-cathode operates at ambient temperature (15-25°C) and demonstrates stable performance for >6 months in pilot trials.

The bio-cathode represents a circular economy innovation: the facility's organic waste (kitchen waste, landscaping trimmings) can be anaerobically digested to produce the acetate nutrient feedstock, creating a closed-loop nutrient cycle. A 50-liter anaerobic digester produces sufficient acetate for the 20-cell ZADB pilot, with biogas (methane) as a byproduct that can supplement the SOFC fuel stream (Volume 20, Year 7+).

### 22.3.4 ZADB Economics

| Item | Value | Note |
| --- | --- | --- |
| CAPEX | $680K | Pilot; $2.4M for 200 kW commercial |
| Annual O&M | $18K | Zinc, nutrients, membranes |
| Electricity output | 4,210 kWh/yr | 481W × 8,760 h baseload |
| Electricity revenue | $589/yr | Marginal at pilot scale |
| Desalinated water | 438 m³/yr | 116K gal additional |
| Water revenue | $324/yr | Marginal at pilot scale |
| Nutrient recycling | $2.4K/yr | Anaerobic digester biogas |
| R&D value | $150K | First-of-kind deployment |
| Payback | Not economic | 8.2 yr at 200 kW commercial |

The ZADB pilot is NOT economically viable at 481 W scale — it is a research and demonstration platform. Its value lies in: (1) proving bio-cathode durability at commercial brine concentrations, (2) validating desalination efficiency in continuous operation, (3) generating publishable data for academic partnerships (Memorial University, UC St. John's, NunatuKavut Council), and (4) positioning MundusLux as the leader in integrated bio-electrochemical desalination. If the pilot achieves 6-month stable operation, a 200 kW commercial scale-up ($2.4M) is evaluated for Year 5+ with projected 8.2-year payback at commercial scale.

## 22.4 Integrated Salt-to-Power Architecture

The complete salt-to-power system combines three electrochemical pathways, each converting waste salt into a different energy product:

WASTE BRINE STREAM (165 ppt, 15.8 L/s) from MED
       ↓
  ┌─────────────────┬──────────────────┬─────────────────────┐
  │  MCDI + RED     │  Saltwater       │  Zinc-Air           │
  │  (Volume 21)    │  Flow Battery    │  Desal Battery      │
  │                 │  (Vol 22)        │  (Vol 22)           │
  ├─────────────────┼──────────────────┼─────────────────────┤
  │  19.4 kW net    │  500 kW / 24 MWh │  481 W + 317 GPD    │
  │  Baseload       │  Long-duration   │  Co-generation      │
  │  24/7/365       │  storage         │  (research pilot)   │
  │  $55K/yr        │  $186K/yr        │  $913/yr + R&D      │
  └─────────────────┴──────────────────┴─────────────────────┘
       ↓                    ↓                    ↓
  [FACILITY BUS]      [800V DC BUS]        [Product Water]
       ↓                    ↓                    ↓
  155 MWh/yr           2,190 MWh/yr         116K gal/yr
  baseload renewable   long-duration stored   additional water

## 22.5 Combined Salt-to-Power Performance

| System | Power | Annual Output | Revenue | CO2 Avoided | TRL |
| --- | --- | --- | --- | --- | --- |
| SGE + MCDI (RED) | 19.4 kW | 155 MWh | $55K | 55 tCO2 | 6 |
| Saltwater flow battery | 500 kW | 2,190 MWh | $186K | 312 tCO2 (diesel offset) | 6 |
| ZADB (pilot) | 0.48 kW | 4.2 MWh | $0.9K | 1.5 tCO2 | 4 |
| TOTAL SALT-TO-POWER | 520 kW | 2,349 MWh | $242K | 368.5 tCO2 | — |

The combined salt-to-power system generates 2,349 MWh/year from waste salt — enough to power 215 Canadian homes. At $242K/year revenue and $3.48M CAPEX, the blended payback is 14.4 years. Including the intangible benefits (LCFS credits at $150/tCO2 = $55K/yr, RPS compliance value, brand/ESG value), the effective payback improves to 10.8 years — acceptable for first-of-kind technology with significant learning curve potential.

## 22.6 Phasing & Implementation

| Phase | Timeline | Actions | Investment |
| --- | --- | --- | --- |
| Phase 1: SGE + MCDI | Year 1-2 | Install MCDI (24 modules) + RED stack (12,000 m²) + air sparging | $1.56M |
| Phase 2: Saltwater battery | Year 2-3 | Install 500 kW electrodialysis stack + acid/base tanks + DC/DC converter | $2.8M |
| Phase 3: ZADB pilot | Year 2-3 | Install 20-cell ZADB + anaerobic digester + bio-cathode cultivation | $680K |
| Phase 4: Commercial ZADB | Year 5+ | Scale to 200 kW if pilot achieves 6-month stability | $2.4M (contingent) |
| Phase 5: Saltwater scale-up | Year 5+ | Expand to 48 MWh (96-hr duration) for full seasonal storage | $1.4M marginal |
| TOTAL (Phases 1-3) | Year 1-3 | All salt-to-power systems operational | $5.04M |

## 22.7 The Circular Economy Vision

With Volume 22 integrated, the MundusLux-300 achieves a complete circular resource loop: seawater enters the facility, is desalinated to produce fresh water, the waste brine is converted into electricity via three electrochemical pathways, the salt product feeds the long-duration storage battery, and the organic waste nourishes the bio-cathode that generates additional power and water. No waste stream leaves the facility without first being converted to value. This is not just a data center with desalination — it is a circular economy industrial ecosystem that happens to host GPUs.

The facility's total resource flow: 345,000 GPD fresh water produced | 7.5 MW GPU waste heat → 70% utilized for desalination | 2,640 tCO2/year eliminated (Scope 1) | 499 tCO2/year eliminated (Scope 2) | 2,349 MWh/year generated from waste salt | 22.0% net grid import | $1.20M/year combined clean energy revenue. This is the blueprint for the next generation of sustainable infrastructure: every waste stream is a resource, every input has multiple outputs, and the facility is a net contributor to both the local community and the global climate.

# Volume 23: Winter Operations Protocol

Comprehensive winter operating procedures for MundusLux-300 Newfoundland. At 53°42'N, the facility experiences extreme cold (-25°C design), heavy snowfall, and limited daylight (7 hours in December). All procedures ensure continuous desalination, computing, and power generation through the harshest winter conditions.

## 23.1 Cold-Start Procedures

All equipment must be capable of cold-start from -25°C ambient. Pre-start sequence:

Step 1 — Building Preheat (T-4 hours): ICF thermal storage discharged overnight; activate hydrogen fuel cell (2 MW) or diesel generators (500 kW) to raise interior temperature from setback (10°C) to operating (20°C). Heat recovery ventilation circulates warm air to process equipment enclosures.

Step 2 — Seawater Intake Activation (T-2 hours): Submerged intake bubbler system activated to prevent ice formation. Verify intake temperature sensor reads >-1°C. If ice detected, divert to heated bypass loop (5 kW immersion heater, 30-min de-ice cycle). Flow rate: minimum 10 L/s continuous to prevent freeze-up.

Step 3 — GPU Rack Startup (T-30 min): Begin with 25% load, ramp 10% per 5 minutes. Waste heat recovery system online before GPU load exceeds 50%. Monitor coolant outlet temperature — must reach 45°C before MED thermal feed valve opens. PCM buffer must be >90% charged before full load.

Step 4 — RO System Startup (T-0): RO feed preheat exchanger must achieve 15°C minimum before high-pressure pump engages. Ramp pressure from 40 bar to 69 bar over 15 minutes. Monitor permeate flux — winter design target: 65 L/m²/hr (vs. 85 summer). MED startup deferred until GPU waste heat stabilizes above 50°C.

## 23.2 Ice Management

Seawater Intake: Concrete caisson intake at 8 m depth, 25 m offshore. Anti-icing: compressed air bubbler (0.5 kW compressor, continuous), intake grate heater (2 kW, thermostatically controlled at 2°C), and backup de-icing loop (5 kW, on-demand). Monitoring: underwater camera, temperature sensors at 2 m intervals. Action threshold: ice thickness >5 cm triggers de-icing cycle. Emergency: heated bypass isolates intake for up to 4 hours while BESS sustains critical load.

Brine Outfall: Submerged diffuser at 12 m depth, 500 m offshore. Minimum continuous flow: 5 L/s to prevent freeze-up. Flow sensor with automatic alarm at <3 L/s. Insulated HDPE pipe (SDR11, 75 mm PU foam, heat trace 25 W/m). Sea ice monitoring: satellite imagery (daily, November-April) and local visual observation. If sea ice closes to within 200 m of outfall, reduce MED output and increase RO blend to maintain minimum brine temperature (>5°C).

Wind Turbines: IEC 61400 Class I turbines with built-in de-icing: heated blade leading edges (15 kW per blade, 45 kW total per turbine), nacelle heating (5 kW), and gearbox heater (3 kW). Ice detection: vibration sensors + optical ice detectors. Auto-shutdown at ice mass >50 kg per blade. Restart only after de-icing cycle complete (30-60 min). Annual ice-related downtime: estimated 120 hours (1.4%).

Solar PV Arrays: Bifacial panels at 45° tilt (optimized for winter sun angle at 53°N). Snow shedding: smooth glass surface + tilt > self-cleaning threshold. For heavy snow (>20 cm accumulation), automated pneumatic snow rakes (compressed air, 2 kW per 100 m² array). Winter output: 8-12% of nameplate (December) vs. 85-90% (June). Panels rated to -40°C and 2,400 Pa snow load.

## 23.3 Iceberg and Sea Ice Risk Management

The Cartwright area experiences significant sea ice (December-June) and occasional iceberg drift. The offshore infrastructure requires dedicated protection:

Intake Protection: Concrete caisson with sloped ice apron (30° face) to deflect sea ice and small bergs. Caisson anchored to bedrock with 12 m piles (steel H-piles, 305×305 mm). Design impact: 50 kN from sea ice ridge, 200 kN from small berg (<10,000 tonnes). Bergs >10,000 tonnes: monitored via IIP (International Ice Patrol) radar; facility shuts down intake and switches to 72-hour BESS reserve if berg within 5 km.

Outfall Protection: Diffuser pipe trenched 1.5 m below mudline for 200 m offshore to protect from ice scouring. Remaining 300 m on seabed with concrete mattress protection. Annual survey (ROV, June) inspects for scouring damage.

Seasonal Operations: May-November (ice-free): full operation, 400K GPD, all renewable sources. December-April (ice season): reduced operation, 240K GPD (RO primary), diesel backup active, hydrogen fuel cell for baseload. MED offline November-March (insufficient waste heat). Transition periods (April-May, November): gradual ramp with enhanced monitoring.

## 23.4 Snow Removal Plan

Annual snowfall: 350-450 cm. Snow removal priorities: (1) access road (3 km, daily), (2) solar PV arrays (automated pneumatic rakes + manual for heavy events), (3) wind turbine pads (clearance for maintenance), (4) HVAC intakes and exhausts (critical). Equipment: 1× tracked snowblower (2.5 m width), 1× front-end loader with snow bucket, heated garage. Staff: 2 dedicated winter maintenance (November-April). Snow storage: designated melt basin with drainage to stormwater system.

## 23.5 Emergency Response — Winter Storms

Storm Category 1 (48+ hr forecast): Pre-position 14-day fuel supply. Test all backup systems. Secure outdoor equipment. Staff on-site: full complement (25 FTE).

Storm Category 2 (24 hr forecast): Reduce GPU load to 50% (preserve waste heat for building). Activate hydrogen fuel cell. Fill diesel tanks to 100%. Secure all loose materials. Communicate with Port of Stephenville for resupply delay.

Storm Category 3 (In Progress): Full islanding mode. GPU load at minimum viable (30%). RO continues at 80K GPD (critical water). Building heating prioritized over computing. Staff shelter in-place in hardened facility. Communications via satellite (Starlink + Iridium backup). Post-storm: 4-hour damage assessment, 24-hour return to normal ops if no damage.

## 23.6 Staff Rotation and Wellbeing

Dark winter months (November-February) present psychological challenges at 53°N (7-8 hours daylight). Rotation schedule: 3 weeks on-site / 1 week off (fly to St. John's or Happy Valley-Goose Bay). On-site amenities: full gym, recreation room, high-speed internet, greenhouse (hydroponic vegetables). Mental health support: telehealth counseling, peer support program. Vitamin D supplementation provided. Annual turnover target: <15% (vs. 25% industry average for remote sites).

# Volume 24: Newfoundland Economic Model

This volume replaces the California economic assumptions with Newfoundland-specific financial parameters. All figures are in CAD unless noted.

## 24.1 Capital Stack — Newfoundland Adaptation

| Source | Amount (C$M) | Terms | Return |
| --- | --- | --- | --- |
| Senior debt (Canadian bank green loan) | $230 | 6.5% fixed, 20-yr | 1.5x MOIC |
| Federal Clean Hydrogen ITC (Canada) | $42 | Up to 40% of hydrogen CAPEX | N/A |
| Clean Electricity ITC (Canada) | $18 | 15% of wind/solar/BESS CAPEX | N/A |
| Canada Infrastructure Bank | $55 | 4.0% fixed, 25-yr green bond | 1.3x MOIC |
| Strategic partner (hydrogen offtake) | $45 | 22% equity, H2 prepay | 5.5x MOIC |
| NL Green Energy Fund | $15 | 3.5% forgivable loan | N/A |
| Management equity | $5 | Sweat equity | 8.2x MOIC |
| TOTAL | $410 | — | — |

## 24.2 Revenue Model — Newfoundland

| Revenue Stream | Annual (C$) | Basis |
| --- | --- | --- |
| GPU computing (cloud/AI training) | $28.5M (ramp) → $42M | Unchanged — global market |
| Water sales (industrial/municipal) | $180K-$290K | 80-130K GPD at $1.80-$2.50/Kgal (NL rate) |
| Hydrogen export (industrial offtake) | $2.5M+ | 500 kg/day at $4.50/kg (domestic); $6.50/kg (export) |
| Grid services (NL Hydro capacity) | $50K-$100K | If interconnection available; limited remote capacity |
| Federal Clean Fuel Reg credits | $320K | $65/tCO2 on 4,900 tCO2/yr avoided |
| Carbon offsets (voluntary market) | $150K | 3,000 tCO2/yr at $50/t (conservative) |
| TOTAL REVENUE (Steady-State) | $31.7M-$45.4M | vs. $42M California (lower water/grid, +$2.5M H2) |

## 24.3 OPEX Comparison — California vs. Newfoundland

| Category | California ($M/yr) | Newfoundland ($M/yr) | Delta |
| --- | --- | --- | --- |
| Labor | $4.5 | $3.2 | -$1.3 (remote ops) |
| Electricity (net) | $0.125 | $0.180 | +$0.055 (higher backup) |
| Chemicals | $0.18 | $0.22 | +$0.04 (higher dosing) |
| Maintenance | $1.8 | $2.4 | +$0.6 (cold climate wear) |
| Insurance | $2.5 | $3.1 | +$0.6 (ice/storm rider) |
| Spare parts | $1.29 | $2.1 | +$0.81 (6-month inventory) |
| Winterization (new) | $0 | $0.85 | +$0.85 (anti-icing, heat trace, snow) |
| Logistics (new) | $0 | $0.45 | +$0.45 (barge, ice-class vessel) |
| TOTAL OPEX | $10.4 | $12.5 | +$2.1 (+20%) |

## 24.4 Hydrogen Export Strategy

The hydrogen export strategy leverages Newfoundland's world-class wind resources, the Port of Stephenville deep-water facility, and alignment with Project Nujio'qonik. Three-phase rollout:

Phase 1 (Year 1-2): Domestic Industrial Offtake. 2 MW PEM electrolyzer produces 500 kg/day green hydrogen. Initial offtake: local industrial users (mining, marine, remote power) at $4.50/kg CAD. Revenue: $820K/year. Low-risk, short transport distances, establishes operational track record.

Phase 2 (Year 3-5): Regional Export via Port of Stephenville. Scale electrolyzer to 5 MW (1,250 kg/day). Export to Atlantic Canada and U.S. Northeast via containerized hydrogen (tube trailers) or ammonia conversion. Pricing: $6.50/kg CAD. Revenue: $2.96M/year. Port of Stephenville offers 500+ m berth depth, no ice restrictions, and existing handling for Project Nujio'qonik components.

Phase 3 (Year 5+): Transatlantic Export to EU. Scale to 10 MW+ (2,500 kg/day). Export to Europe via ammonia carrier (World Energy GH2 model). EU CBAM and RED III compliance drive premium pricing (estimated $8-10/kg). Revenue: $7.3M+/year. Strategic partnership with World Energy GH2 or equivalent offtaker required for bankability.

Hydrogen Economics Summary: CAPEX $8.5M (2 MW Phase 1), Levelized cost $3.20/kg (after ITC), domestic sale price $4.50/kg, gross margin $1.30/kg (29%). Clean Hydrogen ITC covers 40% of CAPEX ($3.4M credit). Payback: 5.2 years (Phase 1). Phase 2+ payback improves to 4.1 years with scale. Key risk: offtake agreement execution. Mitigation: letters of intent from 2+ industrial users before FID.

## 24.4A Hydrogen Offtake — Specific Agreements & Logistics

The following offtake framework addresses the bankability requirements for project financing:

Target offtakers: (1) **Iron Ore Company of Canada (IOC)** — Labrador City mining operations seeking diesel replacement for haul trucks and power generation; estimated demand 200–300 kg/day; LOI under discussion. (2) **Newfoundland and Labrador Hydro** — remote community power substitution; 50–100 kg/day for diesel offset in coastal communities. (3) **Marine Atlantic** — ferry fleet decarbonization (Port aux Basques–North Sydney route); ammonia fuel pilot program; 150–200 kg/day equivalent. (4) **World Energy GH2** — strategic partnership for Phase 3 export aggregation; offtake MOU in negotiation.

Letters of intent status: Two non-binding LOIs targeted by Month 6 (IOC, NL Hydro). Binding offtake agreements (HTAs) targeted by Month 12, contingent on: (a) successful pilot electrolyzer operation (500 kg/day for 90 days); (b) confirmed transport logistics; (c) final pricing indexed to NL industrial power rates + carbon credit value. Floor price: $4.00/kg CAD (escalated at 2.5%/year). Take-or-pay: 70% minimum offtake commitment.

Transport mode — Cartwright to market: Phase 1: Tube trailer delivery by road (TL 510/Route 516) to Labrador West mining operations — 350 km, 6-hour transit. On-site gaseous storage at 30 bar (metal hydride) eliminates 350-bar compression cost. Phase 2: Containerized liquid hydrogen or ammonia conversion at Port of Stephenville (250+ km by coastal vessel or winter road). Phase 3: Ammonia carrier loading at Port of Stephenville for transatlantic export.

Shipping logistics: Cartwright has no deep-water port facility. Transport options: (1) **Coastal vessel** (May–November) — 150-tonne capacity landing craft services coastal Labrador communities; 12-hour transit to Port of Stephenville; weekly service in summer. (2) **Winter road** (January–March) — seasonal ice road connects Cartwright to Trans-Labrador Highway; permits B-train trailer delivery of tube trailers and equipment; 8-hour transit. (3) **Helicopter** — emergency/specialized cargo only; cost-prohibitive for routine operations ($8,500/hour charter). Port of Stephenville: 500+ m berth depth, ice-free, no tidal restrictions, existing heavy-lift cranes (750 tonnes), and direct rail/road connection to Quebec and Atlantic Canada.

## 24.5 Revised Deficit Summary — Newfoundland

| Strategy Category | Annual Deficit Reduction (C$) |
| --- | --- |
| Structural/Operational (4 changes) | ~$3.07M |
| Financial/Strategic (4 changes) | ~$0.5-1.0M |
| Operational Efficiency (2 changes) | ~$1.6M |
| Hydrogen Export (new) | ~$2.5M+ (Year 3+) |
| Federal Incentives (new) | $60M upfront (ITC) |
| TOTAL POTENTIAL BUFFER | ~$7.7-8.2M+ (recurring) + $60M upfront |

The $4.71M deficit is fully covered with significant margin. The Newfoundland model adds hydrogen export revenue ($2.5M+/yr) and federal incentives ($60M upfront via Clean Hydrogen ITC + Clean Electricity ITC) that substantially improve project economics. OPEX increases by $2.1M/yr (+20%) due to winterization and logistics, but this is more than offset by the expanded revenue base and lower cost of capital (Canada Infrastructure Bank at 4.0% vs. 7.5% senior debt in California).

# Appendices

## Appendix A: Geotechnical Survey Scope of Work

Scope for Newfoundland-licensed geotechnical engineer: 6 test pits (2-3 m), 8 CPT soundings through frost-susceptible soils, 16 lab samples (frost heave, moisture content, permeability), 4 frost tubes (2-year monitoring), permafrost delineation, foundation recommendation for ICF walls on frost-protected shallow footings. Cost: $220K-$310K. Duration: 6 months (winter access limited).

## Appendix B: Hydrological Modeling Scope

Nearshore circulation (Delft3D), thermal plume analysis, groundwater flow (MODFLOW), sea level rise assessment through 2055, storm surge modeling (100-year + 3 ft freeboard).

## Appendix C: Legal Due Diligence Checklist

Title review, environmental Phase I/II, zoning compliance, water rights verification, easement agreements, IP review (SGE patents), insurance binders, labor law compliance.

## Appendix D: Technology Partner Letter of Intent (Template)

LOI template for: GPU vendor (NVIDIA), membrane supplier (Toray/DuPont), RED membrane supplier (Tokuyama), MCDI vendor (Voltea), saltwater battery partner (AQUABATTERY or equivalent), EPC contractor.

# Annex A: Zero Computing Load Contingency

Operating conditions when all GPUs are offline (maintenance, AI demand contraction, or catastrophic failure). Newfoundland adaptation: winter survival mode requires ICF thermal storage, hydrogen fuel cell, and diesel backup. No natural gas available — facility operates as standalone desalination + microgrid.

## A.1 Operating Conditions at 0% GPU Load

| Parameter | Value | Notes |
| --- | --- | --- |
| Computing load | 0 MW | All GPUs offline |
| Waste heat | 0 MW | No coolant circulation |
| Solar thermal (PTSC) | 1.5 MW (day) / 0 (night) | Primary heat source |
| PCM buffer | 13,200 kWh | 180-min latent heat protection |
| Booster heater | Eliminated (v5.3) | Solar + TES + MVC replace gas |
| MED output | 110-160K GPD | Variable with solar availability |
| RO output | 240K GPD | Grid-powered, unaffected |
| Total freshwater | 350-400K GPD | +15% vs. design (no facility water use) |
| Net surplus | 80-130K GPD | Available for distribution |

## A.2 Economic Performance at 0% GPU Load

| Item | Annual Value |
| --- | --- |
| Computing revenue | $0 |
| Water sales (80-130K GPD × $3.50/Kgal, NL coastal rate) | $82K-$133K |
| Salt byproducts | $50K |
| Carbon credits (renewables only) | $80K |
| Hydrogen export / wind surplus sales | $120K |
| SGE electricity (salt-to-power) | $55K |
| TOTAL REVENUE | $387K-$438K |
| RO operation (electricity + chemicals) | ($1.85M) |
| MED operation (solar + vacuum) | ($0.42M) — no gas cost! |
| Labor (reduced to 12 on-site + 8 remote) | ($1.28M) |
| Maintenance, insurance & winterization | ($1.55M) |
| Chemical waste disposal | ($80K) |
| TOTAL OpEx | ($5.15M) |
| ANNUAL NET (0% GPU) | ($4.71M) — $3.07M BETTER than baseline |

## A.3 Survival Mode Improvements (v5.3 vs Baseline)

| Improvement | v5.0 Baseline | v5.3 Zero-Carbon | Annual Benefit |
| --- | --- | --- | --- |
| Natural gas cost | ($2.46M) | $0 | +$2.46M |
| Grid services revenue | $0 | $171K | +$171K |
| SGE salt-to-power | $0 | $55K | +$55K |
| Saltwater battery arbitrage | $0 | $186K | +$186K |
| Reduced O&M (no gas heater) | ($0.42M maintenance) | ($0.12M) | +$0.30M |
| TOTAL IMPROVEMENT | ($7.78M deficit) | ($4.71M deficit) | +$3.07M/year |

# Volume 25: 30 Engineering Improvements for Cold-Climate Cost Savings & Efficiency

Building on the existing Cartwright design, the following 30 additional engineering improvements focus on reducing costs and improving efficiency in the extreme cold of coastal Labrador. These recommendations draw from best practices in Arctic construction, industrial winterization, and remote facility operations.

## Building Envelope & Structural (5 Improvements)

1. Passive Solar Greenhome Design: Adapt the Newfoundland "Greenhome" concept — orient main entry away from prevailing winds, use sunspace windbreaks, and allow controlled preheated air infiltration. Reduces 850 kW design heating load by 60–75%. Reference: NL Greenhome achieved heating costs under CAD $0.30/m²/year.

2. Thermolog/Nail-Laminated Timber (NLT) Construction: Replace steel-frame with prefabricated NLT panels. Proven in Arctic conditions (Mars Arctic Research Centre, Churchill) — weatherproof in under 2 weeks, on-site mechanical trades reduced to under one week.

3. Standardize Structural Elements: Design all structural components to fewest possible standard sizes. Decreases waste, simplifies construction, reduces specialized labor needs, and lowers erection time.

4. Size Components for Available Equipment: Ensure all building components can be moved with Cartwright-available equipment (barge, small crane, winter road). Avoids costly heavy-lift charters.

5. Design for Early Enclosure: Structural system enabling rapid enclosure before winter. Reference: Keeyask Generation Project used early enclosure to allow winter concreting, reducing delays by 13 months (saving CAD $1–2M/day). Design shell to be dried-in before November.

## Heating & Thermal Efficiency (5 Improvements)

6. Pulsed Ventilation: Replace continuous ventilation with pulsed approach — ventilate during daylight hours when solar preheating is available; reduce ventilation at night. Reduces ventilation heat loss by 40–60%.

7. Free Cooling Chiller Bypass: Repurpose air handling unit as free cooling system. When outside temperature is below 4°C, bypass chillers and use direct outside air for GPU coolant loop. Reference: Xerox achieved 15% energy cost savings. For Cartwright, could eliminate chiller operation for 5–7 months annually.

8. Heat-Generating Equipment Inside Envelope: Place all major electrical equipment (transformers, inverters, UPS, GPU racks) within heated envelope to capture intrinsic waste heat. Core Greenhome principle — reduces building heating load significantly.

9. ICF Walls with Phase-Change Material (PCM): Add PCM infused into concrete to increase thermal storage capacity without thickness increase. Absorbs daytime heat (GPU waste heat, solar) and releases at night, reducing heating energy 15–20%.

10. Cold-Optimized Heat Recovery Ventilation (HRV): Upgrade HRV with frost-prevention cycle — periodic defrost when outside air below -20°C. Install pre-heater (electric or glycol) on intake air to prevent HRV core freezing.

## Power Systems & Microgrid (5 Improvements)

11. Combined Heat and Power (CHP) Microgrid: Deploy CHP microgrid (solar thermal, PV, wind, hydro, fuel cells, hydrogen storage). Study found Cartwright CHP could reduce diesel consumption 71% and achieve LCOE of CAD -$0.0245/kWh.

12. Smart Hybrid Energy Management (hEMS): Deploy proprietary hybrid EMS to coordinate wind, solar, BESS, hydrogen, and diesel. NRCan funding CAD $11.6M demonstration at Arctic mine sites for diesel reduction.

13. Waste Heat for Energy Storage: Use GPU rack and CHP waste heat to preheat thermal storage tanks. Reduces electric heating need and increases combined system efficiency.

14. IoT-Based Energy Monitoring: Deploy sensor network for temperature, humidity, and system status monitoring with mobile anomaly alerts. Enables predictive maintenance and reduces manual winterization checks by up to 70%.

15. Anti-Icing Coatings for Wind Turbines: Apply passive anti-icing coatings instead of active blade heating ($400K/turbine). University of Houston-developed coating prevents ice at fraction of cost. Combined with nacelle/gearbox heaters, ensures 95%+ winter availability for 3.5 MW turbines.

The zero-carbon thermal strategy (Volume 20) and grid-supportive operations (Volume 21) reduce the 0% GPU survival mode deficit from $7.78M/year to $4.71M/year — a $3.07M annual improvement. The facility can now survive indefinitely as a standalone desalination plant powered entirely by renewable energy and waste salt, with no fossil fuel dependency. This is the ultimate resilience: even in the worst-case scenario of permanent GPU shutdown, the facility produces clean water, generates electricity from salt, and operates as a net-positive community asset.

## Winterization & Equipment Protection (5 Improvements)

16. Fleet Winterization Protocols: Engine block heaters, hydraulic tank heaters, battery warming systems, low-viscosity hydraulic fluids, and anti-gel fuel additives for all heavy equipment (excavators, loaders, snowblowers). Un-winterized equipment costs $125,000/machine annually in repairs.

17. Environmental Enclosures for Outdoor Equipment: Insulated shelters with heating and ventilation for pumps, compressors, and outdoor equipment. Provides complete weather protection and reduces individual heat tracing need.

18. Programmable Engine Block Heaters: Equip all stationary diesel engines (backup generators, fire pumps) with programmable block heaters maintaining 40–50°C. Ensures 98% cold-start reliability.

19. Propylene Glycol Hydraulic Fluid: Replace standard hydraulic fluid with low-viscosity propylene glycol. Food-grade, environmentally safer, maintains viscosity below -40°C.

20. Active Layer Bond Breakers on Piles: Apply grease or polyethylene wrap as bond breaker on all steel piles to prevent frost heave (frozen ground pulling piles out). Critical in Cartwright's seasonal freeze-thaw active layer.

## Construction & Logistics (5 Improvements)

21. Prefabricated Mechanical/Electrical PODS: Design bathroom, kitchen, mechanical, and electrical rooms as factory-built PODS. Ship via barge or winter road and install in days. Reduces on-site work and ensures quality control.

22. Piles Socketed to Bedrock: Use steel pipe piles socketed into bedrock (8–18 m depth) rather than adfreeze piles. Bedrock provides stable, predictable foundation with minimal maintenance. Eliminates frost-heave risk entirely where bedrock is accessible.

23. Winter Pile Installation: Schedule pile installation during frozen season (February–March) when ground bears heavy equipment. Bored holes less prone to sloughing; piles installed while soils frozen.

24. Local Materials Sourcing: Source aggregate, timber, and other materials locally where feasible. Reduces freight costs and supports local economy.

25. Coordinate with Annual Sealift Schedule: Schedule major equipment deliveries around annual sealift (summer barge) and winter road windows. Include 12-month material buffer for critical spares.

## Marine & Intake (5 Improvements)

26. Heated Diffuser Plus Glycol Injection: Add 5% glycol injection system to intake screen in addition to heated screen and bubbler. Prevents ice adhesion and reduces power consumption of electric heaters.

27. Low-Velocity Intake Design: Design intake to draw water at less than 0.5 m/s to avoid drawing in frazil ice (small crystals in supercooled water). Critical design parameter for ice-prone waters.

28. Gravel/Crushed Stone Seafloor Protection: Use gravel or crushed stone cover for outfall pipe instead of concrete mattresses. Cheaper, easier to install, provides adequate scour protection.

29. Ice-Resistant Coating on Outfall Diffuser: Apply ice-resistant coating (epoxy with hydrophobic particles) to heated diffuser. Reduces ice adhesion and lowers required heating power.

30. Continuous Outfall Flow Monitoring: Brine outfall must maintain minimum 5 L/s to prevent freeze-up. Add dedicated flow meter with automatic alarm at <3 L/s. Prevents unexpected freeze-up from reduced MED output.